## Instructions
Throughput and Cycle Time Calculator
Version
| 1 | Initial Version
| 1.1 | Removed the IFNA and replaced with ISERROR to be compativle with ExCel 2010
| 1.2 | Added Work in Progress tab
| 1.3 | Added new charts, survey and sharing data tab.
| 1.31 | Fixed WIP calculation to include started work without a completion date (yet)
| 1.32 | Added a note after KLR15 feedback
| 1.4 | Added new cycle time chart. Thanks to twitter feedback: @joshuajames @kjscotland @smok77 @cyetain @jchyip @yuvalyeret
| 1.5 | Fixed defect in Started vs Completed Items per week chart range (was hardcoded)
| 1.6 | Fixed time issue of data inputs failing equal tests for any day based chart or measure
| 1.61 | Fixed indirect references for pasted blank cells which were failing with #VALUE errors.
| 1.62 | Fixed WIP axis range to include the most recent start or completed date to capture completed work more than one week past the prior. Issue 18.
| 1.7 | Added weibull estimate chart.
| 1.71 | Fixed issues of incorrect WIP calculation if an items completed more than one week beyond the last completed date.
What is this: This spreadsheet helps to probabilistically forecast how long it will take to complete features and stories based on range estimates.
How does it work? Given your estimates, this spreadsheet hypothetically completes all work 500 times. It calculates likelihood result as the number of simulated trials that finished on or before a given date.
Why is this better than burndowns and traditional Agile forecasting? Most forecasting techniques give a single date result and hide the likelihood of that date. Most often the date given as the result is 50% because work is divided by an average (or median). Thats the odds of a toin-coss. This method allows the reader to choose the amount of schedule risk they wish to sign-up for. 85% is a common middle ground used in the industry.
Is it reliable? It has no mathematical errors (that we know of!), and all we guarentee is its better than intuition alone and better than simple regression models. But, help us improve it by letting us know when it misses the actual results you are seeing.
How to: Fill in the orange boxes in the Forecast worksheet and read off the dates in the results table adjacent to the likelihood/certainty you think is appropriate. 85% is a common industry level of certainty used.
What is throughput? Where do I get that data? Throughput is the number of DONE stories completed by a team per week or per sprint (you choose in this spreadsheet, default is per week). We will be providing a viz that gathers this data for your team. Stay tuned.
What is this: This spreadsheet takes work item/story/defect data and creates throughput and cycle time data and charts.
How does it work? Throughput is calculated by counting the number of items that complete in the same calendar week (sunday to saturday). This data is reported on the Throughput worksheet. Cycle time is calculated by subtracting the completed date and the start date. This is the number of days between these dates. For items completing on the same day as they are started, you can override the default value to be used (rather than get zero).
How to: Get a list of completed dates (ata minimum) for each item in your electronic tracking tool. Enter this data in Column A in the "Your Data" worksheet. ptionally add the start date, and any other field values that help you manage this data.
Ideas, errors, requests? Email: troy.magennis@focusedobjective.com
Work licensed under a Creative Commons Attribution-NonCommercial-ShareAlike 4.0 International License.
Details here: http://creativecommons.org/licenses/by-nc-sa/4.0/ and
http://creativecommons.org/licenses/by-nc-sa/4.0/legalcode
Get more tools like this from: http://bit.ly/SimResources
About us: Focused Objective LLC offers tools, training and expert advice on metrics, risk and forecasting. We have more advanced tools to model Agile teams and projects that help analyze staffing options and risk, and a proven track record of positive results. We are always happy to discuss next steps and training opportunities should this tool prove useful. See our website: http://www.focusedobjective.com or email me at troy.magennis@focusedobjective.com.
Please don't by this book on Amazon; its out of date (we leave it there for people who insist on a hard-copy). Go to Bit.ly/agilesim as it says on the card and download for free.
Also - please hire us! we can help with metrics, forecasting and risk management of Agile projects. We are able to make these tools free because we are called upon for our expertise often. Either way, talk to us first before looking elsewhere!

## Your Data
Completed Date | Start Date (optional) | Type (optional) | Id (optional) | Description (optional)
2015-01-21 | 2015-01-14 | Story
2015-01-26 | 2015-01-14 | Story
2015-01-26 | 2015-01-14 | Defect
2015-01-26 | 2015-01-21
2015-01-26 | 2015-01-22
2015-01-29 | 2015-01-23
2015-02-02 | 2015-01-23
2015-02-02 | 2015-01-20
2015-02-02 | 2015-01-20
2015-02-04 | 2015-01-20
2015-02-04 | 2015-01-26
2015-02-04 | 2015-01-23
2015-02-04 | 2015-01-22
2015-02-04 | 2015-01-28
2015-02-05 | 2015-01-29
2015-02-05 | 2015-01-22
2015-02-06 | 2015-01-28
2015-02-09 | 2015-01-28
2015-02-09 | 2015-02-02
2015-02-09 | 2015-01-29
2015-02-10 | 2015-01-29
2015-02-11 | 2015-02-04
2015-02-11 | 2015-02-02
2015-02-12 | 2015-01-29
2015-02-16 | 2015-02-05
2015-02-17 | 2015-02-09
2015-02-17 | 2015-02-04
2015-02-17 | 2015-02-04
2015-02-17 | 2015-02-05
2015-02-17 | 2015-02-11
2015-02-18 | 2015-02-11
2015-02-23 | 2015-02-11
2015-02-23 | 2015-02-12
2015-02-23 | 2015-02-10
2015-02-24 | 2015-02-11
2015-02-24 | 2015-02-11
2015-02-24 | 2015-02-10
2015-02-25 | 2015-02-13
2015-02-25 | 2015-02-10
2015-02-25 | 2015-02-20
2015-02-25 | 2015-02-20
2015-02-26 | 2015-02-18
2015-02-27 | 2015-02-23
2015-02-27 | 2015-02-20
2015-02-27 | 2015-02-20
2015-02-27 | 2015-02-25
2015-02-27 | 2015-02-20
2015-03-02 | 2015-02-25
2015-03-03 | 2015-02-25
2015-03-04 | 2015-02-12
2015-03-04 | 2015-02-27
2015-03-05 | 2015-02-27
2015-03-05 | 2015-02-23
2015-03-05 | 2015-02-25
2015-03-06 | 2015-02-27
2015-03-06 | 2015-03-01
2015-03-09 | 2015-03-02
2015-03-10 | 2015-03-03
2015-03-10 | 2015-03-03
2015-03-10 | 2015-03-05
2015-03-10 | 2015-03-03
2015-03-10 | 2015-03-03
2015-03-10 | 2015-03-06
2015-03-10 | 2015-03-05
2015-03-11 | 2015-03-09
2015-03-12 | 2015-03-09
2015-03-12 | 2015-03-09
2015-03-17 | 2015-03-04
2015-03-17 | 2015-02-26
2015-03-17 | 2015-02-26
2015-03-17 | 2015-02-26
2015-03-19 | 2015-02-26
2015-03-19 | 2015-03-11
2015-03-20 | 2015-03-12
2015-03-20 | 2015-03-12
2015-03-20 | 2015-03-17
2015-03-20 | 2015-03-12
2015-03-23 | 2015-03-17
2015-03-24 | 2015-03-16
2015-03-24 | 2015-03-18
2015-03-26 | 2015-03-18
2015-03-26 | 2015-03-18
2015-03-26 | 2015-03-18
2015-03-31 | 2015-03-18
2015-04-02 | 2015-03-19
2015-04-02 | 2015-03-23
2015-04-02 | 2015-03-24
2015-04-02 | 2015-03-24
2015-04-02 | 2015-03-25
2015-04-03 | 2015-03-19
2015-04-06 | 2015-03-19
2015-04-06 | 2015-03-30
2015-04-07 | 2015-03-31
2015-04-08 | 2015-04-01
2015-04-08 | 2015-03-20
2015-04-08 | 2015-03-25
2015-04-09 | 2015-03-31
2015-04-09 | 2015-04-02
2015-04-09 | 2015-04-03
2015-04-10 | 2015-04-02
2015-04-10 | 2015-03-26
2015-04-10 | 2015-04-07
2015-04-14 | 2015-04-08
2015-04-14 | 2015-04-08
2015-04-16 | 2015-04-06
2015-04-16 | 2015-04-08
2015-04-16 | 2015-04-08
2015-04-17 | 2015-04-02
2015-04-20 | 2015-04-08
2015-04-22 | 2015-04-08
2015-04-22 | 2015-04-14
2015-04-23 | 2015-04-10
2015-04-23 | 2015-04-09
2015-04-23 | 2015-04-13
2015-04-23 | 2015-04-16
2015-04-24 | 2015-04-14
2015-04-27 | 2015-04-16
2015-04-27 | 2015-04-20
2015-04-27 | 2015-04-17
2015-04-27 | 2015-04-22
2015-04-28 | 2015-04-20
2015-04-28 | 2015-04-20
2015-04-30 | 2015-04-20
2015-05-01 | 2015-04-23
2015-05-04 | 2015-04-27
2015-05-04 | 2015-04-28
2015-05-05 | 2015-04-23
2015-05-06 | 2015-04-28
2015-05-06 | 2015-04-27
2015-05-06 | 2015-04-28
2015-05-08 | 2015-04-30
2015-05-08 | 2015-04-29
2015-05-11 | 2015-05-04
2015-05-11 | 2015-04-27
2015-05-11 | 2015-04-29
2015-05-12 | 2015-05-01
2015-05-12 | 2015-05-06
2015-05-12 | 2015-05-04
2015-05-13 | 2015-05-04
2015-05-13 | 2015-05-04
2015-05-13 | 2015-05-06
2015-05-06
2015-05-08
2015-05-12
2015-05-11
2015-05-12
2015-05-12
2015-05-06
2015-05-07
2015-05-12
2015-05-13
Put your data on this sheet.
For throughput: Only the completed date is needed.
For cycle-time and WIP, the completed date and start date is needed.
The Id and Description fields are just for your convenience.

## Settings
Cycle time value to use when items are completed on the same day as being started.
0.5

## Charts
This chart has "issues" but i want ideas -
1. the series are all different units
2. the date is wrong for the WIP series (off by 1 week)
3. its meant to infer trend and correlation, but because of the values in each unit, it looks like magnitude is important.
4. it doesnt resize to the amount of data.
Thinking: Normalizing each measure 0 (lowest) and 1 (highest) so we are comparing the same ranges as a proportion. And fixing the dates.
The word Cycle Time means different things to different people. For this spreadsheet, it is the calendar days between two dates. YOU have to define what those dates mean. Does Completed mean delivered to a customer? Does it mean handed off for deployment? The same issue with the start date.Is start when an item is comitted? or when i is created? Please be sure to document what this cycle time means and is captured consistently.
More discussion on the glossary of definitions for cycle time can be found here in a post by Andy Carmichael: http://xprocess.blogspot.co.uk/2015/05/glossary-proposal.html
if you feel strongly this should be renamed TiP (Time in process) then please email me: troy.magennis@focusedobjective.com
The actual vs estimate weibull curve fit chart shows how different the estimated Weibull distribution curve is from actual computed percentile values over the minimum to maximum range of cycle time data. If the actual versus estimated curves are "close" (plus or minus a day) then the data probably follows the Weibull distribution and we have confidence it is consistently captured. Don't be alarmed is the curves fail to match when there are fewer than 15 samples. Expect a match at 30+ samples or be suspicious of cycle time data. The shape and scale parameters can be used in most Monte Carlo simulation tools to represent cycle time distribution.

## Research Survey
What process does the team identify they are doing? |  |  | Not Answered | Other:
Does the team use sprints? If yes, How long are they? |  |  | Not Answered | Other:
What percentage of work is planned versus un-planned as a percentage?
Planned % | 80%
Un-planned % | 20%
Does your team have significant external team dependencies? For example, do you often get blocked waiting for another team to deliver a component or library?
Not Answered
How many people are on the team?
Predom Skillset | Count | Co-located?
Developers | 0 | Not Answered
Testers | 0 | Not Answered
Designers | 0 | Not Answered
Product Owners | 0 | Not Answered
Other:
| 0 | Not Answered
| 0 | Not Answered
| 0 | Not Answered
Please only use my email address |  |  | For questions only
Email address
Contact name
Please consider sharing this data for research. We are primarily interested in the start and stop dates, and this survey data. Industry cycle-time and throughput data will help improve the science of software development. If you do share, please enter as much information below as you care to share, remove any data you aren't willing to share from the "Your Data" worksheet, and then email us this spreadsheet: troy.magennis@focusedobjective.com
Privacy policy -
1. We will NEVER share you name or contact information with third parties
2. We request you opt-in to giving us your email address for clarifying questions or to send you regular updates on analysis depending on what you request when submitting to us
3. We will NEVER share the organization name or contact name when sharing this data with other researchers
We WILL publish this data (without identifying information) using the Attribution-ShareAlike 4.0 International: http://creativecommons.org/licenses/by-sa/4.0/ for research purposes.
Checklist:
1. Remove any data you aren't willing to share from the "Your Data" worksheet
2. Fill in as much of this survey as you are willing to share
3. Email us this spreadsheet: troy.magennis@focusedobjective.com
Thank you.

## Throughput
Week Starting | Week Ending | week groups | Throughput | Normalized | CSV | Percentiles
2015-01-18 | 2015-01-24 | 2015-04 | 1 | 0 | 1 | min | 5% | 25% | 50% | 75% | 95% | max
2015-01-25 | 2015-01-31 | 2015-05 | 5 | 0.26667 | 1,5 | 1 | 4.2 | 7 | 8 | 10 | 12.8 | 16
2015-02-01 | 2015-02-07 | 2015-06 | 11 | 0.66667 | 1,5,11
2015-02-08 | 2015-02-14 | 2015-07 | 7 | 0.4 | 1,5,11,7 | Bin | Frequency
2015-02-15 | 2015-02-21 | 2015-08 | 7 | 0.4 | 1,5,11,7,7 | 1 | 1
2015-02-22 | 2015-02-28 | 2015-09 | 16 | 1 | 1,5,11,7,7,16 | 2 | 0
2015-03-01 | 2015-03-07 | 2015-10 | 9 | 0.53333 | 1,5,11,7,7,16,9 | 3 | 0
2015-03-08 | 2015-03-14 | 2015-11 | 11 | 0.66667 | 1,5,11,7,7,16,9,11 | 4 | 0
2015-03-15 | 2015-03-21 | 2015-12 | 10 | 0.6 | 1,5,11,7,7,16,9,11,10 | 5 | 1
2015-03-22 | 2015-03-28 | 2015-13 | 6 | 0.33333 | 1,5,11,7,7,16,9,11,10,6 | 6 | 2
2015-03-29 | 2015-04-04 | 2015-14 | 7 | 0.4 | 1,5,11,7,7,16,9,11,10,6,7 | 7 | 3
2015-04-05 | 2015-04-11 | 2015-15 | 12 | 0.73333 | 1,5,11,7,7,16,9,11,10,6,7,12 | 8 | 3
2015-04-12 | 2015-04-18 | 2015-16 | 6 | 0.33333 | 1,5,11,7,7,16,9,11,10,6,7,12,6 | 9 | 2
2015-04-19 | 2015-04-25 | 2015-17 | 8 | 0.46667 | 1,5,11,7,7,16,9,11,10,6,7,12,6,8 | 10 | 1
2015-04-26 | 2015-05-02 | 2015-18 | 8 | 0.46667 | 1,5,11,7,7,16,9,11,10,6,7,12,6,8,8 | 11 | 2
2015-05-03 | 2015-05-09 | 2015-19 | 8 | 0.46667 | 1,5,11,7,7,16,9,11,10,6,7,12,6,8,8,8 | 12 | 1
2015-05-10 | 2015-05-16 | 2015-20 | 9 | 0.53333 | 1,5,11,7,7,16,9,11,10,6,7,12,6,8,8,8,9 | 13 | 0
[6 empty] | 14 | 0
[6 empty] | 15 | 0
[6 empty] | 16 | 1
[6 empty] | 17 | 0
[6 empty] | 18 | 0
[6 empty] | 19 | 0
[6 empty] | 20 | 0
[6 empty] | 21 | 0
Formulas:
Week Starting = IF(ISNUMBER([Week Starting, row above]),IF([Week Starting, row above]+7<=MAX(PriorSundays),[Week Starting, row above]+7,""),"")
Week Ending = IF(ISNUMBER([Week Starting]),[Week Starting]+6,"")
week groups = IF(ISNUMBER([Week Starting]),YEAR([Week Starting])&"-"&TEXT(WEEKNUM([Week Starting]),"00"),"")

## Cycle Time
Completed Date | Week Group | Cycle Time (days) | CSV | 50% | 75% | 95% | Week Starting | Week Ending | week groups | Min Cycle Time | Avg Cycle Time | Max Cycle Time | 25th Percentile | 30th | Median | 70th | 75th Percentile | 85th | Percentiles
2015-01-21 | 2015-04 | 7 | 7 | 8 | 12 | 15 | 2015-01-18 | 2015-01-24 | 2015-04 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Min | 0.05 | 0.25 | 0.5 | 0.75 | 0.95 | Max
2015-01-26 | 2015-05 | 12 | 7,12 | 8 | 12 | 15 | 2015-01-25 | 2015-01-31 | 2015-05 | 4 | 7.8 | 12 | 5 | 5.2 | 6 | 10.8 | 12 | 12 | 2 | 4 | 7 | 8 | 12 | 15 | 21
2015-01-26 | 2015-05 | 12 | 7,12,12 | 8 | 12 | 15 | 2015-02-01 | 2015-02-07 | 2015-06 | 7 | 11.0909 | 15 | 9 | 9 | 12 | 13 | 13 | 13.5
2015-01-26 | 2015-05 | 5 | 7,12,12,5 | 8 | 12 | 15 | 2015-02-08 | 2015-02-14 | 2015-07 | 7 | 10.2857 | 14 | 8 | 8.6 | 11 | 12 | 12 | 12.2 | Bin | Frequency
2015-01-26 | 2015-05 | 4 | 7,12,12,5,4 | 8 | 12 | 15 | 2015-02-15 | 2015-02-21 | 2015-08 | 6 | 10 | 13 | 7.5 | 7.8 | 11 | 12.2 | 12.5 | 13 | 2 | 2
2015-01-29 | 2015-05 | 6 | 7,12,12,5,4,6 | 8 | 12 | 15 | 2015-02-22 | 2015-02-28 | 2015-09 | 2 | 9.25 | 15 | 6.5 | 7 | 9.5 | 12.5 | 13 | 13 | 3 | 4
2015-02-02 | 2015-06 | 10 | 7,12,12,5,4,6,10 | 8 | 12 | 15 | 2015-03-01 | 2015-03-07 | 2015-10 | 5 | 8 | 20 | 5 | 5.4 | 6 | 7.6 | 8 | 9.6 | 4 | 3
2015-02-02 | 2015-06 | 13 | 7,12,12,5,4,6,10,13 | 8 | 12 | 15 | 2015-03-08 | 2015-03-14 | 2015-11 | 2 | 5.1818 | 7 | 3.5 | 4 | 5 | 7 | 7 | 7 | 5 | 9
2015-02-02 | 2015-06 | 13 | 7,12,12,5,4,6,10,13,13 | 8 | 12 | 15 | 2015-03-15 | 2015-03-21 | 2015-12 | 3 | 12.6 | 21 | 8 | 8 | 10.5 | 19 | 19 | 19 | 6 | 11
2015-02-04 | 2015-06 | 15 | 7,12,12,5,4,6,10,13,13,15 | 8 | 12 | 15 | 2015-03-22 | 2015-03-28 | 2015-13 | 6 | 7.3333 | 8 | 6.5 | 7 | 8 | 8 | 8 | 8 | 7 | 24
2015-02-04 | 2015-06 | 9 | 7,12,12,5,4,6,10,13,13,15,9 | 8 | 12 | 15 | 2015-03-29 | 2015-04-04 | 2015-14 | 8 | 11.1429 | 15 | 9 | 9 | 10 | 13.2 | 13.5 | 14.1 | 8 | 23
2015-02-04 | 2015-06 | 12 | 7,12,12,5,4,6,10,13,13,15,9,12 | 8 | 12 | 15 | 2015-04-05 | 2015-04-11 | 2015-15 | 3 | 10 | 19 | 7 | 7 | 7.5 | 12.5 | 14.25 | 16.05 | 9 | 10
2015-02-04 | 2015-06 | 13 | 7,12,12,5,4,6,10,13,13,15,9,12,13 | 8 | 12 | 15 | 2015-04-12 | 2015-04-18 | 2015-16 | 6 | 8.8333 | 15 | 6.5 | 7 | 8 | 9 | 9.5 | 11.25 | 10 | 8
2015-02-04 | 2015-06 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7 | 8 | 12 | 15 | 2015-04-19 | 2015-04-25 | 2015-17 | 7 | 11 | 14 | 9.5 | 10 | 11 | 12.9 | 13.25 | 13.95 | 11 | 5
2015-02-05 | 2015-06 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7 | 8 | 12 | 15 | 2015-04-26 | 2015-05-02 | 2015-18 | 5 | 8.375 | 11 | 7.75 | 8 | 8 | 9.8 | 10 | 10 | 12 | 11
2015-02-05 | 2015-06 | 14 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14 | 8 | 12 | 15 | 2015-05-03 | 2015-05-09 | 2015-19 | 6 | 8.375 | 12 | 7.75 | 8 | 8 | 8.9 | 9 | 9 | 13 | 11
2015-02-06 | 2015-06 | 9 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9 | 8 | 12 | 15 | 2015-05-10 | 2015-05-16 | 2015-20 | 6 | 9.2222 | 14 | 7 | 7.4 | 9 | 10.2 | 11 | 11.8 | 14 | 8
2015-02-09 | 2015-07 | 12 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12 | 8 | 12 | 15 | [12 empty] | 15 | 5
2015-02-09 | 2015-07 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7 | 8 | 12 | 15 | [12 empty] | 16 | 0
2015-02-09 | 2015-07 | 11 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11 | 8 | 12 | 15 | [12 empty] | 17 | 0
2015-02-10 | 2015-07 | 12 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12 | 8 | 12 | 15 | [12 empty] | 18 | 1
2015-02-11 | 2015-07 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7 | 8 | 12 | 15 | [12 empty] | 19 | 4
2015-02-11 | 2015-07 | 9 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9 | 8 | 12 | 15 | [12 empty] | 20 | 1
2015-02-12 | 2015-07 | 14 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14 | 8 | 12 | 15 | [12 empty] | 21 | 1
2015-02-16 | 2015-08 | 11 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11 | 8 | 12 | 15
2015-02-17 | 2015-08 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8 | 8 | 12 | 15
2015-02-17 | 2015-08 | 13 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13 | 8 | 12 | 15
2015-02-17 | 2015-08 | 13 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13 | 8 | 12 | 15
2015-02-17 | 2015-08 | 12 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12 | 8 | 12 | 15
2015-02-17 | 2015-08 | 6 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6 | 8 | 12 | 15
2015-02-18 | 2015-08 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7 | 8 | 12 | 15
2015-02-23 | 2015-09 | 12 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12 | 8 | 12 | 15
2015-02-23 | 2015-09 | 11 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11 | 8 | 12 | 15
2015-02-23 | 2015-09 | 13 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13 | 8 | 12 | 15
2015-02-24 | 2015-09 | 13 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13 | 8 | 12 | 15
2015-02-24 | 2015-09 | 13 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13 | 8 | 12 | 15
2015-02-24 | 2015-09 | 14 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14 | 8 | 12 | 15
2015-02-25 | 2015-09 | 12 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12 | 8 | 12 | 15
2015-02-25 | 2015-09 | 15 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15 | 8 | 12 | 15
2015-02-25 | 2015-09 | 5 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5 | 8 | 12 | 15
2015-02-25 | 2015-09 | 5 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5 | 8 | 12 | 15
2015-02-26 | 2015-09 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8 | 8 | 12 | 15
2015-02-27 | 2015-09 | 4 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4 | 8 | 12 | 15
2015-02-27 | 2015-09 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7 | 8 | 12 | 15
2015-02-27 | 2015-09 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7 | 8 | 12 | 15
2015-02-27 | 2015-09 | 2 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2 | 8 | 12 | 15
2015-02-27 | 2015-09 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7 | 8 | 12 | 15
2015-03-02 | 2015-10 | 5 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5 | 8 | 12 | 15
2015-03-03 | 2015-10 | 6 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6 | 8 | 12 | 15
2015-03-04 | 2015-10 | 20 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20 | 8 | 12 | 15
2015-03-04 | 2015-10 | 5 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5 | 8 | 12 | 15
2015-03-05 | 2015-10 | 6 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6 | 8 | 12 | 15
2015-03-05 | 2015-10 | 10 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10 | 8 | 12 | 15
2015-03-05 | 2015-10 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8 | 8 | 12 | 15
2015-03-06 | 2015-10 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7 | 8 | 12 | 15
2015-03-06 | 2015-10 | 5 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5 | 8 | 12 | 15
2015-03-09 | 2015-11 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7 | 8 | 12 | 15
2015-03-10 | 2015-11 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7 | 8 | 12 | 15
2015-03-10 | 2015-11 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7 | 8 | 12 | 15
2015-03-10 | 2015-11 | 5 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5 | 8 | 12 | 15
2015-03-10 | 2015-11 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7 | 8 | 12 | 15
2015-03-10 | 2015-11 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7 | 8 | 12 | 15
2015-03-10 | 2015-11 | 4 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4 | 8 | 12 | 15
2015-03-10 | 2015-11 | 5 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5 | 8 | 12 | 15
2015-03-11 | 2015-11 | 2 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2 | 8 | 12 | 15
2015-03-12 | 2015-11 | 3 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3 | 8 | 12 | 15
2015-03-12 | 2015-11 | 3 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3 | 8 | 12 | 15
2015-03-17 | 2015-12 | 13 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13 | 8 | 12 | 15
2015-03-17 | 2015-12 | 19 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19 | 8 | 12 | 15
2015-03-17 | 2015-12 | 19 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19 | 8 | 12 | 15
2015-03-17 | 2015-12 | 19 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19 | 8 | 12 | 15
2015-03-19 | 2015-12 | 21 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21 | 8 | 12 | 15
2015-03-19 | 2015-12 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8 | 8 | 12 | 15
2015-03-20 | 2015-12 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8 | 8 | 12 | 15
2015-03-20 | 2015-12 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8 | 8 | 12 | 15
2015-03-20 | 2015-12 | 3 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3 | 8 | 12 | 15
2015-03-20 | 2015-12 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8 | 8 | 12 | 15
2015-03-23 | 2015-13 | 6 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6 | 8 | 12 | 15
2015-03-24 | 2015-13 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8 | 8 | 12 | 15
2015-03-24 | 2015-13 | 6 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6 | 8 | 12 | 15
2015-03-26 | 2015-13 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8 | 8 | 12 | 15
2015-03-26 | 2015-13 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8 | 8 | 12 | 15
2015-03-26 | 2015-13 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8 | 8 | 12 | 15
2015-03-31 | 2015-14 | 13 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13 | 8 | 12 | 15
2015-04-02 | 2015-14 | 14 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14 | 8 | 12 | 15
2015-04-02 | 2015-14 | 10 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10 | 8 | 12 | 15
2015-04-02 | 2015-14 | 9 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9 | 8 | 12 | 15
2015-04-02 | 2015-14 | 9 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9 | 8 | 12 | 15
2015-04-02 | 2015-14 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8 | 8 | 12 | 15
2015-04-03 | 2015-14 | 15 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15 | 8 | 12 | 15
2015-04-06 | 2015-15 | 18 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18 | 8 | 12 | 15
2015-04-06 | 2015-15 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7 | 8 | 12 | 15
2015-04-07 | 2015-15 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7 | 8 | 12 | 15
2015-04-08 | 2015-15 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7 | 8 | 12 | 15
2015-04-08 | 2015-15 | 19 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19 | 8 | 12 | 15
2015-04-08 | 2015-15 | 14 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14 | 8 | 12 | 15
2015-04-09 | 2015-15 | 9 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9 | 8 | 12 | 15
2015-04-09 | 2015-15 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7 | 8 | 12 | 15
2015-04-09 | 2015-15 | 6 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6 | 8 | 12 | 15
2015-04-10 | 2015-15 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8 | 8 | 12 | 15
2015-04-10 | 2015-15 | 15 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15 | 8 | 12 | 15
2015-04-10 | 2015-15 | 3 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3 | 8 | 12 | 15
2015-04-14 | 2015-16 | 6 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6 | 8 | 12 | 15
2015-04-14 | 2015-16 | 6 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6 | 8 | 12 | 15
2015-04-16 | 2015-16 | 10 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10 | 8 | 12 | 15
2015-04-16 | 2015-16 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8 | 8 | 12 | 15
2015-04-16 | 2015-16 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8 | 8 | 12 | 15
2015-04-17 | 2015-16 | 15 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15 | 8 | 12 | 15
2015-04-20 | 2015-17 | 12 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12 | 8 | 12 | 15
2015-04-22 | 2015-17 | 14 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14 | 8 | 12 | 15
2015-04-22 | 2015-17 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8 | 8 | 12 | 15
2015-04-23 | 2015-17 | 13 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13 | 8 | 12 | 15
2015-04-23 | 2015-17 | 14 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14 | 8 | 12 | 15
2015-04-23 | 2015-17 | 10 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10 | 8 | 12 | 15
2015-04-23 | 2015-17 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7 | 8 | 12 | 15
2015-04-24 | 2015-17 | 10 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10 | 8 | 12 | 15
2015-04-27 | 2015-18 | 11 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11 | 8 | 12 | 15
2015-04-27 | 2015-18 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7 | 8 | 12 | 15
2015-04-27 | 2015-18 | 10 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10 | 8 | 12 | 15
2015-04-27 | 2015-18 | 5 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5 | 8 | 12 | 15
2015-04-28 | 2015-18 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8 | 8 | 12 | 15
2015-04-28 | 2015-18 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8 | 8 | 12 | 15
2015-04-30 | 2015-18 | 10 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10 | 8 | 12 | 15
2015-05-01 | 2015-18 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8 | 8 | 12 | 15
2015-05-04 | 2015-19 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7 | 8 | 12 | 15
2015-05-04 | 2015-19 | 6 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6 | 8 | 12 | 15
2015-05-05 | 2015-19 | 12 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12 | 8 | 12 | 15
2015-05-06 | 2015-19 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8 | 8 | 12 | 15
2015-05-06 | 2015-19 | 9 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9 | 8 | 12 | 15
2015-05-06 | 2015-19 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8 | 8 | 12 | 15
2015-05-08 | 2015-19 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8 | 8 | 12 | 15
2015-05-08 | 2015-19 | 9 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9 | 8 | 12 | 15
2015-05-11 | 2015-20 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9,7 | 8 | 12 | 15
2015-05-11 | 2015-20 | 14 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9,7,14 | 8 | 12 | 15
2015-05-11 | 2015-20 | 12 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9,7,14,12 | 8 | 12 | 15
2015-05-12 | 2015-20 | 11 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9,7,14,12,11 | 8 | 12 | 15
2015-05-12 | 2015-20 | 6 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9,7,14,12,11,6 | 8 | 12 | 15
2015-05-12 | 2015-20 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9,7,14,12,11,6,8 | 8 | 12 | 15
2015-05-13 | 2015-20 | 9 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9,7,14,12,11,6,8,9 | 8 | 12 | 15
2015-05-13 | 2015-20 | 9 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9,7,14,12,11,6,8,9,9 | 8 | 12 | 15
2015-05-13 | 2015-20 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9,7,14,12,11,6,8,9,9,7 | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
The word Cycle Time means different things to different people. For this spreadsheet, it is the calendar days between two dates. YOU have to define what those dates mean. Does Completed mean delivered to a customer? Does it mean handed off for deployment? The same issue with the start date.Is start when an item is comitted? or when i is created? Please be sure to document what this cycle time means and is captured consistently.
More discussion on the glossary of definitions for cycle time can be found here in a post by Andy Carmichael: http://xprocess.blogspot.co.uk/2015/05/glossary-proposal.html
if you feel strongly this should be renamed TiP (Time in process) then please email me: troy.magennis@focusedobjective.com

## Work in Progress
Date | Year-WeekNum | Work in Progress | Count Started | Count Completed | Cum Started | Cumulative Completed | Week Starting Sunday | Year-WeekNum | Min WIP | Avg WIP | Max WIP | Started this Week | Complete this Week | Delta | Start Cumulative | Complete Cumulative
2015-01-14 | 2015-03 | 3 | 3 | 0 | 3 | 0 | 2015-01-11 | 2015-03 | 3 | 3 | 3 | 3 | 0 | -3 | 3 | 0
2015-01-15 | 2015-03 | 3 | 0 | 0 | 3 | 0 | 2015-01-18 | 2015-04 | 3 | 7.2857 | 12 | 10 | 1 | -9 | 13 | 1
2015-01-16 | 2015-03 | 3 | 0 | 0 | 3 | 0 | 2015-01-25 | 2015-05 | 9 | 12.4286 | 15 | 8 | 5 | -3 | 21 | 6
2015-01-17 | 2015-03 | 3 | 0 | 0 | 3 | 0 | 2015-02-01 | 2015-06 | 11 | 12.7143 | 15 | 7 | 11 | 4 | 28 | 17
2015-01-18 | 2015-04 | 3 | 0 | 0 | 3 | 0 | 2015-02-08 | 2015-07 | 9 | 13.1429 | 16 | 12 | 7 | -5 | 40 | 24
2015-01-19 | 2015-04 | 3 | 0 | 0 | 3 | 0 | 2015-02-15 | 2015-08 | 10 | 13 | 16 | 6 | 7 | 1 | 46 | 31
2015-01-20 | 2015-04 | 6 | 3 | 0 | 6 | 0 | 2015-02-22 | 2015-09 | 11 | 12.7143 | 15 | 13 | 16 | 3 | 59 | 47
2015-01-21 | 2015-04 | 6 | 1 | 1 | 7 | 1 | 2015-03-01 | 2015-10 | 13 | 13.8571 | 16 | 10 | 9 | -1 | 69 | 56
2015-01-22 | 2015-04 | 9 | 3 | 0 | 10 | 1 | 2015-03-08 | 2015-11 | 8 | 10.1429 | 15 | 7 | 11 | 4 | 76 | 67
2015-01-23 | 2015-04 | 12 | 3 | 0 | 13 | 1 | 2015-03-15 | 2015-12 | 8 | 10.8571 | 14 | 12 | 10 | -2 | 88 | 77
2015-01-24 | 2015-04 | 12 | 0 | 0 | 13 | 1 | 2015-03-22 | 2015-13 | 11 | 11.2857 | 13 | 6 | 6 | 0 | 94 | 83
2015-01-25 | 2015-05 | 12 | 0 | 0 | 13 | 1 | 2015-03-29 | 2015-14 | 11 | 12.2857 | 14 | 8 | 7 | -1 | 102 | 90
2015-01-26 | 2015-05 | 9 | 1 | 4 | 14 | 5 | 2015-04-05 | 2015-15 | 10 | 11.4286 | 14 | 10 | 12 | 2 | 112 | 102
2015-01-27 | 2015-05 | 9 | 0 | 0 | 14 | 5 | 2015-04-12 | 2015-16 | 10 | 10.4286 | 11 | 6 | 6 | 0 | 118 | 108
2015-01-28 | 2015-05 | 12 | 3 | 0 | 17 | 5 | 2015-04-19 | 2015-17 | 9 | 10.8571 | 13 | 7 | 8 | 1 | 125 | 116
2015-01-29 | 2015-05 | 15 | 4 | 1 | 21 | 6 | 2015-04-26 | 2015-18 | 8 | 10 | 11 | 10 | 8 | -2 | 135 | 124
2015-01-30 | 2015-05 | 15 | 0 | 0 | 21 | 6 | 2015-05-03 | 2015-19 | 11 | 12.7143 | 14 | 10 | 8 | -2 | 145 | 132
2015-01-31 | 2015-05 | 15 | 0 | 0 | 21 | 6 | 2015-05-10 | 2015-20 | 10 | 11.5 | 13 | 6 | 9 | 3 | 151 | 141
2015-02-01 | 2015-06 | 15 | 0 | 0 | 21 | 6
2015-02-02 | 2015-06 | 14 | 2 | 3 | 23 | 9
2015-02-03 | 2015-06 | 14 | 0 | 0 | 23 | 9
2015-02-04 | 2015-06 | 12 | 3 | 5 | 26 | 14
2015-02-05 | 2015-06 | 12 | 2 | 2 | 28 | 16
2015-02-06 | 2015-06 | 11 | 0 | 1 | 28 | 17
2015-02-07 | 2015-06 | 11 | 0 | 0 | 28 | 17
2015-02-08 | 2015-07 | 11 | 0 | 0 | 28 | 17
2015-02-09 | 2015-07 | 9 | 1 | 3 | 29 | 20
2015-02-10 | 2015-07 | 11 | 3 | 1 | 32 | 21
2015-02-11 | 2015-07 | 14 | 5 | 2 | 37 | 23
2015-02-12 | 2015-07 | 15 | 2 | 1 | 39 | 24
2015-02-13 | 2015-07 | 16 | 1 | 0 | 40 | 24
2015-02-14 | 2015-07 | 16 | 0 | 0 | 40 | 24
2015-02-15 | 2015-08 | 16 | 0 | 0 | 40 | 24
2015-02-16 | 2015-08 | 15 | 0 | 1 | 40 | 25
2015-02-17 | 2015-08 | 10 | 0 | 5 | 40 | 30
2015-02-18 | 2015-08 | 10 | 1 | 1 | 41 | 31
2015-02-19 | 2015-08 | 10 | 0 | 0 | 41 | 31
2015-02-20 | 2015-08 | 15 | 5 | 0 | 46 | 31
2015-02-21 | 2015-08 | 15 | 0 | 0 | 46 | 31
2015-02-22 | 2015-09 | 15 | 0 | 0 | 46 | 31
2015-02-23 | 2015-09 | 14 | 2 | 3 | 48 | 34
2015-02-24 | 2015-09 | 11 | 0 | 3 | 48 | 37
2015-02-25 | 2015-09 | 11 | 4 | 4 | 52 | 41
2015-02-26 | 2015-09 | 14 | 4 | 1 | 56 | 42
2015-02-27 | 2015-09 | 12 | 3 | 5 | 59 | 47
2015-02-28 | 2015-09 | 12 | 0 | 0 | 59 | 47
2015-03-01 | 2015-10 | 13 | 1 | 0 | 60 | 47
2015-03-02 | 2015-10 | 13 | 1 | 1 | 61 | 48
2015-03-03 | 2015-10 | 16 | 4 | 1 | 65 | 49
2015-03-04 | 2015-10 | 15 | 1 | 2 | 66 | 51
2015-03-05 | 2015-10 | 14 | 2 | 3 | 68 | 54
2015-03-06 | 2015-10 | 13 | 1 | 2 | 69 | 56
2015-03-07 | 2015-10 | 13 | 0 | 0 | 69 | 56
2015-03-08 | 2015-11 | 13 | 0 | 0 | 69 | 56
2015-03-09 | 2015-11 | 15 | 3 | 1 | 72 | 57
2015-03-10 | 2015-11 | 8 | 0 | 7 | 72 | 64
2015-03-11 | 2015-11 | 8 | 1 | 1 | 73 | 65
2015-03-12 | 2015-11 | 9 | 3 | 2 | 76 | 67
2015-03-13 | 2015-11 | 9 | 0 | 0 | 76 | 67
2015-03-14 | 2015-11 | 9 | 0 | 0 | 76 | 67
2015-03-15 | 2015-12 | 9 | 0 | 0 | 76 | 67
2015-03-16 | 2015-12 | 10 | 1 | 0 | 77 | 67
2015-03-17 | 2015-12 | 8 | 2 | 4 | 79 | 71
2015-03-18 | 2015-12 | 13 | 5 | 0 | 84 | 71
2015-03-19 | 2015-12 | 14 | 3 | 2 | 87 | 73
2015-03-20 | 2015-12 | 11 | 1 | 4 | 88 | 77
2015-03-21 | 2015-12 | 11 | 0 | 0 | 88 | 77
2015-03-22 | 2015-13 | 11 | 0 | 0 | 88 | 77
2015-03-23 | 2015-13 | 11 | 1 | 1 | 89 | 78
2015-03-24 | 2015-13 | 11 | 2 | 2 | 91 | 80
2015-03-25 | 2015-13 | 13 | 2 | 0 | 93 | 80
2015-03-26 | 2015-13 | 11 | 1 | 3 | 94 | 83
2015-03-27 | 2015-13 | 11 | 0 | 0 | 94 | 83
2015-03-28 | 2015-13 | 11 | 0 | 0 | 94 | 83
2015-03-29 | 2015-14 | 11 | 0 | 0 | 94 | 83
2015-03-30 | 2015-14 | 12 | 1 | 0 | 95 | 83
2015-03-31 | 2015-14 | 13 | 2 | 1 | 97 | 84
2015-04-01 | 2015-14 | 14 | 1 | 0 | 98 | 84
2015-04-02 | 2015-14 | 12 | 3 | 5 | 101 | 89
2015-04-03 | 2015-14 | 12 | 1 | 1 | 102 | 90
2015-04-04 | 2015-14 | 12 | 0 | 0 | 102 | 90
2015-04-05 | 2015-15 | 12 | 0 | 0 | 102 | 90
2015-04-06 | 2015-15 | 11 | 1 | 2 | 103 | 92
2015-04-07 | 2015-15 | 11 | 1 | 1 | 104 | 93
2015-04-08 | 2015-15 | 14 | 6 | 3 | 110 | 96
2015-04-09 | 2015-15 | 12 | 1 | 3 | 111 | 99
2015-04-10 | 2015-15 | 10 | 1 | 3 | 112 | 102
2015-04-11 | 2015-15 | 10 | 0 | 0 | 112 | 102
2015-04-12 | 2015-16 | 10 | 0 | 0 | 112 | 102
2015-04-13 | 2015-16 | 11 | 1 | 0 | 113 | 102
2015-04-14 | 2015-16 | 11 | 2 | 2 | 115 | 104
2015-04-15 | 2015-16 | 11 | 0 | 0 | 115 | 104
2015-04-16 | 2015-16 | 10 | 2 | 3 | 117 | 107
2015-04-17 | 2015-16 | 10 | 1 | 1 | 118 | 108
2015-04-18 | 2015-16 | 10 | 0 | 0 | 118 | 108
2015-04-19 | 2015-17 | 10 | 0 | 0 | 118 | 108
2015-04-20 | 2015-17 | 13 | 4 | 1 | 122 | 109
2015-04-21 | 2015-17 | 13 | 0 | 0 | 122 | 109
2015-04-22 | 2015-17 | 12 | 1 | 2 | 123 | 111
2015-04-23 | 2015-17 | 10 | 2 | 4 | 125 | 115
2015-04-24 | 2015-17 | 9 | 0 | 1 | 125 | 116
2015-04-25 | 2015-17 | 9 | 0 | 0 | 125 | 116
2015-04-26 | 2015-18 | 9 | 0 | 0 | 125 | 116
2015-04-27 | 2015-18 | 8 | 3 | 4 | 128 | 120
2015-04-28 | 2015-18 | 9 | 3 | 2 | 131 | 122
2015-04-29 | 2015-18 | 11 | 2 | 0 | 133 | 122
2015-04-30 | 2015-18 | 11 | 1 | 1 | 134 | 123
2015-05-01 | 2015-18 | 11 | 1 | 1 | 135 | 124
2015-05-02 | 2015-18 | 11 | 0 | 0 | 135 | 124
2015-05-03 | 2015-19 | 11 | 0 | 0 | 135 | 124
2015-05-04 | 2015-19 | 13 | 4 | 2 | 139 | 126
2015-05-05 | 2015-19 | 12 | 0 | 1 | 139 | 127
2015-05-06 | 2015-19 | 13 | 4 | 3 | 143 | 130
2015-05-07 | 2015-19 | 14 | 1 | 0 | 144 | 130
2015-05-08 | 2015-19 | 13 | 1 | 2 | 145 | 132
2015-05-09 | 2015-19 | 13 | 0 | 0 | 145 | 132
2015-05-10 | 2015-20 | 13 | 0 | 0 | 145 | 132
2015-05-11 | 2015-20 | 11 | 1 | 3 | 146 | 135
2015-05-12 | 2015-20 | 12 | 4 | 3 | 150 | 138
2015-05-13 | 2015-20 | 10 | 1 | 3 | 151 | 141
Formulas:
Date = IF(ISNUMBER([Date, row above]),IF([Date, row above]+1<=MAX(IndirectStartDates,IndirectCompletedDates),[Date, row above]+1,""),"")
Year-WeekNum = IF(ISNUMBER([Date]),YEAR([Date])&"-"&TEXT(WEEKNUM([Date]),"00"),"")
Year-WeekNum = IF(ISNUMBER([Week Starting Sunday]),YEAR([Week Starting Sunday])&"-"&TEXT(WEEKNUM([Week Starting Sunday]),"00"),"")
Week Starting Sunday = IF(ISNUMBER([Week Starting Sunday, row above]),IF([Week Starting Sunday, row above]+7<=MAX(IndirectStartDates,IndirectCompletedDates),[Week Starting Sunday, row above]+7,""),"")

## Weibull
Best fit |  |  |  | Estimated Weibull Parameters | All |  |  | Chart title | Cycle time Actual vs Estimate Weibull Curve Fit Estimated parameters - shape:2.69 scale:10.27
30% | 7 |  |  | Shape | 2.6916
70% | 11 |  |  | Scale | 10.2669
p | actual | estimated | rounded days |  | x | y | cum est
5% | 4 | 3.4056 | 3 |  | 2 | 0.016275 | 0.012168
10% | 5 | 4.4498 | 4 |  | 2.19 | 0.018912 | 0.015508
15% | 6 | 5.2272 | 5 |  | 2.38 | 0.021684 | 0.019363
20% | 6 | 5.8806 | 6 |  | 2.57 | 0.024582 | 0.023756
25% | 7 | 6.4627 | 6 |  | 2.76 | 0.027594 | 0.028711
30% | 7 | 7 | 7 |  | 2.95 | 0.030707 | 0.034248
35% | 7 | 7.5086 | 8 |  | 3.14 | 0.03391 | 0.040386
40% | 8 | 7.9994 | 8 |  | 3.33 | 0.037189 | 0.047139
45% | 8 | 8.4808 | 8 |  | 3.52 | 0.040532 | 0.054521
50% | 8 | 8.9599 | 9 |  | 3.71 | 0.043926 | 0.062544
55% | 9 | 9.4435 | 9 |  | 3.9 | 0.047356 | 0.071216
60% | 9 | 9.9388 | 10 |  | 4.09 | 0.050809 | 0.080541
65% | 10 | 10.4541 | 10 |  | 4.28 | 0.05427 | 0.090524
70% | 11 | 11 | 11 |  | 4.47 | 0.057724 | 0.10116
75% | 12 | 11.5916 | 12 |  | 4.66 | 0.061157 | 0.11246
80% | 13 | 12.2526 | 12 |  | 4.85 | 0.064554 | 0.1244
85% | 13 | 13.0245 | 13 |  | 5.04 | 0.0679 | 0.13698
90% | 14 | 13.9963 | 14 |  | 5.23 | 0.071179 | 0.1502
95% | 15 | 15.4339 | 15 |  | 5.42 | 0.074378 | 0.16403
100% | 21 | 21 | 21 |  | 5.61 | 0.077481 | 0.17846
[5 empty] | 5.8 | 0.080474 | 0.19346
[5 empty] | 5.99 | 0.083344 | 0.20903
[5 empty] | 6.18 | 0.086076 | 0.22513
[5 empty] | 6.37 | 0.088659 | 0.24173
[5 empty] | 6.56 | 0.09108 | 0.25881
[5 empty] | 6.75 | 0.093327 | 0.27633
[5 empty] | 6.94 | 0.09539 | 0.29426
[5 empty] | 7.13 | 0.09726 | 0.31256
[5 empty] | 7.32 | 0.098927 | 0.3312
[5 empty] | 7.51 | 0.10038 | 0.35014
[5 empty] | 7.7 | 0.10162 | 0.36934
[5 empty] | 7.89 | 0.10264 | 0.38875
[5 empty] | 8.08 | 0.10344 | 0.40833
[5 empty] | 8.27 | 0.104 | 0.42804
[5 empty] | 8.46 | 0.10433 | 0.44783
[5 empty] | 8.65 | 0.10444 | 0.46767
[5 empty] | 8.84 | 0.10431 | 0.4875
[5 empty] | 9.03 | 0.10395 | 0.50729
[5 empty] | 9.22 | 0.10338 | 0.52699
[5 empty] | 9.41 | 0.10258 | 0.54656
[5 empty] | 9.6 | 0.10157 | 0.56596
[5 empty] | 9.79 | 0.10035 | 0.58514
[5 empty] | 9.98 | 0.098935 | 0.60408
[5 empty] | 10.17 | 0.097331 | 0.62273
[5 empty] | 10.36 | 0.095549 | 0.64105
[5 empty] | 10.55 | 0.093599 | 0.65903
[5 empty] | 10.74 | 0.091492 | 0.67661
[5 empty] | 10.93 | 0.089242 | 0.69378
[5 empty] | 11.12 | 0.086862 | 0.71051
[5 empty] | 11.31 | 0.084364 | 0.72678
[5 empty] | 11.5 | 0.081762 | 0.74257
[5 empty] | 11.69 | 0.079071 | 0.75785
[5 empty] | 11.88 | 0.076304 | 0.77261
[5 empty] | 12.07 | 0.073474 | 0.78684
[5 empty] | 12.26 | 0.070597 | 0.80053
[5 empty] | 12.45 | 0.067686 | 0.81366
[5 empty] | 12.64 | 0.064753 | 0.82625
[5 empty] | 12.83 | 0.061813 | 0.83827
[5 empty] | 13.02 | 0.058877 | 0.84973
[5 empty] | 13.21 | 0.055957 | 0.86064
[5 empty] | 13.4 | 0.053065 | 0.871
[5 empty] | 13.59 | 0.050211 | 0.88081
[5 empty] | 13.78 | 0.047405 | 0.89008
[5 empty] | 13.97 | 0.044656 | 0.89883
[5 empty] | 14.16 | 0.041973 | 0.90706
[5 empty] | 14.35 | 0.039361 | 0.91478
[5 empty] | 14.54 | 0.036829 | 0.92202
[5 empty] | 14.73 | 0.034382 | 0.92878
[5 empty] | 14.92 | 0.032023 | 0.93509
[5 empty] | 15.11 | 0.029759 | 0.94096
[5 empty] | 15.3 | 0.027591 | 0.9464
[5 empty] | 15.49 | 0.025521 | 0.95145
[5 empty] | 15.68 | 0.023552 | 0.95611
[5 empty] | 15.87 | 0.021684 | 0.9604
[5 empty] | 16.06 | 0.019918 | 0.96436
[5 empty] | 16.25 | 0.018252 | 0.96798
[5 empty] | 16.44 | 0.016686 | 0.9713
[5 empty] | 16.63 | 0.015218 | 0.97433
[5 empty] | 16.82 | 0.013846 | 0.97709
[5 empty] | 17.01 | 0.012567 | 0.97959
[5 empty] | 17.2 | 0.011379 | 0.98187
[5 empty] | 17.39 | 0.010278 | 0.98392
[5 empty] | 17.58 | 0.0092605 | 0.98578
[5 empty] | 17.77 | 0.0083235 | 0.98745
[5 empty] | 17.96 | 0.0074629 | 0.98895
[5 empty] | 18.15 | 0.0066747 | 0.99029
[5 empty] | 18.34 | 0.0059548 | 0.99149
[5 empty] | 18.53 | 0.0052992 | 0.99255
[5 empty] | 18.72 | 0.004704 | 0.9935
[5 empty] | 18.91 | 0.004165 | 0.99435
[5 empty] | 19.1 | 0.0036784 | 0.99509
[5 empty] | 19.29 | 0.0032403 | 0.99575
[5 empty] | 19.48 | 0.002847 | 0.99632
[5 empty] | 19.67 | 0.002495 | 0.99683
[5 empty] | 19.86 | 0.0021809 | 0.99728
[5 empty] | 20.05 | 0.0019013 | 0.99766
[5 empty] | 20.24 | 0.0016532 | 0.998
[5 empty] | 20.43 | 0.0014337 | 0.99829
[5 empty] | 20.62 | 0.00124 | 0.99855
[5 empty] | 20.81 | 0.0010697 | 0.99877
[5 empty] | 21 | 0.00092025 | 0.99895

## Share Data
Throughput
CSV | 1,5,11,7,7,16,9,11,10,6,7,12,6,8,8,8,9
SIP 2.0 | <sip name="dist" type="CSV" ver="1.0">1,5,11,7,7,16,9,11,10,6,7,12,6,8,8,8,9</sip>
Kanban/Scrum Sim Distribution | <distribution name="dist" shape="fromSamples">1,5,11,7,7,16,9,11,10,6,7,12,6,8,8,8,9</distribution>
Cycle Time
CSV | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9,7,14,12,11,6,8,9,9,7
SIP 2.0 | <sip name="dist" type="CSV" ver="1.0">7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9,7,14,12,11,6,8,9,9,7</sip>
Kanban/Scrum Sim Distribution | <distribution name="dist" shape="fromSamples">7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9,7,14,12,11,6,8,9,9,7</distribution>
These are industry standard formats for sharing data with other people and applications.

## Calculations (hidden)
Indirect Completed Dates | Indirect Start Dates | Prior Complete Sunday | Year Complete | WeekNumber Complete | Year-Week Complete | Prior Start Sunday | Year Start | WeekNumber Start | Year-Week Start | Cycle Time (days)
2015-01-21 | 2015-01-14 | 2015-01-18 | 2015 | 4 | 2015-04 | 2015-01-11 | 2015 | 3 | 2015-03 | 7
2015-01-26 | 2015-01-14 | 2015-01-25 | 2015 | 5 | 2015-05 | 2015-01-11 | 2015 | 3 | 2015-03 | 12
2015-01-26 | 2015-01-14 | 2015-01-25 | 2015 | 5 | 2015-05 | 2015-01-11 | 2015 | 3 | 2015-03 | 12
2015-01-26 | 2015-01-21 | 2015-01-25 | 2015 | 5 | 2015-05 | 2015-01-18 | 2015 | 4 | 2015-04 | 5
2015-01-26 | 2015-01-22 | 2015-01-25 | 2015 | 5 | 2015-05 | 2015-01-18 | 2015 | 4 | 2015-04 | 4
2015-01-29 | 2015-01-23 | 2015-01-25 | 2015 | 5 | 2015-05 | 2015-01-18 | 2015 | 4 | 2015-04 | 6
2015-02-02 | 2015-01-23 | 2015-02-01 | 2015 | 6 | 2015-06 | 2015-01-18 | 2015 | 4 | 2015-04 | 10
2015-02-02 | 2015-01-20 | 2015-02-01 | 2015 | 6 | 2015-06 | 2015-01-18 | 2015 | 4 | 2015-04 | 13
2015-02-02 | 2015-01-20 | 2015-02-01 | 2015 | 6 | 2015-06 | 2015-01-18 | 2015 | 4 | 2015-04 | 13
2015-02-04 | 2015-01-20 | 2015-02-01 | 2015 | 6 | 2015-06 | 2015-01-18 | 2015 | 4 | 2015-04 | 15
2015-02-04 | 2015-01-26 | 2015-02-01 | 2015 | 6 | 2015-06 | 2015-01-25 | 2015 | 5 | 2015-05 | 9
2015-02-04 | 2015-01-23 | 2015-02-01 | 2015 | 6 | 2015-06 | 2015-01-18 | 2015 | 4 | 2015-04 | 12
2015-02-04 | 2015-01-22 | 2015-02-01 | 2015 | 6 | 2015-06 | 2015-01-18 | 2015 | 4 | 2015-04 | 13
2015-02-04 | 2015-01-28 | 2015-02-01 | 2015 | 6 | 2015-06 | 2015-01-25 | 2015 | 5 | 2015-05 | 7
2015-02-05 | 2015-01-29 | 2015-02-01 | 2015 | 6 | 2015-06 | 2015-01-25 | 2015 | 5 | 2015-05 | 7
2015-02-05 | 2015-01-22 | 2015-02-01 | 2015 | 6 | 2015-06 | 2015-01-18 | 2015 | 4 | 2015-04 | 14
2015-02-06 | 2015-01-28 | 2015-02-01 | 2015 | 6 | 2015-06 | 2015-01-25 | 2015 | 5 | 2015-05 | 9
2015-02-09 | 2015-01-28 | 2015-02-08 | 2015 | 7 | 2015-07 | 2015-01-25 | 2015 | 5 | 2015-05 | 12
2015-02-09 | 2015-02-02 | 2015-02-08 | 2015 | 7 | 2015-07 | 2015-02-01 | 2015 | 6 | 2015-06 | 7
2015-02-09 | 2015-01-29 | 2015-02-08 | 2015 | 7 | 2015-07 | 2015-01-25 | 2015 | 5 | 2015-05 | 11
2015-02-10 | 2015-01-29 | 2015-02-08 | 2015 | 7 | 2015-07 | 2015-01-25 | 2015 | 5 | 2015-05 | 12
2015-02-11 | 2015-02-04 | 2015-02-08 | 2015 | 7 | 2015-07 | 2015-02-01 | 2015 | 6 | 2015-06 | 7
2015-02-11 | 2015-02-02 | 2015-02-08 | 2015 | 7 | 2015-07 | 2015-02-01 | 2015 | 6 | 2015-06 | 9
2015-02-12 | 2015-01-29 | 2015-02-08 | 2015 | 7 | 2015-07 | 2015-01-25 | 2015 | 5 | 2015-05 | 14
2015-02-16 | 2015-02-05 | 2015-02-15 | 2015 | 8 | 2015-08 | 2015-02-01 | 2015 | 6 | 2015-06 | 11
2015-02-17 | 2015-02-09 | 2015-02-15 | 2015 | 8 | 2015-08 | 2015-02-08 | 2015 | 7 | 2015-07 | 8
2015-02-17 | 2015-02-04 | 2015-02-15 | 2015 | 8 | 2015-08 | 2015-02-01 | 2015 | 6 | 2015-06 | 13
2015-02-17 | 2015-02-04 | 2015-02-15 | 2015 | 8 | 2015-08 | 2015-02-01 | 2015 | 6 | 2015-06 | 13
2015-02-17 | 2015-02-05 | 2015-02-15 | 2015 | 8 | 2015-08 | 2015-02-01 | 2015 | 6 | 2015-06 | 12
2015-02-17 | 2015-02-11 | 2015-02-15 | 2015 | 8 | 2015-08 | 2015-02-08 | 2015 | 7 | 2015-07 | 6
2015-02-18 | 2015-02-11 | 2015-02-15 | 2015 | 8 | 2015-08 | 2015-02-08 | 2015 | 7 | 2015-07 | 7
2015-02-23 | 2015-02-11 | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-08 | 2015 | 7 | 2015-07 | 12
2015-02-23 | 2015-02-12 | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-08 | 2015 | 7 | 2015-07 | 11
2015-02-23 | 2015-02-10 | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-08 | 2015 | 7 | 2015-07 | 13
2015-02-24 | 2015-02-11 | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-08 | 2015 | 7 | 2015-07 | 13
2015-02-24 | 2015-02-11 | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-08 | 2015 | 7 | 2015-07 | 13
2015-02-24 | 2015-02-10 | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-08 | 2015 | 7 | 2015-07 | 14
2015-02-25 | 2015-02-13 | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-08 | 2015 | 7 | 2015-07 | 12
2015-02-25 | 2015-02-10 | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-08 | 2015 | 7 | 2015-07 | 15
2015-02-25 | 2015-02-20 | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-15 | 2015 | 8 | 2015-08 | 5
2015-02-25 | 2015-02-20 | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-15 | 2015 | 8 | 2015-08 | 5
2015-02-26 | 2015-02-18 | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-15 | 2015 | 8 | 2015-08 | 8
2015-02-27 | 2015-02-23 | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-22 | 2015 | 9 | 2015-09 | 4
2015-02-27 | 2015-02-20 | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-15 | 2015 | 8 | 2015-08 | 7
2015-02-27 | 2015-02-20 | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-15 | 2015 | 8 | 2015-08 | 7
2015-02-27 | 2015-02-25 | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-22 | 2015 | 9 | 2015-09 | 2
2015-02-27 | 2015-02-20 | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-15 | 2015 | 8 | 2015-08 | 7
2015-03-02 | 2015-02-25 | 2015-03-01 | 2015 | 10 | 2015-10 | 2015-02-22 | 2015 | 9 | 2015-09 | 5
2015-03-03 | 2015-02-25 | 2015-03-01 | 2015 | 10 | 2015-10 | 2015-02-22 | 2015 | 9 | 2015-09 | 6
2015-03-04 | 2015-02-12 | 2015-03-01 | 2015 | 10 | 2015-10 | 2015-02-08 | 2015 | 7 | 2015-07 | 20
2015-03-04 | 2015-02-27 | 2015-03-01 | 2015 | 10 | 2015-10 | 2015-02-22 | 2015 | 9 | 2015-09 | 5
2015-03-05 | 2015-02-27 | 2015-03-01 | 2015 | 10 | 2015-10 | 2015-02-22 | 2015 | 9 | 2015-09 | 6
2015-03-05 | 2015-02-23 | 2015-03-01 | 2015 | 10 | 2015-10 | 2015-02-22 | 2015 | 9 | 2015-09 | 10
2015-03-05 | 2015-02-25 | 2015-03-01 | 2015 | 10 | 2015-10 | 2015-02-22 | 2015 | 9 | 2015-09 | 8
2015-03-06 | 2015-02-27 | 2015-03-01 | 2015 | 10 | 2015-10 | 2015-02-22 | 2015 | 9 | 2015-09 | 7
2015-03-06 | 2015-03-01 | 2015-03-01 | 2015 | 10 | 2015-10 | 2015-03-01 | 2015 | 10 | 2015-10 | 5
2015-03-09 | 2015-03-02 | 2015-03-08 | 2015 | 11 | 2015-11 | 2015-03-01 | 2015 | 10 | 2015-10 | 7
2015-03-10 | 2015-03-03 | 2015-03-08 | 2015 | 11 | 2015-11 | 2015-03-01 | 2015 | 10 | 2015-10 | 7
2015-03-10 | 2015-03-03 | 2015-03-08 | 2015 | 11 | 2015-11 | 2015-03-01 | 2015 | 10 | 2015-10 | 7
2015-03-10 | 2015-03-05 | 2015-03-08 | 2015 | 11 | 2015-11 | 2015-03-01 | 2015 | 10 | 2015-10 | 5
2015-03-10 | 2015-03-03 | 2015-03-08 | 2015 | 11 | 2015-11 | 2015-03-01 | 2015 | 10 | 2015-10 | 7
2015-03-10 | 2015-03-03 | 2015-03-08 | 2015 | 11 | 2015-11 | 2015-03-01 | 2015 | 10 | 2015-10 | 7
2015-03-10 | 2015-03-06 | 2015-03-08 | 2015 | 11 | 2015-11 | 2015-03-01 | 2015 | 10 | 2015-10 | 4
2015-03-10 | 2015-03-05 | 2015-03-08 | 2015 | 11 | 2015-11 | 2015-03-01 | 2015 | 10 | 2015-10 | 5
2015-03-11 | 2015-03-09 | 2015-03-08 | 2015 | 11 | 2015-11 | 2015-03-08 | 2015 | 11 | 2015-11 | 2
2015-03-12 | 2015-03-09 | 2015-03-08 | 2015 | 11 | 2015-11 | 2015-03-08 | 2015 | 11 | 2015-11 | 3
2015-03-12 | 2015-03-09 | 2015-03-08 | 2015 | 11 | 2015-11 | 2015-03-08 | 2015 | 11 | 2015-11 | 3
2015-03-17 | 2015-03-04 | 2015-03-15 | 2015 | 12 | 2015-12 | 2015-03-01 | 2015 | 10 | 2015-10 | 13
2015-03-17 | 2015-02-26 | 2015-03-15 | 2015 | 12 | 2015-12 | 2015-02-22 | 2015 | 9 | 2015-09 | 19
2015-03-17 | 2015-02-26 | 2015-03-15 | 2015 | 12 | 2015-12 | 2015-02-22 | 2015 | 9 | 2015-09 | 19
2015-03-17 | 2015-02-26 | 2015-03-15 | 2015 | 12 | 2015-12 | 2015-02-22 | 2015 | 9 | 2015-09 | 19
2015-03-19 | 2015-02-26 | 2015-03-15 | 2015 | 12 | 2015-12 | 2015-02-22 | 2015 | 9 | 2015-09 | 21
2015-03-19 | 2015-03-11 | 2015-03-15 | 2015 | 12 | 2015-12 | 2015-03-08 | 2015 | 11 | 2015-11 | 8
2015-03-20 | 2015-03-12 | 2015-03-15 | 2015 | 12 | 2015-12 | 2015-03-08 | 2015 | 11 | 2015-11 | 8
2015-03-20 | 2015-03-12 | 2015-03-15 | 2015 | 12 | 2015-12 | 2015-03-08 | 2015 | 11 | 2015-11 | 8
2015-03-20 | 2015-03-17 | 2015-03-15 | 2015 | 12 | 2015-12 | 2015-03-15 | 2015 | 12 | 2015-12 | 3
2015-03-20 | 2015-03-12 | 2015-03-15 | 2015 | 12 | 2015-12 | 2015-03-08 | 2015 | 11 | 2015-11 | 8
2015-03-23 | 2015-03-17 | 2015-03-22 | 2015 | 13 | 2015-13 | 2015-03-15 | 2015 | 12 | 2015-12 | 6
2015-03-24 | 2015-03-16 | 2015-03-22 | 2015 | 13 | 2015-13 | 2015-03-15 | 2015 | 12 | 2015-12 | 8
2015-03-24 | 2015-03-18 | 2015-03-22 | 2015 | 13 | 2015-13 | 2015-03-15 | 2015 | 12 | 2015-12 | 6
2015-03-26 | 2015-03-18 | 2015-03-22 | 2015 | 13 | 2015-13 | 2015-03-15 | 2015 | 12 | 2015-12 | 8
2015-03-26 | 2015-03-18 | 2015-03-22 | 2015 | 13 | 2015-13 | 2015-03-15 | 2015 | 12 | 2015-12 | 8
2015-03-26 | 2015-03-18 | 2015-03-22 | 2015 | 13 | 2015-13 | 2015-03-15 | 2015 | 12 | 2015-12 | 8
2015-03-31 | 2015-03-18 | 2015-03-29 | 2015 | 14 | 2015-14 | 2015-03-15 | 2015 | 12 | 2015-12 | 13
2015-04-02 | 2015-03-19 | 2015-03-29 | 2015 | 14 | 2015-14 | 2015-03-15 | 2015 | 12 | 2015-12 | 14
2015-04-02 | 2015-03-23 | 2015-03-29 | 2015 | 14 | 2015-14 | 2015-03-22 | 2015 | 13 | 2015-13 | 10
2015-04-02 | 2015-03-24 | 2015-03-29 | 2015 | 14 | 2015-14 | 2015-03-22 | 2015 | 13 | 2015-13 | 9
2015-04-02 | 2015-03-24 | 2015-03-29 | 2015 | 14 | 2015-14 | 2015-03-22 | 2015 | 13 | 2015-13 | 9
2015-04-02 | 2015-03-25 | 2015-03-29 | 2015 | 14 | 2015-14 | 2015-03-22 | 2015 | 13 | 2015-13 | 8
2015-04-03 | 2015-03-19 | 2015-03-29 | 2015 | 14 | 2015-14 | 2015-03-15 | 2015 | 12 | 2015-12 | 15
2015-04-06 | 2015-03-19 | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-03-15 | 2015 | 12 | 2015-12 | 18
2015-04-06 | 2015-03-30 | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-03-29 | 2015 | 14 | 2015-14 | 7
2015-04-07 | 2015-03-31 | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-03-29 | 2015 | 14 | 2015-14 | 7
2015-04-08 | 2015-04-01 | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-03-29 | 2015 | 14 | 2015-14 | 7
2015-04-08 | 2015-03-20 | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-03-15 | 2015 | 12 | 2015-12 | 19
2015-04-08 | 2015-03-25 | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-03-22 | 2015 | 13 | 2015-13 | 14
2015-04-09 | 2015-03-31 | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-03-29 | 2015 | 14 | 2015-14 | 9
2015-04-09 | 2015-04-02 | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-03-29 | 2015 | 14 | 2015-14 | 7
2015-04-09 | 2015-04-03 | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-03-29 | 2015 | 14 | 2015-14 | 6
2015-04-10 | 2015-04-02 | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-03-29 | 2015 | 14 | 2015-14 | 8
2015-04-10 | 2015-03-26 | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-03-22 | 2015 | 13 | 2015-13 | 15
2015-04-10 | 2015-04-07 | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-04-05 | 2015 | 15 | 2015-15 | 3
2015-04-14 | 2015-04-08 | 2015-04-12 | 2015 | 16 | 2015-16 | 2015-04-05 | 2015 | 15 | 2015-15 | 6
2015-04-14 | 2015-04-08 | 2015-04-12 | 2015 | 16 | 2015-16 | 2015-04-05 | 2015 | 15 | 2015-15 | 6
2015-04-16 | 2015-04-06 | 2015-04-12 | 2015 | 16 | 2015-16 | 2015-04-05 | 2015 | 15 | 2015-15 | 10
2015-04-16 | 2015-04-08 | 2015-04-12 | 2015 | 16 | 2015-16 | 2015-04-05 | 2015 | 15 | 2015-15 | 8
2015-04-16 | 2015-04-08 | 2015-04-12 | 2015 | 16 | 2015-16 | 2015-04-05 | 2015 | 15 | 2015-15 | 8
2015-04-17 | 2015-04-02 | 2015-04-12 | 2015 | 16 | 2015-16 | 2015-03-29 | 2015 | 14 | 2015-14 | 15
2015-04-20 | 2015-04-08 | 2015-04-19 | 2015 | 17 | 2015-17 | 2015-04-05 | 2015 | 15 | 2015-15 | 12
2015-04-22 | 2015-04-08 | 2015-04-19 | 2015 | 17 | 2015-17 | 2015-04-05 | 2015 | 15 | 2015-15 | 14
2015-04-22 | 2015-04-14 | 2015-04-19 | 2015 | 17 | 2015-17 | 2015-04-12 | 2015 | 16 | 2015-16 | 8
2015-04-23 | 2015-04-10 | 2015-04-19 | 2015 | 17 | 2015-17 | 2015-04-05 | 2015 | 15 | 2015-15 | 13
2015-04-23 | 2015-04-09 | 2015-04-19 | 2015 | 17 | 2015-17 | 2015-04-05 | 2015 | 15 | 2015-15 | 14
2015-04-23 | 2015-04-13 | 2015-04-19 | 2015 | 17 | 2015-17 | 2015-04-12 | 2015 | 16 | 2015-16 | 10
2015-04-23 | 2015-04-16 | 2015-04-19 | 2015 | 17 | 2015-17 | 2015-04-12 | 2015 | 16 | 2015-16 | 7
2015-04-24 | 2015-04-14 | 2015-04-19 | 2015 | 17 | 2015-17 | 2015-04-12 | 2015 | 16 | 2015-16 | 10
2015-04-27 | 2015-04-16 | 2015-04-26 | 2015 | 18 | 2015-18 | 2015-04-12 | 2015 | 16 | 2015-16 | 11
2015-04-27 | 2015-04-20 | 2015-04-26 | 2015 | 18 | 2015-18 | 2015-04-19 | 2015 | 17 | 2015-17 | 7
2015-04-27 | 2015-04-17 | 2015-04-26 | 2015 | 18 | 2015-18 | 2015-04-12 | 2015 | 16 | 2015-16 | 10
2015-04-27 | 2015-04-22 | 2015-04-26 | 2015 | 18 | 2015-18 | 2015-04-19 | 2015 | 17 | 2015-17 | 5
2015-04-28 | 2015-04-20 | 2015-04-26 | 2015 | 18 | 2015-18 | 2015-04-19 | 2015 | 17 | 2015-17 | 8
2015-04-28 | 2015-04-20 | 2015-04-26 | 2015 | 18 | 2015-18 | 2015-04-19 | 2015 | 17 | 2015-17 | 8
2015-04-30 | 2015-04-20 | 2015-04-26 | 2015 | 18 | 2015-18 | 2015-04-19 | 2015 | 17 | 2015-17 | 10
2015-05-01 | 2015-04-23 | 2015-04-26 | 2015 | 18 | 2015-18 | 2015-04-19 | 2015 | 17 | 2015-17 | 8
2015-05-04 | 2015-04-27 | 2015-05-03 | 2015 | 19 | 2015-19 | 2015-04-26 | 2015 | 18 | 2015-18 | 7
2015-05-04 | 2015-04-28 | 2015-05-03 | 2015 | 19 | 2015-19 | 2015-04-26 | 2015 | 18 | 2015-18 | 6
2015-05-05 | 2015-04-23 | 2015-05-03 | 2015 | 19 | 2015-19 | 2015-04-19 | 2015 | 17 | 2015-17 | 12
2015-05-06 | 2015-04-28 | 2015-05-03 | 2015 | 19 | 2015-19 | 2015-04-26 | 2015 | 18 | 2015-18 | 8
2015-05-06 | 2015-04-27 | 2015-05-03 | 2015 | 19 | 2015-19 | 2015-04-26 | 2015 | 18 | 2015-18 | 9
2015-05-06 | 2015-04-28 | 2015-05-03 | 2015 | 19 | 2015-19 | 2015-04-26 | 2015 | 18 | 2015-18 | 8
2015-05-08 | 2015-04-30 | 2015-05-03 | 2015 | 19 | 2015-19 | 2015-04-26 | 2015 | 18 | 2015-18 | 8
2015-05-08 | 2015-04-29 | 2015-05-03 | 2015 | 19 | 2015-19 | 2015-04-26 | 2015 | 18 | 2015-18 | 9
2015-05-11 | 2015-05-04 | 2015-05-10 | 2015 | 20 | 2015-20 | 2015-05-03 | 2015 | 19 | 2015-19 | 7
2015-05-11 | 2015-04-27 | 2015-05-10 | 2015 | 20 | 2015-20 | 2015-04-26 | 2015 | 18 | 2015-18 | 14
2015-05-11 | 2015-04-29 | 2015-05-10 | 2015 | 20 | 2015-20 | 2015-04-26 | 2015 | 18 | 2015-18 | 12
2015-05-12 | 2015-05-01 | 2015-05-10 | 2015 | 20 | 2015-20 | 2015-04-26 | 2015 | 18 | 2015-18 | 11
2015-05-12 | 2015-05-06 | 2015-05-10 | 2015 | 20 | 2015-20 | 2015-05-03 | 2015 | 19 | 2015-19 | 6
2015-05-12 | 2015-05-04 | 2015-05-10 | 2015 | 20 | 2015-20 | 2015-05-03 | 2015 | 19 | 2015-19 | 8
2015-05-13 | 2015-05-04 | 2015-05-10 | 2015 | 20 | 2015-20 | 2015-05-03 | 2015 | 19 | 2015-19 | 9
2015-05-13 | 2015-05-04 | 2015-05-10 | 2015 | 20 | 2015-20 | 2015-05-03 | 2015 | 19 | 2015-19 | 9
2015-05-13 | 2015-05-06 | 2015-05-10 | 2015 | 20 | 2015-20 | 2015-05-03 | 2015 | 19 | 2015-19 | 7
| 2015-05-06 |  |  |  |  | 2015-05-03 | 2015 | 19 | 2015-19 | #N/A
| 2015-05-08 |  |  |  |  | 2015-05-03 | 2015 | 19 | 2015-19 | #N/A
| 2015-05-12 |  |  |  |  | 2015-05-10 | 2015 | 20 | 2015-20 | #N/A
| 2015-05-11 |  |  |  |  | 2015-05-10 | 2015 | 20 | 2015-20 | #N/A
| 2015-05-12 |  |  |  |  | 2015-05-10 | 2015 | 20 | 2015-20 | #N/A
| 2015-05-12 |  |  |  |  | 2015-05-10 | 2015 | 20 | 2015-20 | #N/A
| 2015-05-06 |  |  |  |  | 2015-05-03 | 2015 | 19 | 2015-19 | #N/A
| 2015-05-07 |  |  |  |  | 2015-05-03 | 2015 | 19 | 2015-19 | #N/A
| 2015-05-12 |  |  |  |  | 2015-05-10 | 2015 | 20 | 2015-20 | #N/A
| 2015-05-13 |  |  |  |  | 2015-05-10 | 2015 | 20 | 2015-20 | #N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
Formulas:
Indirect Completed Dates = IF(AND(TRIM(INDEX(CompletedDateValues,ROW([Indirect Completed Dates])))<>"",INDEX(CompletedDateValues,ROW([Indirect Completed Dates]))>0),INT(INDEX(CompletedDateValues,ROW([Indirect Completed Dates]))),"")
Indirect Start Dates = IF(AND(TRIM(INDEX(StartDateValues,ROW([Indirect Completed Dates])))<>"",INDEX(StartDateValues,ROW([Indirect Completed Dates]))>0),INT(INDEX(StartDateValues,ROW([Indirect Completed Dates]))),"")
Prior Complete Sunday = IF([Indirect Completed Dates]="","",[Indirect Completed Dates] - (WEEKDAY([Indirect Completed Dates])-1))
WeekNumber Complete = IF([Prior Complete Sunday]="","",WEEKNUM([Prior Complete Sunday]))
Prior Start Sunday = IF([Indirect Start Dates]="","",[Indirect Start Dates] - (WEEKDAY([Indirect Start Dates])-1))
WeekNumber Start = IF([Prior Start Sunday]="","",WEEKNUM([Prior Start Sunday]))
Column A and B grab data from the "Your Data" sheet by indirect reference. This allows you to cut and copy and move rows in your data without corrupting the formula cell references.
This is the prior sunday for the completed date. This date is used as the start of week.
This is a neatly formatted week group name. It makes the week number two digits so that groupds sort chronologically.
This is the number of days between start and end. If the dates are flipped, it returns 0 days. If work finishes on the same day, it uses the value on the Settings tab. Typically this is 0.5 or 1 day.