## Instructions
Throughput and Cycle Time Calculator
Version
| 1 | Initial Version
| 1.1 | Removed the IFNA and replaced with ISERROR to be compativle with ExCel 2010
| 1.2 | Added Work in Progress tab
| 1.3 | Added new charts, survey and sharing data tab.
| 1.31 | Fixed WIP calculation to include started work without a completion date (yet)
| 1.32 | Added a note after KLR15 feedback
| 1.4 | Added new cycle time chart. Thanks to twitter feedback: @joshuajames @kjscotland @smok77 @cyetain @jchyip @yuvalyeret
| 1.5 | Fixed defect in Started vs Completed Items per week chart range (was hardcoded)
| 1.6 | Fixed time issue of data inputs failing equal tests for any day based chart or measure
What is this: This spreadsheet helps to probabilistically forecast how long it will take to complete features and stories based on range estimates.
How does it work? Given your estimates, this spreadsheet hypothetically completes all work 500 times. It calculates likelihood result as the number of simulated trials that finished on or before a given date.
Why is this better than burndowns and traditional Agile forecasting? Most forecasting techniques give a single date result and hide the likelihood of that date. Most often the date given as the result is 50% because work is divided by an average (or median). Thats the odds of a toin-coss. This method allows the reader to choose the amount of schedule risk they wish to sign-up for. 85% is a common middle ground used in the industry.
Is it reliable? It has no mathematical errors (that we know of!), and all we guarentee is its better than intuition alone and better than simple regression models. But, help us improve it by letting us know when it misses the actual results you are seeing.
How to: Fill in the orange boxes in the Forecast worksheet and read off the dates in the results table adjacent to the likelihood/certainty you think is appropriate. 85% is a common industry level of certainty used.
What is throughput? Where do I get that data? Throughput is the number of DONE stories completed by a team per week or per sprint (you choose in this spreadsheet, default is per week). We will be providing a viz that gathers this data for your team. Stay tuned.
What is this: This spreadsheet takes work item/story/defect data and creates throughput and cycle time data and charts.
How does it work? Throughput is calculated by counting the number of items that complete in the same calendar week (sunday to saturday). This data is reported on the Throughput worksheet. Cycle time is calculated by subtracting the completed date and the start date. This is the number of days between these dates. For items completing on the same day as they are started, you can override the default value to be used (rather than get zero).
How to: Get a list of completed dates (ata minimum) for each item in your electronic tracking tool. Enter this data in Column A in the "Your Data" worksheet. ptionally add the start date, and any other field values that help you manage this data.
Ideas, errors, requests? Email: troy.magennis@focusedobjective.com
Work licensed under a Creative Commons Attribution-NonCommercial-ShareAlike 4.0 International License.
Details here: http://creativecommons.org/licenses/by-nc-sa/4.0/ and
http://creativecommons.org/licenses/by-nc-sa/4.0/legalcode
Get more tools like this from: http://bit.ly/SimResources
About us: Focused Objective LLC offers tools, training and expert advice on metrics, risk and forecasting. We have more advanced tools to model Agile teams and projects that help analyze staffing options and risk, and a proven track record of positive results. We are always happy to discuss next steps and training opportunities should this tool prove useful. See our website: http://www.focusedobjective.com or email me at troy.magennis@focusedobjective.com.
Please don't by this book on Amazon; its out of date (we leave it there for people who insist on a hard-copy). Go to Bit.ly/agilesim as it says on the card and download for free.
Also - please hire us! we can help with metrics, forecasting and risk management of Agile projects. We are able to make these tools free because we are called upon for our expertise often. Either way, talk to us first before looking elsewhere!

## Your Data
Completed Date | Start Date (optional) | Type (optional) | Id (optional) | Description (optional)
2015-01-21 | 2015-01-14 | Story
2015-01-26 | 2015-01-14 | Story
2015-01-26 | 2015-01-14 | Defect
2015-01-26 | 2015-01-21
2015-01-26 | 2015-01-22
2015-01-29 | 2015-01-23
2015-02-02 | 2015-01-23
2015-02-02 | 2015-01-20
2015-02-02 | 2015-01-20
2015-02-04 | 2015-01-20
2015-02-04 | 2015-01-26
2015-02-04 | 2015-01-23
2015-02-04 | 2015-01-22
2015-02-04 | 2015-01-28
2015-02-05 | 2015-01-29
2015-02-05 | 2015-01-22
2015-02-06 | 2015-01-28
2015-02-09 | 2015-01-28
2015-02-09 | 2015-02-02
2015-02-09 | 2015-01-29
2015-02-10 | 2015-01-29
2015-02-11 | 2015-02-04
2015-02-11 | 2015-02-02
2015-02-12 | 2015-01-29
2015-02-16 | 2015-02-05
2015-02-17 | 2015-02-09
2015-02-17 | 2015-02-04
2015-02-17 | 2015-02-04
2015-02-17 | 2015-02-05
2015-02-17 | 2015-02-11
2015-02-18 | 2015-02-11
2015-02-23 | 2015-02-11
2015-02-23 | 2015-02-12
2015-02-23 | 2015-02-10
2015-02-24 | 2015-02-11
2015-02-24 | 2015-02-11
2015-02-24 | 2015-02-10
2015-02-25 | 2015-02-13
2015-02-25 | 2015-02-10
2015-02-25 | 2015-02-20
2015-02-25 | 2015-02-20
2015-02-26 | 2015-02-18
2015-02-27 | 2015-02-23
2015-02-27 | 2015-02-20
2015-02-27 | 2015-02-20
2015-02-27 | 2015-02-25
2015-02-27 | 2015-02-20
2015-03-02 | 2015-02-25
2015-03-03 | 2015-02-25
2015-03-04 | 2015-02-12
2015-03-04 | 2015-02-27
2015-03-05 | 2015-02-27
2015-03-05 | 2015-02-23
2015-03-05 | 2015-02-25
2015-03-06 | 2015-02-27
2015-03-06 | 2015-03-01
2015-03-09 | 2015-03-02
2015-03-10 | 2015-03-03
2015-03-10 | 2015-03-03
2015-03-10 | 2015-03-05
2015-03-10 | 2015-03-03
2015-03-10 | 2015-03-03
2015-03-10 | 2015-03-06
2015-03-10 | 2015-03-05
2015-03-11 | 2015-03-09
2015-03-12 | 2015-03-09
2015-03-12 | 2015-03-09
2015-03-17 | 2015-03-04
2015-03-17 | 2015-02-26
2015-03-17 | 2015-02-26
2015-03-17 | 2015-02-26
2015-03-19 | 2015-02-26
2015-03-19 | 2015-03-11
2015-03-20 | 2015-03-12
2015-03-20 | 2015-03-12
2015-03-20 | 2015-03-17
2015-03-20 | 2015-03-12
2015-03-23 | 2015-03-17
2015-03-24 | 2015-03-16
2015-03-24 | 2015-03-18
2015-03-26 | 2015-03-18
2015-03-26 | 2015-03-18
2015-03-26 | 2015-03-18
2015-03-31 | 2015-03-18
2015-04-02 | 2015-03-19
2015-04-02 | 2015-03-23
2015-04-02 | 2015-03-24
2015-04-02 | 2015-03-24
2015-04-02 | 2015-03-25
2015-04-03 | 2015-03-19
2015-04-06 | 2015-03-19
2015-04-06 | 2015-03-30
2015-04-07 | 2015-03-31
2015-04-08 | 2015-04-01
2015-04-08 | 2015-03-20
2015-04-08 | 2015-03-25
2015-04-09 | 2015-03-31
2015-04-09 | 2015-04-02
2015-04-09 | 2015-04-03
2015-04-10 | 2015-04-02
2015-04-10 | 2015-03-26
2015-04-10 | 2015-04-07
2015-04-14 | 2015-04-08
2015-04-14 | 2015-04-08
2015-04-16 | 2015-04-06
2015-04-16 | 2015-04-08
2015-04-16 | 2015-04-08
2015-04-17 | 2015-04-02
2015-04-20 | 2015-04-08
2015-04-22 | 2015-04-08
2015-04-22 | 2015-04-14
2015-04-23 | 2015-04-10
2015-04-23 | 2015-04-09
2015-04-23 | 2015-04-13
2015-04-23 | 2015-04-16
2015-04-24 | 2015-04-14
2015-04-27 | 2015-04-16
2015-04-27 | 2015-04-20
2015-04-27 | 2015-04-17
2015-04-27 | 2015-04-22
2015-04-28 | 2015-04-20
2015-04-28 | 2015-04-20
2015-04-30 | 2015-04-20
2015-05-01 | 2015-04-23
2015-05-04 | 2015-04-27
2015-05-04 | 2015-04-28
2015-05-05 | 2015-04-23
2015-05-06 | 2015-04-28
2015-05-06 | 2015-04-27
2015-05-06 | 2015-04-28
2015-05-08 | 2015-04-30
2015-05-08 | 2015-04-29
2015-05-11 | 2015-05-04
2015-05-11 | 2015-04-27
2015-05-11 | 2015-04-29
2015-05-12 | 2015-05-01
2015-05-12 | 2015-05-06
2015-05-12 | 2015-05-04
2015-05-13 | 2015-05-04
2015-05-13 | 2015-05-04
2015-05-13 | 2015-05-06
2015-05-06
2015-05-08
2015-05-12
2015-05-11
2015-05-12
2015-05-12
2015-05-06
2015-05-07
2015-05-12
2015-05-13
Put your data on this sheet.
For throughput: Only the completed date is needed.
For cycle-time and WIP, the completed date and start date is needed.
The Id and Description fields are just for your convenience.

## Settings
Cycle time value to use when items are completed on the same day as being started.
0.5

## Charts
This chart has "issues" but i want ideas -
1. the series are all different units
2. the date is wrong for the WIP series (off by 1 week)
3. its meant to infer trend and correlation, but because of the values in each unit, it looks like magnitude is important.
4. it doesnt resize to the amount of data.
Thinking: Normalizing each measure 0 (lowest) and 1 (highest) so we are comparing the same ranges as a proportion. And fixing the dates.
The word Cycle Time means different things to different people. For this spreadsheet, it is the calendar days between two dates. YOU have to define what those dates mean. Does Completed mean delivered to a customer? Does it mean handed off for deployment? The same issue with the start date.Is start when an item is comitted? or when i is created? Please be sure to document what this cycle time means and is captured consistently.
More discussion on the glossary of definitions for cycle time can be found here in a post by Andy Carmichael: http://xprocess.blogspot.co.uk/2015/05/glossary-proposal.html
if you feel strongly this should be renamed TiP (Time in process) then please email me: troy.magennis@focusedobjective.com

## Research Survey
What process does the team identify they are doing? |  |  | Not Answered | Other:
Does the team use sprints? If yes, How long are they? |  |  | Not Answered | Other:
What percentage of work is planned versus un-planned as a percentage?
Planned % | 80%
Un-planned % | 20%
Does your team have significant external team dependencies? For example, do you often get blocked waiting for another team to deliver a component or library?
Not Answered
How many people are on the team?
Predom Skillset | Count | Co-located?
Developers | 0 | Not Answered
Testers | 0 | Not Answered
Designers | 0 | Not Answered
Product Owners | 0 | Not Answered
Other:
| 0 | Not Answered
| 0 | Not Answered
| 0 | Not Answered
Please only use my email address |  |  | For questions only
Email address
Contact name
Please consider sharing this data for research. We are primarily interested in the start and stop dates, and this survey data. Industry cycle-time and throughput data will help improve the science of software development. If you do share, please enter as much information below as you care to share, remove any data you aren't willing to share from the "Your Data" worksheet, and then email us this spreadsheet: troy.magennis@focusedobjective.com
Privacy policy -
1. We will NEVER share you name or contact information with third parties
2. We request you opt-in to giving us your email address for clarifying questions or to send you regular updates on analysis depending on what you request when submitting to us
3. We will NEVER share the organization name or contact name when sharing this data with other researchers
We WILL publish this data (without identifying information) using the Attribution-ShareAlike 4.0 International: http://creativecommons.org/licenses/by-sa/4.0/ for research purposes.
Checklist:
1. Remove any data you aren't willing to share from the "Your Data" worksheet
2. Fill in as much of this survey as you are willing to share
3. Email us this spreadsheet: troy.magennis@focusedobjective.com
Thank you.

## Share Data
Throughput
CSV | 1,5,11,7,7,16,9,11,10,6,7,12,6,8,8,8,9
SIP 2.0 | <sip name="dist" type="CSV" ver="1.0">1,5,11,7,7,16,9,11,10,6,7,12,6,8,8,8,9</sip>
Kanban/Scrum Sim Distribution | <distribution name="dist" shape="fromSamples">1,5,11,7,7,16,9,11,10,6,7,12,6,8,8,8,9</distribution>
Cycle Time
CSV | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9,7,14,12,11,6,8,9,9,7
SIP 2.0 | <sip name="dist" type="CSV" ver="1.0">7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9,7,14,12,11,6,8,9,9,7</sip>
Kanban/Scrum Sim Distribution | <distribution name="dist" shape="fromSamples">7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9,7,14,12,11,6,8,9,9,7</distribution>
These are industry standard formats for sharing data with other people and applications.

## Throughput
Week Starting | Week Ending | week groups | Throughput | Normalized | CSV | Percentiles
2015-01-18 | 2015-01-24 | 2015-04 | 1 | 0 | 1 | min | 5% | 25% | 50% | 75% | 95% | max
2015-01-25 | 2015-01-31 | 2015-05 | 5 | 0.26667 | 1,5 | 1 | 4.2 | 7 | 8 | 10 | 12.8 | 16
2015-02-01 | 2015-02-07 | 2015-06 | 11 | 0.66667 | 1,5,11
2015-02-08 | 2015-02-14 | 2015-07 | 7 | 0.4 | 1,5,11,7 | Bin | Frequency
2015-02-15 | 2015-02-21 | 2015-08 | 7 | 0.4 | 1,5,11,7,7 | 1 | 1
2015-02-22 | 2015-02-28 | 2015-09 | 16 | 1 | 1,5,11,7,7,16 | 2 | 0
2015-03-01 | 2015-03-07 | 2015-10 | 9 | 0.53333 | 1,5,11,7,7,16,9 | 3 | 0
2015-03-08 | 2015-03-14 | 2015-11 | 11 | 0.66667 | 1,5,11,7,7,16,9,11 | 4 | 0
2015-03-15 | 2015-03-21 | 2015-12 | 10 | 0.6 | 1,5,11,7,7,16,9,11,10 | 5 | 1
2015-03-22 | 2015-03-28 | 2015-13 | 6 | 0.33333 | 1,5,11,7,7,16,9,11,10,6 | 6 | 2
2015-03-29 | 2015-04-04 | 2015-14 | 7 | 0.4 | 1,5,11,7,7,16,9,11,10,6,7 | 7 | 3
2015-04-05 | 2015-04-11 | 2015-15 | 12 | 0.73333 | 1,5,11,7,7,16,9,11,10,6,7,12 | 8 | 3
2015-04-12 | 2015-04-18 | 2015-16 | 6 | 0.33333 | 1,5,11,7,7,16,9,11,10,6,7,12,6 | 9 | 2
2015-04-19 | 2015-04-25 | 2015-17 | 8 | 0.46667 | 1,5,11,7,7,16,9,11,10,6,7,12,6,8 | 10 | 1
2015-04-26 | 2015-05-02 | 2015-18 | 8 | 0.46667 | 1,5,11,7,7,16,9,11,10,6,7,12,6,8,8 | 11 | 2
2015-05-03 | 2015-05-09 | 2015-19 | 8 | 0.46667 | 1,5,11,7,7,16,9,11,10,6,7,12,6,8,8,8 | 12 | 1
2015-05-10 | 2015-05-16 | 2015-20 | 9 | 0.53333 | 1,5,11,7,7,16,9,11,10,6,7,12,6,8,8,8,9 | 13 | 0
[6 empty] | 14 | 0
[6 empty] | 15 | 0
[6 empty] | 16 | 1
[6 empty] | 17 | 0
[6 empty] | 18 | 0
[6 empty] | 19 | 0
[6 empty] | 20 | 0
[6 empty] | 21 | 0
Formulas:
Week Starting = IF(ISNUMBER([Week Starting, row above]),IF([Week Starting, row above]+7<=MAX(PriorSundays),[Week Starting, row above]+7,""),"")
Week Ending = IF(ISNUMBER([Week Starting]),[Week Starting]+6,"")
week groups = IF(ISNUMBER([Week Starting]),YEAR([Week Starting])&"-"&TEXT(WEEKNUM([Week Starting]),"00"),"")

## Cycle Time
Completed Date | Week Group | Cycle Time (days) | CSV | 50% | 75% | 95% | Week Starting | Week Ending | week groups | Min Cycle Time | Avg Cycle Time | Max Cycle Time | 25th Percentile | 30th | Median | 70th | 75th Percentile | 85th | Percentiles
2015-01-21 | 2015-04 | 7 | 7 | 8 | 12 | 15 | 2015-01-18 | 2015-01-24 | 2015-04 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Min | 0.05 | 0.25 | 0.5 | 0.75 | 0.95 | Max
2015-01-26 | 2015-05 | 12 | 7,12 | 8 | 12 | 15 | 2015-01-25 | 2015-01-31 | 2015-05 | 4 | 7.8 | 12 | 5 | 5.2 | 6 | 10.8 | 12 | 12 | 2 | 4 | 7 | 8 | 12 | 15 | 21
2015-01-26 | 2015-05 | 12 | 7,12,12 | 8 | 12 | 15 | 2015-02-01 | 2015-02-07 | 2015-06 | 7 | 11.0909 | 15 | 9 | 9 | 12 | 13 | 13 | 13.5
2015-01-26 | 2015-05 | 5 | 7,12,12,5 | 8 | 12 | 15 | 2015-02-08 | 2015-02-14 | 2015-07 | 7 | 10.2857 | 14 | 8 | 8.6 | 11 | 12 | 12 | 12.2 | Bin | Frequency
2015-01-26 | 2015-05 | 4 | 7,12,12,5,4 | 8 | 12 | 15 | 2015-02-15 | 2015-02-21 | 2015-08 | 6 | 10 | 13 | 7.5 | 7.8 | 11 | 12.2 | 12.5 | 13 | 2 | 2
2015-01-29 | 2015-05 | 6 | 7,12,12,5,4,6 | 8 | 12 | 15 | 2015-02-22 | 2015-02-28 | 2015-09 | 2 | 9.25 | 15 | 6.5 | 7 | 9.5 | 12.5 | 13 | 13 | 3 | 4
2015-02-02 | 2015-06 | 10 | 7,12,12,5,4,6,10 | 8 | 12 | 15 | 2015-03-01 | 2015-03-07 | 2015-10 | 5 | 8 | 20 | 5 | 5.4 | 6 | 7.6 | 8 | 9.6 | 4 | 3
2015-02-02 | 2015-06 | 13 | 7,12,12,5,4,6,10,13 | 8 | 12 | 15 | 2015-03-08 | 2015-03-14 | 2015-11 | 2 | 5.1818 | 7 | 3.5 | 4 | 5 | 7 | 7 | 7 | 5 | 9
2015-02-02 | 2015-06 | 13 | 7,12,12,5,4,6,10,13,13 | 8 | 12 | 15 | 2015-03-15 | 2015-03-21 | 2015-12 | 3 | 12.6 | 21 | 8 | 8 | 10.5 | 19 | 19 | 19 | 6 | 11
2015-02-04 | 2015-06 | 15 | 7,12,12,5,4,6,10,13,13,15 | 8 | 12 | 15 | 2015-03-22 | 2015-03-28 | 2015-13 | 6 | 7.3333 | 8 | 6.5 | 7 | 8 | 8 | 8 | 8 | 7 | 24
2015-02-04 | 2015-06 | 9 | 7,12,12,5,4,6,10,13,13,15,9 | 8 | 12 | 15 | 2015-03-29 | 2015-04-04 | 2015-14 | 8 | 11.1429 | 15 | 9 | 9 | 10 | 13.2 | 13.5 | 14.1 | 8 | 23
2015-02-04 | 2015-06 | 12 | 7,12,12,5,4,6,10,13,13,15,9,12 | 8 | 12 | 15 | 2015-04-05 | 2015-04-11 | 2015-15 | 3 | 10 | 19 | 7 | 7 | 7.5 | 12.5 | 14.25 | 16.05 | 9 | 10
2015-02-04 | 2015-06 | 13 | 7,12,12,5,4,6,10,13,13,15,9,12,13 | 8 | 12 | 15 | 2015-04-12 | 2015-04-18 | 2015-16 | 6 | 8.8333 | 15 | 6.5 | 7 | 8 | 9 | 9.5 | 11.25 | 10 | 8
2015-02-04 | 2015-06 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7 | 8 | 12 | 15 | 2015-04-19 | 2015-04-25 | 2015-17 | 7 | 11 | 14 | 9.5 | 10 | 11 | 12.9 | 13.25 | 13.95 | 11 | 5
2015-02-05 | 2015-06 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7 | 8 | 12 | 15 | 2015-04-26 | 2015-05-02 | 2015-18 | 5 | 8.375 | 11 | 7.75 | 8 | 8 | 9.8 | 10 | 10 | 12 | 11
2015-02-05 | 2015-06 | 14 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14 | 8 | 12 | 15 | 2015-05-03 | 2015-05-09 | 2015-19 | 6 | 8.375 | 12 | 7.75 | 8 | 8 | 8.9 | 9 | 9 | 13 | 11
2015-02-06 | 2015-06 | 9 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9 | 8 | 12 | 15 | 2015-05-10 | 2015-05-16 | 2015-20 | 6 | 9.2222 | 14 | 7 | 7.4 | 9 | 10.2 | 11 | 11.8 | 14 | 8
2015-02-09 | 2015-07 | 12 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12 | 8 | 12 | 15 | [12 empty] | 15 | 5
2015-02-09 | 2015-07 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7 | 8 | 12 | 15 | [12 empty] | 16 | 0
2015-02-09 | 2015-07 | 11 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11 | 8 | 12 | 15 | [12 empty] | 17 | 0
2015-02-10 | 2015-07 | 12 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12 | 8 | 12 | 15 | [12 empty] | 18 | 1
2015-02-11 | 2015-07 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7 | 8 | 12 | 15 | [12 empty] | 19 | 4
2015-02-11 | 2015-07 | 9 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9 | 8 | 12 | 15 | [12 empty] | 20 | 1
2015-02-12 | 2015-07 | 14 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14 | 8 | 12 | 15 | [12 empty] | 21 | 1
2015-02-16 | 2015-08 | 11 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11 | 8 | 12 | 15
2015-02-17 | 2015-08 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8 | 8 | 12 | 15
2015-02-17 | 2015-08 | 13 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13 | 8 | 12 | 15
2015-02-17 | 2015-08 | 13 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13 | 8 | 12 | 15
2015-02-17 | 2015-08 | 12 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12 | 8 | 12 | 15
2015-02-17 | 2015-08 | 6 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6 | 8 | 12 | 15
2015-02-18 | 2015-08 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7 | 8 | 12 | 15
2015-02-23 | 2015-09 | 12 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12 | 8 | 12 | 15
2015-02-23 | 2015-09 | 11 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11 | 8 | 12 | 15
2015-02-23 | 2015-09 | 13 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13 | 8 | 12 | 15
2015-02-24 | 2015-09 | 13 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13 | 8 | 12 | 15
2015-02-24 | 2015-09 | 13 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13 | 8 | 12 | 15
2015-02-24 | 2015-09 | 14 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14 | 8 | 12 | 15
2015-02-25 | 2015-09 | 12 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12 | 8 | 12 | 15
2015-02-25 | 2015-09 | 15 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15 | 8 | 12 | 15
2015-02-25 | 2015-09 | 5 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5 | 8 | 12 | 15
2015-02-25 | 2015-09 | 5 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5 | 8 | 12 | 15
2015-02-26 | 2015-09 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8 | 8 | 12 | 15
2015-02-27 | 2015-09 | 4 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4 | 8 | 12 | 15
2015-02-27 | 2015-09 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7 | 8 | 12 | 15
2015-02-27 | 2015-09 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7 | 8 | 12 | 15
2015-02-27 | 2015-09 | 2 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2 | 8 | 12 | 15
2015-02-27 | 2015-09 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7 | 8 | 12 | 15
2015-03-02 | 2015-10 | 5 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5 | 8 | 12 | 15
2015-03-03 | 2015-10 | 6 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6 | 8 | 12 | 15
2015-03-04 | 2015-10 | 20 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20 | 8 | 12 | 15
2015-03-04 | 2015-10 | 5 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5 | 8 | 12 | 15
2015-03-05 | 2015-10 | 6 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6 | 8 | 12 | 15
2015-03-05 | 2015-10 | 10 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10 | 8 | 12 | 15
2015-03-05 | 2015-10 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8 | 8 | 12 | 15
2015-03-06 | 2015-10 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7 | 8 | 12 | 15
2015-03-06 | 2015-10 | 5 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5 | 8 | 12 | 15
2015-03-09 | 2015-11 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7 | 8 | 12 | 15
2015-03-10 | 2015-11 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7 | 8 | 12 | 15
2015-03-10 | 2015-11 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7 | 8 | 12 | 15
2015-03-10 | 2015-11 | 5 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5 | 8 | 12 | 15
2015-03-10 | 2015-11 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7 | 8 | 12 | 15
2015-03-10 | 2015-11 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7 | 8 | 12 | 15
2015-03-10 | 2015-11 | 4 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4 | 8 | 12 | 15
2015-03-10 | 2015-11 | 5 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5 | 8 | 12 | 15
2015-03-11 | 2015-11 | 2 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2 | 8 | 12 | 15
2015-03-12 | 2015-11 | 3 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3 | 8 | 12 | 15
2015-03-12 | 2015-11 | 3 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3 | 8 | 12 | 15
2015-03-17 | 2015-12 | 13 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13 | 8 | 12 | 15
2015-03-17 | 2015-12 | 19 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19 | 8 | 12 | 15
2015-03-17 | 2015-12 | 19 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19 | 8 | 12 | 15
2015-03-17 | 2015-12 | 19 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19 | 8 | 12 | 15
2015-03-19 | 2015-12 | 21 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21 | 8 | 12 | 15
2015-03-19 | 2015-12 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8 | 8 | 12 | 15
2015-03-20 | 2015-12 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8 | 8 | 12 | 15
2015-03-20 | 2015-12 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8 | 8 | 12 | 15
2015-03-20 | 2015-12 | 3 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3 | 8 | 12 | 15
2015-03-20 | 2015-12 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8 | 8 | 12 | 15
2015-03-23 | 2015-13 | 6 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6 | 8 | 12 | 15
2015-03-24 | 2015-13 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8 | 8 | 12 | 15
2015-03-24 | 2015-13 | 6 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6 | 8 | 12 | 15
2015-03-26 | 2015-13 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8 | 8 | 12 | 15
2015-03-26 | 2015-13 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8 | 8 | 12 | 15
2015-03-26 | 2015-13 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8 | 8 | 12 | 15
2015-03-31 | 2015-14 | 13 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13 | 8 | 12 | 15
2015-04-02 | 2015-14 | 14 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14 | 8 | 12 | 15
2015-04-02 | 2015-14 | 10 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10 | 8 | 12 | 15
2015-04-02 | 2015-14 | 9 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9 | 8 | 12 | 15
2015-04-02 | 2015-14 | 9 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9 | 8 | 12 | 15
2015-04-02 | 2015-14 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8 | 8 | 12 | 15
2015-04-03 | 2015-14 | 15 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15 | 8 | 12 | 15
2015-04-06 | 2015-15 | 18 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18 | 8 | 12 | 15
2015-04-06 | 2015-15 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7 | 8 | 12 | 15
2015-04-07 | 2015-15 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7 | 8 | 12 | 15
2015-04-08 | 2015-15 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7 | 8 | 12 | 15
2015-04-08 | 2015-15 | 19 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19 | 8 | 12 | 15
2015-04-08 | 2015-15 | 14 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14 | 8 | 12 | 15
2015-04-09 | 2015-15 | 9 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9 | 8 | 12 | 15
2015-04-09 | 2015-15 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7 | 8 | 12 | 15
2015-04-09 | 2015-15 | 6 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6 | 8 | 12 | 15
2015-04-10 | 2015-15 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8 | 8 | 12 | 15
2015-04-10 | 2015-15 | 15 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15 | 8 | 12 | 15
2015-04-10 | 2015-15 | 3 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3 | 8 | 12 | 15
2015-04-14 | 2015-16 | 6 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6 | 8 | 12 | 15
2015-04-14 | 2015-16 | 6 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6 | 8 | 12 | 15
2015-04-16 | 2015-16 | 10 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10 | 8 | 12 | 15
2015-04-16 | 2015-16 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8 | 8 | 12 | 15
2015-04-16 | 2015-16 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8 | 8 | 12 | 15
2015-04-17 | 2015-16 | 15 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15 | 8 | 12 | 15
2015-04-20 | 2015-17 | 12 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12 | 8 | 12 | 15
2015-04-22 | 2015-17 | 14 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14 | 8 | 12 | 15
2015-04-22 | 2015-17 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8 | 8 | 12 | 15
2015-04-23 | 2015-17 | 13 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13 | 8 | 12 | 15
2015-04-23 | 2015-17 | 14 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14 | 8 | 12 | 15
2015-04-23 | 2015-17 | 10 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10 | 8 | 12 | 15
2015-04-23 | 2015-17 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7 | 8 | 12 | 15
2015-04-24 | 2015-17 | 10 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10 | 8 | 12 | 15
2015-04-27 | 2015-18 | 11 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11 | 8 | 12 | 15
2015-04-27 | 2015-18 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7 | 8 | 12 | 15
2015-04-27 | 2015-18 | 10 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10 | 8 | 12 | 15
2015-04-27 | 2015-18 | 5 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5 | 8 | 12 | 15
2015-04-28 | 2015-18 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8 | 8 | 12 | 15
2015-04-28 | 2015-18 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8 | 8 | 12 | 15
2015-04-30 | 2015-18 | 10 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10 | 8 | 12 | 15
2015-05-01 | 2015-18 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8 | 8 | 12 | 15
2015-05-04 | 2015-19 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7 | 8 | 12 | 15
2015-05-04 | 2015-19 | 6 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6 | 8 | 12 | 15
2015-05-05 | 2015-19 | 12 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12 | 8 | 12 | 15
2015-05-06 | 2015-19 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8 | 8 | 12 | 15
2015-05-06 | 2015-19 | 9 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9 | 8 | 12 | 15
2015-05-06 | 2015-19 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8 | 8 | 12 | 15
2015-05-08 | 2015-19 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8 | 8 | 12 | 15
2015-05-08 | 2015-19 | 9 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9 | 8 | 12 | 15
2015-05-11 | 2015-20 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9,7 | 8 | 12 | 15
2015-05-11 | 2015-20 | 14 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9,7,14 | 8 | 12 | 15
2015-05-11 | 2015-20 | 12 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9,7,14,12 | 8 | 12 | 15
2015-05-12 | 2015-20 | 11 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9,7,14,12,11 | 8 | 12 | 15
2015-05-12 | 2015-20 | 6 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9,7,14,12,11,6 | 8 | 12 | 15
2015-05-12 | 2015-20 | 8 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9,7,14,12,11,6,8 | 8 | 12 | 15
2015-05-13 | 2015-20 | 9 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9,7,14,12,11,6,8,9 | 8 | 12 | 15
2015-05-13 | 2015-20 | 9 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9,7,14,12,11,6,8,9,9 | 8 | 12 | 15
2015-05-13 | 2015-20 | 7 | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9,7,14,12,11,6,8,9,9,7 | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
|  |  |  | 8 | 12 | 15
The word Cycle Time means different things to different people. For this spreadsheet, it is the calendar days between two dates. YOU have to define what those dates mean. Does Completed mean delivered to a customer? Does it mean handed off for deployment? The same issue with the start date.Is start when an item is comitted? or when i is created? Please be sure to document what this cycle time means and is captured consistently.
More discussion on the glossary of definitions for cycle time can be found here in a post by Andy Carmichael: http://xprocess.blogspot.co.uk/2015/05/glossary-proposal.html
if you feel strongly this should be renamed TiP (Time in process) then please email me: troy.magennis@focusedobjective.com

## Work in Progress
Date | Year-WeekNum | Work in Progress | Count Started | Count Completed | Cum Started | Cumulative Completed | Week Starting Sunday | Year-WeekNum | Min WIP | Avg WIP | Max WIP | Started this Week | Complete this Week | Delta | Start Cumulative | Complete Cumulative
2015-01-14 | 2015-03 | 3 | 3 | 0 | 3 | 0 | 2015-01-11 | 2015-03 | 3 | 3 | 3 | 3 | 0 | -3 | 3 | 0
2015-01-15 | 2015-03 | 3 | 0 | 0 | 3 | 0 | 2015-01-18 | 2015-04 | 3 | 7.2857 | 12 | 10 | 1 | -9 | 13 | 1
2015-01-16 | 2015-03 | 3 | 0 | 0 | 3 | 0 | 2015-01-25 | 2015-05 | 9 | 12.4286 | 15 | 8 | 5 | -3 | 21 | 6
2015-01-17 | 2015-03 | 3 | 0 | 0 | 3 | 0 | 2015-02-01 | 2015-06 | 11 | 12.7143 | 15 | 7 | 11 | 4 | 28 | 17
2015-01-18 | 2015-04 | 3 | 0 | 0 | 3 | 0 | 2015-02-08 | 2015-07 | 9 | 13.1429 | 16 | 12 | 7 | -5 | 40 | 24
2015-01-19 | 2015-04 | 3 | 0 | 0 | 3 | 0 | 2015-02-15 | 2015-08 | 10 | 13 | 16 | 6 | 7 | 1 | 46 | 31
2015-01-20 | 2015-04 | 6 | 3 | 0 | 6 | 0 | 2015-02-22 | 2015-09 | 11 | 12.7143 | 15 | 13 | 16 | 3 | 59 | 47
2015-01-21 | 2015-04 | 6 | 1 | 1 | 7 | 1 | 2015-03-01 | 2015-10 | 13 | 13.8571 | 16 | 10 | 9 | -1 | 69 | 56
2015-01-22 | 2015-04 | 9 | 3 | 0 | 10 | 1 | 2015-03-08 | 2015-11 | 8 | 10.1429 | 15 | 7 | 11 | 4 | 76 | 67
2015-01-23 | 2015-04 | 12 | 3 | 0 | 13 | 1 | 2015-03-15 | 2015-12 | 8 | 10.8571 | 14 | 12 | 10 | -2 | 88 | 77
2015-01-24 | 2015-04 | 12 | 0 | 0 | 13 | 1 | 2015-03-22 | 2015-13 | 11 | 11.2857 | 13 | 6 | 6 | 0 | 94 | 83
2015-01-25 | 2015-05 | 12 | 0 | 0 | 13 | 1 | 2015-03-29 | 2015-14 | 11 | 12.2857 | 14 | 8 | 7 | -1 | 102 | 90
2015-01-26 | 2015-05 | 9 | 1 | 4 | 14 | 5 | 2015-04-05 | 2015-15 | 10 | 11.4286 | 14 | 10 | 12 | 2 | 112 | 102
2015-01-27 | 2015-05 | 9 | 0 | 0 | 14 | 5 | 2015-04-12 | 2015-16 | 10 | 10.4286 | 11 | 6 | 6 | 0 | 118 | 108
2015-01-28 | 2015-05 | 12 | 3 | 0 | 17 | 5 | 2015-04-19 | 2015-17 | 9 | 10.8571 | 13 | 7 | 8 | 1 | 125 | 116
2015-01-29 | 2015-05 | 15 | 4 | 1 | 21 | 6 | 2015-04-26 | 2015-18 | 8 | 10 | 11 | 10 | 8 | -2 | 135 | 124
2015-01-30 | 2015-05 | 15 | 0 | 0 | 21 | 6 | 2015-05-03 | 2015-19 | 11 | 12.7143 | 14 | 10 | 8 | -2 | 145 | 132
2015-01-31 | 2015-05 | 15 | 0 | 0 | 21 | 6 | 2015-05-10 | 2015-20 | 10 | 11.5 | 13 | 6 | 9 | 3 | 151 | 141
2015-02-01 | 2015-06 | 15 | 0 | 0 | 21 | 6
2015-02-02 | 2015-06 | 14 | 2 | 3 | 23 | 9
2015-02-03 | 2015-06 | 14 | 0 | 0 | 23 | 9
2015-02-04 | 2015-06 | 12 | 3 | 5 | 26 | 14
2015-02-05 | 2015-06 | 12 | 2 | 2 | 28 | 16
2015-02-06 | 2015-06 | 11 | 0 | 1 | 28 | 17
2015-02-07 | 2015-06 | 11 | 0 | 0 | 28 | 17
2015-02-08 | 2015-07 | 11 | 0 | 0 | 28 | 17
2015-02-09 | 2015-07 | 9 | 1 | 3 | 29 | 20
2015-02-10 | 2015-07 | 11 | 3 | 1 | 32 | 21
2015-02-11 | 2015-07 | 14 | 5 | 2 | 37 | 23
2015-02-12 | 2015-07 | 15 | 2 | 1 | 39 | 24
2015-02-13 | 2015-07 | 16 | 1 | 0 | 40 | 24
2015-02-14 | 2015-07 | 16 | 0 | 0 | 40 | 24
2015-02-15 | 2015-08 | 16 | 0 | 0 | 40 | 24
2015-02-16 | 2015-08 | 15 | 0 | 1 | 40 | 25
2015-02-17 | 2015-08 | 10 | 0 | 5 | 40 | 30
2015-02-18 | 2015-08 | 10 | 1 | 1 | 41 | 31
2015-02-19 | 2015-08 | 10 | 0 | 0 | 41 | 31
2015-02-20 | 2015-08 | 15 | 5 | 0 | 46 | 31
2015-02-21 | 2015-08 | 15 | 0 | 0 | 46 | 31
2015-02-22 | 2015-09 | 15 | 0 | 0 | 46 | 31
2015-02-23 | 2015-09 | 14 | 2 | 3 | 48 | 34
2015-02-24 | 2015-09 | 11 | 0 | 3 | 48 | 37
2015-02-25 | 2015-09 | 11 | 4 | 4 | 52 | 41
2015-02-26 | 2015-09 | 14 | 4 | 1 | 56 | 42
2015-02-27 | 2015-09 | 12 | 3 | 5 | 59 | 47
2015-02-28 | 2015-09 | 12 | 0 | 0 | 59 | 47
2015-03-01 | 2015-10 | 13 | 1 | 0 | 60 | 47
2015-03-02 | 2015-10 | 13 | 1 | 1 | 61 | 48
2015-03-03 | 2015-10 | 16 | 4 | 1 | 65 | 49
2015-03-04 | 2015-10 | 15 | 1 | 2 | 66 | 51
2015-03-05 | 2015-10 | 14 | 2 | 3 | 68 | 54
2015-03-06 | 2015-10 | 13 | 1 | 2 | 69 | 56
2015-03-07 | 2015-10 | 13 | 0 | 0 | 69 | 56
2015-03-08 | 2015-11 | 13 | 0 | 0 | 69 | 56
2015-03-09 | 2015-11 | 15 | 3 | 1 | 72 | 57
2015-03-10 | 2015-11 | 8 | 0 | 7 | 72 | 64
2015-03-11 | 2015-11 | 8 | 1 | 1 | 73 | 65
2015-03-12 | 2015-11 | 9 | 3 | 2 | 76 | 67
2015-03-13 | 2015-11 | 9 | 0 | 0 | 76 | 67
2015-03-14 | 2015-11 | 9 | 0 | 0 | 76 | 67
2015-03-15 | 2015-12 | 9 | 0 | 0 | 76 | 67
2015-03-16 | 2015-12 | 10 | 1 | 0 | 77 | 67
2015-03-17 | 2015-12 | 8 | 2 | 4 | 79 | 71
2015-03-18 | 2015-12 | 13 | 5 | 0 | 84 | 71
2015-03-19 | 2015-12 | 14 | 3 | 2 | 87 | 73
2015-03-20 | 2015-12 | 11 | 1 | 4 | 88 | 77
2015-03-21 | 2015-12 | 11 | 0 | 0 | 88 | 77
2015-03-22 | 2015-13 | 11 | 0 | 0 | 88 | 77
2015-03-23 | 2015-13 | 11 | 1 | 1 | 89 | 78
2015-03-24 | 2015-13 | 11 | 2 | 2 | 91 | 80
2015-03-25 | 2015-13 | 13 | 2 | 0 | 93 | 80
2015-03-26 | 2015-13 | 11 | 1 | 3 | 94 | 83
2015-03-27 | 2015-13 | 11 | 0 | 0 | 94 | 83
2015-03-28 | 2015-13 | 11 | 0 | 0 | 94 | 83
2015-03-29 | 2015-14 | 11 | 0 | 0 | 94 | 83
2015-03-30 | 2015-14 | 12 | 1 | 0 | 95 | 83
2015-03-31 | 2015-14 | 13 | 2 | 1 | 97 | 84
2015-04-01 | 2015-14 | 14 | 1 | 0 | 98 | 84
2015-04-02 | 2015-14 | 12 | 3 | 5 | 101 | 89
2015-04-03 | 2015-14 | 12 | 1 | 1 | 102 | 90
2015-04-04 | 2015-14 | 12 | 0 | 0 | 102 | 90
2015-04-05 | 2015-15 | 12 | 0 | 0 | 102 | 90
2015-04-06 | 2015-15 | 11 | 1 | 2 | 103 | 92
2015-04-07 | 2015-15 | 11 | 1 | 1 | 104 | 93
2015-04-08 | 2015-15 | 14 | 6 | 3 | 110 | 96
2015-04-09 | 2015-15 | 12 | 1 | 3 | 111 | 99
2015-04-10 | 2015-15 | 10 | 1 | 3 | 112 | 102
2015-04-11 | 2015-15 | 10 | 0 | 0 | 112 | 102
2015-04-12 | 2015-16 | 10 | 0 | 0 | 112 | 102
2015-04-13 | 2015-16 | 11 | 1 | 0 | 113 | 102
2015-04-14 | 2015-16 | 11 | 2 | 2 | 115 | 104
2015-04-15 | 2015-16 | 11 | 0 | 0 | 115 | 104
2015-04-16 | 2015-16 | 10 | 2 | 3 | 117 | 107
2015-04-17 | 2015-16 | 10 | 1 | 1 | 118 | 108
2015-04-18 | 2015-16 | 10 | 0 | 0 | 118 | 108
2015-04-19 | 2015-17 | 10 | 0 | 0 | 118 | 108
2015-04-20 | 2015-17 | 13 | 4 | 1 | 122 | 109
2015-04-21 | 2015-17 | 13 | 0 | 0 | 122 | 109
2015-04-22 | 2015-17 | 12 | 1 | 2 | 123 | 111
2015-04-23 | 2015-17 | 10 | 2 | 4 | 125 | 115
2015-04-24 | 2015-17 | 9 | 0 | 1 | 125 | 116
2015-04-25 | 2015-17 | 9 | 0 | 0 | 125 | 116
2015-04-26 | 2015-18 | 9 | 0 | 0 | 125 | 116
2015-04-27 | 2015-18 | 8 | 3 | 4 | 128 | 120
2015-04-28 | 2015-18 | 9 | 3 | 2 | 131 | 122
2015-04-29 | 2015-18 | 11 | 2 | 0 | 133 | 122
2015-04-30 | 2015-18 | 11 | 1 | 1 | 134 | 123
2015-05-01 | 2015-18 | 11 | 1 | 1 | 135 | 124
2015-05-02 | 2015-18 | 11 | 0 | 0 | 135 | 124
2015-05-03 | 2015-19 | 11 | 0 | 0 | 135 | 124
2015-05-04 | 2015-19 | 13 | 4 | 2 | 139 | 126
2015-05-05 | 2015-19 | 12 | 0 | 1 | 139 | 127
2015-05-06 | 2015-19 | 13 | 4 | 3 | 143 | 130
2015-05-07 | 2015-19 | 14 | 1 | 0 | 144 | 130
2015-05-08 | 2015-19 | 13 | 1 | 2 | 145 | 132
2015-05-09 | 2015-19 | 13 | 0 | 0 | 145 | 132
2015-05-10 | 2015-20 | 13 | 0 | 0 | 145 | 132
2015-05-11 | 2015-20 | 11 | 1 | 3 | 146 | 135
2015-05-12 | 2015-20 | 12 | 4 | 3 | 150 | 138
2015-05-13 | 2015-20 | 10 | 1 | 3 | 151 | 141
Formulas:
Date = IF(ISNUMBER([Date, row above]),IF([Date, row above]+1<=MAX(IndirectStartDates),[Date, row above]+1,""),"")
Year-WeekNum = IF(ISNUMBER([Date]),YEAR([Date])&"-"&TEXT(WEEKNUM([Date]),"00"),"")
Year-WeekNum = IF(ISNUMBER([Week Starting Sunday]),YEAR([Week Starting Sunday])&"-"&TEXT(WEEKNUM([Week Starting Sunday]),"00"),"")
Week Starting Sunday = IF(ISNUMBER([Week Starting Sunday, row above]),IF([Week Starting Sunday, row above]+7<=MAX(IndirectStartDates),[Week Starting Sunday, row above]+7,""),"")
These calculations and charts are BETA. They are sill undergoing testing and development for both mathematical errors and usability. Please help us test them by double checking these results and emails us if you have errors or suggestions. troy.magennis@focusedobjective.com

## Weibull
Best fit |  |  |  | Estimated Weibull Parameters | All
30% | 7 |  |  | Shape | 2.6916
70% | 11 |  |  | Scale | 10.2669
| actual | estimated | rounded days |  | x | y | cum est
5% | 4 | 3.4056 | 3 |  | 2 | 0.016275 | 0.012168
10% | 5 | 4.4498 | 4 |  | 2.19 | 0.018912 | 0.015508
15% | 6 | 5.2272 | 5 |  | 2.38 | 0.021684 | 0.019363
20% | 6 | 5.8806 | 6 |  | 2.57 | 0.024582 | 0.023756
25% | 7 | 6.4627 | 6 |  | 2.76 | 0.027594 | 0.028711
30% | 7 | 7 | 7 |  | 2.95 | 0.030707 | 0.034248
35% | 7 | 7.5086 | 8 |  | 3.14 | 0.03391 | 0.040386
40% | 8 | 7.9994 | 8 |  | 3.33 | 0.037189 | 0.047139
45% | 8 | 8.4808 | 8 |  | 3.52 | 0.040532 | 0.054521
50% | 8 | 8.9599 | 9 |  | 3.71 | 0.043926 | 0.062544
55% | 9 | 9.4435 | 9 |  | 3.9 | 0.047356 | 0.071216
60% | 9 | 9.9388 | 10 |  | 4.09 | 0.050809 | 0.080541
65% | 10 | 10.4541 | 10 |  | 4.28 | 0.05427 | 0.090524
70% | 11 | 11 | 11 |  | 4.47 | 0.057724 | 0.10116
75% | 12 | 11.5916 | 12 |  | 4.66 | 0.061157 | 0.11246
80% | 13 | 12.2526 | 12 |  | 4.85 | 0.064554 | 0.1244
85% | 13 | 13.0245 | 13 |  | 5.04 | 0.0679 | 0.13698
90% | 14 | 13.9963 | 14 |  | 5.23 | 0.071179 | 0.1502
95% | 15 | 15.4339 | 15 |  | 5.42 | 0.074378 | 0.16403
100% | 21 | 21 | 21 |  | 5.61 | 0.077481 | 0.17846
[5 empty] | 5.8 | 0.080474 | 0.19346
[5 empty] | 5.99 | 0.083344 | 0.20903
[5 empty] | 6.18 | 0.086076 | 0.22513
[5 empty] | 6.37 | 0.088659 | 0.24173
[5 empty] | 6.56 | 0.09108 | 0.25881
[5 empty] | 6.75 | 0.093327 | 0.27633
[5 empty] | 6.94 | 0.09539 | 0.29426
[5 empty] | 7.13 | 0.09726 | 0.31256
[5 empty] | 7.32 | 0.098927 | 0.3312
[5 empty] | 7.51 | 0.10038 | 0.35014
[5 empty] | 7.7 | 0.10162 | 0.36934
[5 empty] | 7.89 | 0.10264 | 0.38875
[5 empty] | 8.08 | 0.10344 | 0.40833
[5 empty] | 8.27 | 0.104 | 0.42804
[5 empty] | 8.46 | 0.10433 | 0.44783
[5 empty] | 8.65 | 0.10444 | 0.46767
[5 empty] | 8.84 | 0.10431 | 0.4875
[5 empty] | 9.03 | 0.10395 | 0.50729
[5 empty] | 9.22 | 0.10338 | 0.52699
[5 empty] | 9.41 | 0.10258 | 0.54656
[5 empty] | 9.6 | 0.10157 | 0.56596
[5 empty] | 9.79 | 0.10035 | 0.58514
[5 empty] | 9.98 | 0.098935 | 0.60408
[5 empty] | 10.17 | 0.097331 | 0.62273
[5 empty] | 10.36 | 0.095549 | 0.64105
[5 empty] | 10.55 | 0.093599 | 0.65903
[5 empty] | 10.74 | 0.091492 | 0.67661
[5 empty] | 10.93 | 0.089242 | 0.69378
[5 empty] | 11.12 | 0.086862 | 0.71051
[5 empty] | 11.31 | 0.084364 | 0.72678
[5 empty] | 11.5 | 0.081762 | 0.74257
[5 empty] | 11.69 | 0.079071 | 0.75785
[5 empty] | 11.88 | 0.076304 | 0.77261
[5 empty] | 12.07 | 0.073474 | 0.78684
[5 empty] | 12.26 | 0.070597 | 0.80053
[5 empty] | 12.45 | 0.067686 | 0.81366
[5 empty] | 12.64 | 0.064753 | 0.82625
[5 empty] | 12.83 | 0.061813 | 0.83827
[5 empty] | 13.02 | 0.058877 | 0.84973
[5 empty] | 13.21 | 0.055957 | 0.86064
[5 empty] | 13.4 | 0.053065 | 0.871
[5 empty] | 13.59 | 0.050211 | 0.88081
[5 empty] | 13.78 | 0.047405 | 0.89008
[5 empty] | 13.97 | 0.044656 | 0.89883
[5 empty] | 14.16 | 0.041973 | 0.90706
[5 empty] | 14.35 | 0.039361 | 0.91478
[5 empty] | 14.54 | 0.036829 | 0.92202
[5 empty] | 14.73 | 0.034382 | 0.92878
[5 empty] | 14.92 | 0.032023 | 0.93509
[5 empty] | 15.11 | 0.029759 | 0.94096
[5 empty] | 15.3 | 0.027591 | 0.9464
[5 empty] | 15.49 | 0.025521 | 0.95145
[5 empty] | 15.68 | 0.023552 | 0.95611
[5 empty] | 15.87 | 0.021684 | 0.9604
[5 empty] | 16.06 | 0.019918 | 0.96436
[5 empty] | 16.25 | 0.018252 | 0.96798
[5 empty] | 16.44 | 0.016686 | 0.9713
[5 empty] | 16.63 | 0.015218 | 0.97433
[5 empty] | 16.82 | 0.013846 | 0.97709
[5 empty] | 17.01 | 0.012567 | 0.97959
[5 empty] | 17.2 | 0.011379 | 0.98187
[5 empty] | 17.39 | 0.010278 | 0.98392
[5 empty] | 17.58 | 0.0092605 | 0.98578
[5 empty] | 17.77 | 0.0083235 | 0.98745
[5 empty] | 17.96 | 0.0074629 | 0.98895
[5 empty] | 18.15 | 0.0066747 | 0.99029
[5 empty] | 18.34 | 0.0059548 | 0.99149
[5 empty] | 18.53 | 0.0052992 | 0.99255
[5 empty] | 18.72 | 0.004704 | 0.9935
[5 empty] | 18.91 | 0.004165 | 0.99435
[5 empty] | 19.1 | 0.0036784 | 0.99509
[5 empty] | 19.29 | 0.0032403 | 0.99575
[5 empty] | 19.48 | 0.002847 | 0.99632
[5 empty] | 19.67 | 0.002495 | 0.99683
[5 empty] | 19.86 | 0.0021809 | 0.99728
[5 empty] | 20.05 | 0.0019013 | 0.99766
[5 empty] | 20.24 | 0.0016532 | 0.998
[5 empty] | 20.43 | 0.0014337 | 0.99829
[5 empty] | 20.62 | 0.00124 | 0.99855
[5 empty] | 20.81 | 0.0010697 | 0.99877
[5 empty] | 21 | 0.00092025 | 0.99895

## Calculations (hidden)
Indirect Completed Dates | Indirect Start Dates | Prior Complete Sunday | Year Complete | WeekNumber Complete | Year-Week Complete | Prior Start Sunday | Year Start | WeekNumber Start | Year-Week Start | Cycle Time (days)
2015-01-21 | 2015-01-14 | 2015-01-18 | 2015 | 4 | 2015-04 | 2015-01-11 | 2015 | 3 | 2015-03 | 7
2015-01-26 | 2015-01-14 | 2015-01-25 | 2015 | 5 | 2015-05 | 2015-01-11 | 2015 | 3 | 2015-03 | 12
2015-01-26 | 2015-01-14 | 2015-01-25 | 2015 | 5 | 2015-05 | 2015-01-11 | 2015 | 3 | 2015-03 | 12
2015-01-26 | 2015-01-21 | 2015-01-25 | 2015 | 5 | 2015-05 | 2015-01-18 | 2015 | 4 | 2015-04 | 5
2015-01-26 | 2015-01-22 | 2015-01-25 | 2015 | 5 | 2015-05 | 2015-01-18 | 2015 | 4 | 2015-04 | 4
2015-01-29 | 2015-01-23 | 2015-01-25 | 2015 | 5 | 2015-05 | 2015-01-18 | 2015 | 4 | 2015-04 | 6
2015-02-02 | 2015-01-23 | 2015-02-01 | 2015 | 6 | 2015-06 | 2015-01-18 | 2015 | 4 | 2015-04 | 10
2015-02-02 | 2015-01-20 | 2015-02-01 | 2015 | 6 | 2015-06 | 2015-01-18 | 2015 | 4 | 2015-04 | 13
2015-02-02 | 2015-01-20 | 2015-02-01 | 2015 | 6 | 2015-06 | 2015-01-18 | 2015 | 4 | 2015-04 | 13
2015-02-04 | 2015-01-20 | 2015-02-01 | 2015 | 6 | 2015-06 | 2015-01-18 | 2015 | 4 | 2015-04 | 15
2015-02-04 | 2015-01-26 | 2015-02-01 | 2015 | 6 | 2015-06 | 2015-01-25 | 2015 | 5 | 2015-05 | 9
2015-02-04 | 2015-01-23 | 2015-02-01 | 2015 | 6 | 2015-06 | 2015-01-18 | 2015 | 4 | 2015-04 | 12
2015-02-04 | 2015-01-22 | 2015-02-01 | 2015 | 6 | 2015-06 | 2015-01-18 | 2015 | 4 | 2015-04 | 13
2015-02-04 | 2015-01-28 | 2015-02-01 | 2015 | 6 | 2015-06 | 2015-01-25 | 2015 | 5 | 2015-05 | 7
2015-02-05 | 2015-01-29 | 2015-02-01 | 2015 | 6 | 2015-06 | 2015-01-25 | 2015 | 5 | 2015-05 | 7
2015-02-05 | 2015-01-22 | 2015-02-01 | 2015 | 6 | 2015-06 | 2015-01-18 | 2015 | 4 | 2015-04 | 14
2015-02-06 | 2015-01-28 | 2015-02-01 | 2015 | 6 | 2015-06 | 2015-01-25 | 2015 | 5 | 2015-05 | 9
2015-02-09 | 2015-01-28 | 2015-02-08 | 2015 | 7 | 2015-07 | 2015-01-25 | 2015 | 5 | 2015-05 | 12
2015-02-09 | 2015-02-02 | 2015-02-08 | 2015 | 7 | 2015-07 | 2015-02-01 | 2015 | 6 | 2015-06 | 7
2015-02-09 | 2015-01-29 | 2015-02-08 | 2015 | 7 | 2015-07 | 2015-01-25 | 2015 | 5 | 2015-05 | 11
2015-02-10 | 2015-01-29 | 2015-02-08 | 2015 | 7 | 2015-07 | 2015-01-25 | 2015 | 5 | 2015-05 | 12
2015-02-11 | 2015-02-04 | 2015-02-08 | 2015 | 7 | 2015-07 | 2015-02-01 | 2015 | 6 | 2015-06 | 7
2015-02-11 | 2015-02-02 | 2015-02-08 | 2015 | 7 | 2015-07 | 2015-02-01 | 2015 | 6 | 2015-06 | 9
2015-02-12 | 2015-01-29 | 2015-02-08 | 2015 | 7 | 2015-07 | 2015-01-25 | 2015 | 5 | 2015-05 | 14
2015-02-16 | 2015-02-05 | 2015-02-15 | 2015 | 8 | 2015-08 | 2015-02-01 | 2015 | 6 | 2015-06 | 11
2015-02-17 | 2015-02-09 | 2015-02-15 | 2015 | 8 | 2015-08 | 2015-02-08 | 2015 | 7 | 2015-07 | 8
2015-02-17 | 2015-02-04 | 2015-02-15 | 2015 | 8 | 2015-08 | 2015-02-01 | 2015 | 6 | 2015-06 | 13
2015-02-17 | 2015-02-04 | 2015-02-15 | 2015 | 8 | 2015-08 | 2015-02-01 | 2015 | 6 | 2015-06 | 13
2015-02-17 | 2015-02-05 | 2015-02-15 | 2015 | 8 | 2015-08 | 2015-02-01 | 2015 | 6 | 2015-06 | 12
2015-02-17 | 2015-02-11 | 2015-02-15 | 2015 | 8 | 2015-08 | 2015-02-08 | 2015 | 7 | 2015-07 | 6
2015-02-18 | 2015-02-11 | 2015-02-15 | 2015 | 8 | 2015-08 | 2015-02-08 | 2015 | 7 | 2015-07 | 7
2015-02-23 | 2015-02-11 | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-08 | 2015 | 7 | 2015-07 | 12
2015-02-23 | 2015-02-12 | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-08 | 2015 | 7 | 2015-07 | 11
2015-02-23 | 2015-02-10 | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-08 | 2015 | 7 | 2015-07 | 13
2015-02-24 | 2015-02-11 | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-08 | 2015 | 7 | 2015-07 | 13
2015-02-24 | 2015-02-11 | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-08 | 2015 | 7 | 2015-07 | 13
2015-02-24 | 2015-02-10 | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-08 | 2015 | 7 | 2015-07 | 14
2015-02-25 | 2015-02-13 | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-08 | 2015 | 7 | 2015-07 | 12
2015-02-25 | 2015-02-10 | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-08 | 2015 | 7 | 2015-07 | 15
2015-02-25 | 2015-02-20 | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-15 | 2015 | 8 | 2015-08 | 5
2015-02-25 | 2015-02-20 | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-15 | 2015 | 8 | 2015-08 | 5
2015-02-26 | 2015-02-18 | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-15 | 2015 | 8 | 2015-08 | 8
2015-02-27 | 2015-02-23 | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-22 | 2015 | 9 | 2015-09 | 4
2015-02-27 | 2015-02-20 | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-15 | 2015 | 8 | 2015-08 | 7
2015-02-27 | 2015-02-20 | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-15 | 2015 | 8 | 2015-08 | 7
2015-02-27 | 2015-02-25 | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-22 | 2015 | 9 | 2015-09 | 2
2015-02-27 | 2015-02-20 | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-15 | 2015 | 8 | 2015-08 | 7
2015-03-02 | 2015-02-25 | 2015-03-01 | 2015 | 10 | 2015-10 | 2015-02-22 | 2015 | 9 | 2015-09 | 5
2015-03-03 | 2015-02-25 | 2015-03-01 | 2015 | 10 | 2015-10 | 2015-02-22 | 2015 | 9 | 2015-09 | 6
2015-03-04 | 2015-02-12 | 2015-03-01 | 2015 | 10 | 2015-10 | 2015-02-08 | 2015 | 7 | 2015-07 | 20
2015-03-04 | 2015-02-27 | 2015-03-01 | 2015 | 10 | 2015-10 | 2015-02-22 | 2015 | 9 | 2015-09 | 5
2015-03-05 | 2015-02-27 | 2015-03-01 | 2015 | 10 | 2015-10 | 2015-02-22 | 2015 | 9 | 2015-09 | 6
2015-03-05 | 2015-02-23 | 2015-03-01 | 2015 | 10 | 2015-10 | 2015-02-22 | 2015 | 9 | 2015-09 | 10
2015-03-05 | 2015-02-25 | 2015-03-01 | 2015 | 10 | 2015-10 | 2015-02-22 | 2015 | 9 | 2015-09 | 8
2015-03-06 | 2015-02-27 | 2015-03-01 | 2015 | 10 | 2015-10 | 2015-02-22 | 2015 | 9 | 2015-09 | 7
2015-03-06 | 2015-03-01 | 2015-03-01 | 2015 | 10 | 2015-10 | 2015-03-01 | 2015 | 10 | 2015-10 | 5
2015-03-09 | 2015-03-02 | 2015-03-08 | 2015 | 11 | 2015-11 | 2015-03-01 | 2015 | 10 | 2015-10 | 7
2015-03-10 | 2015-03-03 | 2015-03-08 | 2015 | 11 | 2015-11 | 2015-03-01 | 2015 | 10 | 2015-10 | 7
2015-03-10 | 2015-03-03 | 2015-03-08 | 2015 | 11 | 2015-11 | 2015-03-01 | 2015 | 10 | 2015-10 | 7
2015-03-10 | 2015-03-05 | 2015-03-08 | 2015 | 11 | 2015-11 | 2015-03-01 | 2015 | 10 | 2015-10 | 5
2015-03-10 | 2015-03-03 | 2015-03-08 | 2015 | 11 | 2015-11 | 2015-03-01 | 2015 | 10 | 2015-10 | 7
2015-03-10 | 2015-03-03 | 2015-03-08 | 2015 | 11 | 2015-11 | 2015-03-01 | 2015 | 10 | 2015-10 | 7
2015-03-10 | 2015-03-06 | 2015-03-08 | 2015 | 11 | 2015-11 | 2015-03-01 | 2015 | 10 | 2015-10 | 4
2015-03-10 | 2015-03-05 | 2015-03-08 | 2015 | 11 | 2015-11 | 2015-03-01 | 2015 | 10 | 2015-10 | 5
2015-03-11 | 2015-03-09 | 2015-03-08 | 2015 | 11 | 2015-11 | 2015-03-08 | 2015 | 11 | 2015-11 | 2
2015-03-12 | 2015-03-09 | 2015-03-08 | 2015 | 11 | 2015-11 | 2015-03-08 | 2015 | 11 | 2015-11 | 3
2015-03-12 | 2015-03-09 | 2015-03-08 | 2015 | 11 | 2015-11 | 2015-03-08 | 2015 | 11 | 2015-11 | 3
2015-03-17 | 2015-03-04 | 2015-03-15 | 2015 | 12 | 2015-12 | 2015-03-01 | 2015 | 10 | 2015-10 | 13
2015-03-17 | 2015-02-26 | 2015-03-15 | 2015 | 12 | 2015-12 | 2015-02-22 | 2015 | 9 | 2015-09 | 19
2015-03-17 | 2015-02-26 | 2015-03-15 | 2015 | 12 | 2015-12 | 2015-02-22 | 2015 | 9 | 2015-09 | 19
2015-03-17 | 2015-02-26 | 2015-03-15 | 2015 | 12 | 2015-12 | 2015-02-22 | 2015 | 9 | 2015-09 | 19
2015-03-19 | 2015-02-26 | 2015-03-15 | 2015 | 12 | 2015-12 | 2015-02-22 | 2015 | 9 | 2015-09 | 21
2015-03-19 | 2015-03-11 | 2015-03-15 | 2015 | 12 | 2015-12 | 2015-03-08 | 2015 | 11 | 2015-11 | 8
2015-03-20 | 2015-03-12 | 2015-03-15 | 2015 | 12 | 2015-12 | 2015-03-08 | 2015 | 11 | 2015-11 | 8
2015-03-20 | 2015-03-12 | 2015-03-15 | 2015 | 12 | 2015-12 | 2015-03-08 | 2015 | 11 | 2015-11 | 8
2015-03-20 | 2015-03-17 | 2015-03-15 | 2015 | 12 | 2015-12 | 2015-03-15 | 2015 | 12 | 2015-12 | 3
2015-03-20 | 2015-03-12 | 2015-03-15 | 2015 | 12 | 2015-12 | 2015-03-08 | 2015 | 11 | 2015-11 | 8
2015-03-23 | 2015-03-17 | 2015-03-22 | 2015 | 13 | 2015-13 | 2015-03-15 | 2015 | 12 | 2015-12 | 6
2015-03-24 | 2015-03-16 | 2015-03-22 | 2015 | 13 | 2015-13 | 2015-03-15 | 2015 | 12 | 2015-12 | 8
2015-03-24 | 2015-03-18 | 2015-03-22 | 2015 | 13 | 2015-13 | 2015-03-15 | 2015 | 12 | 2015-12 | 6
2015-03-26 | 2015-03-18 | 2015-03-22 | 2015 | 13 | 2015-13 | 2015-03-15 | 2015 | 12 | 2015-12 | 8
2015-03-26 | 2015-03-18 | 2015-03-22 | 2015 | 13 | 2015-13 | 2015-03-15 | 2015 | 12 | 2015-12 | 8
2015-03-26 | 2015-03-18 | 2015-03-22 | 2015 | 13 | 2015-13 | 2015-03-15 | 2015 | 12 | 2015-12 | 8
2015-03-31 | 2015-03-18 | 2015-03-29 | 2015 | 14 | 2015-14 | 2015-03-15 | 2015 | 12 | 2015-12 | 13
2015-04-02 | 2015-03-19 | 2015-03-29 | 2015 | 14 | 2015-14 | 2015-03-15 | 2015 | 12 | 2015-12 | 14
2015-04-02 | 2015-03-23 | 2015-03-29 | 2015 | 14 | 2015-14 | 2015-03-22 | 2015 | 13 | 2015-13 | 10
2015-04-02 | 2015-03-24 | 2015-03-29 | 2015 | 14 | 2015-14 | 2015-03-22 | 2015 | 13 | 2015-13 | 9
2015-04-02 | 2015-03-24 | 2015-03-29 | 2015 | 14 | 2015-14 | 2015-03-22 | 2015 | 13 | 2015-13 | 9
2015-04-02 | 2015-03-25 | 2015-03-29 | 2015 | 14 | 2015-14 | 2015-03-22 | 2015 | 13 | 2015-13 | 8
2015-04-03 | 2015-03-19 | 2015-03-29 | 2015 | 14 | 2015-14 | 2015-03-15 | 2015 | 12 | 2015-12 | 15
2015-04-06 | 2015-03-19 | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-03-15 | 2015 | 12 | 2015-12 | 18
2015-04-06 | 2015-03-30 | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-03-29 | 2015 | 14 | 2015-14 | 7
2015-04-07 | 2015-03-31 | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-03-29 | 2015 | 14 | 2015-14 | 7
2015-04-08 | 2015-04-01 | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-03-29 | 2015 | 14 | 2015-14 | 7
2015-04-08 | 2015-03-20 | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-03-15 | 2015 | 12 | 2015-12 | 19
2015-04-08 | 2015-03-25 | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-03-22 | 2015 | 13 | 2015-13 | 14
2015-04-09 | 2015-03-31 | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-03-29 | 2015 | 14 | 2015-14 | 9
2015-04-09 | 2015-04-02 | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-03-29 | 2015 | 14 | 2015-14 | 7
2015-04-09 | 2015-04-03 | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-03-29 | 2015 | 14 | 2015-14 | 6
2015-04-10 | 2015-04-02 | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-03-29 | 2015 | 14 | 2015-14 | 8
2015-04-10 | 2015-03-26 | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-03-22 | 2015 | 13 | 2015-13 | 15
2015-04-10 | 2015-04-07 | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-04-05 | 2015 | 15 | 2015-15 | 3
2015-04-14 | 2015-04-08 | 2015-04-12 | 2015 | 16 | 2015-16 | 2015-04-05 | 2015 | 15 | 2015-15 | 6
2015-04-14 | 2015-04-08 | 2015-04-12 | 2015 | 16 | 2015-16 | 2015-04-05 | 2015 | 15 | 2015-15 | 6
2015-04-16 | 2015-04-06 | 2015-04-12 | 2015 | 16 | 2015-16 | 2015-04-05 | 2015 | 15 | 2015-15 | 10
2015-04-16 | 2015-04-08 | 2015-04-12 | 2015 | 16 | 2015-16 | 2015-04-05 | 2015 | 15 | 2015-15 | 8
2015-04-16 | 2015-04-08 | 2015-04-12 | 2015 | 16 | 2015-16 | 2015-04-05 | 2015 | 15 | 2015-15 | 8
2015-04-17 | 2015-04-02 | 2015-04-12 | 2015 | 16 | 2015-16 | 2015-03-29 | 2015 | 14 | 2015-14 | 15
2015-04-20 | 2015-04-08 | 2015-04-19 | 2015 | 17 | 2015-17 | 2015-04-05 | 2015 | 15 | 2015-15 | 12
2015-04-22 | 2015-04-08 | 2015-04-19 | 2015 | 17 | 2015-17 | 2015-04-05 | 2015 | 15 | 2015-15 | 14
2015-04-22 | 2015-04-14 | 2015-04-19 | 2015 | 17 | 2015-17 | 2015-04-12 | 2015 | 16 | 2015-16 | 8
2015-04-23 | 2015-04-10 | 2015-04-19 | 2015 | 17 | 2015-17 | 2015-04-05 | 2015 | 15 | 2015-15 | 13
2015-04-23 | 2015-04-09 | 2015-04-19 | 2015 | 17 | 2015-17 | 2015-04-05 | 2015 | 15 | 2015-15 | 14
2015-04-23 | 2015-04-13 | 2015-04-19 | 2015 | 17 | 2015-17 | 2015-04-12 | 2015 | 16 | 2015-16 | 10
2015-04-23 | 2015-04-16 | 2015-04-19 | 2015 | 17 | 2015-17 | 2015-04-12 | 2015 | 16 | 2015-16 | 7
2015-04-24 | 2015-04-14 | 2015-04-19 | 2015 | 17 | 2015-17 | 2015-04-12 | 2015 | 16 | 2015-16 | 10
2015-04-27 | 2015-04-16 | 2015-04-26 | 2015 | 18 | 2015-18 | 2015-04-12 | 2015 | 16 | 2015-16 | 11
2015-04-27 | 2015-04-20 | 2015-04-26 | 2015 | 18 | 2015-18 | 2015-04-19 | 2015 | 17 | 2015-17 | 7
2015-04-27 | 2015-04-17 | 2015-04-26 | 2015 | 18 | 2015-18 | 2015-04-12 | 2015 | 16 | 2015-16 | 10
2015-04-27 | 2015-04-22 | 2015-04-26 | 2015 | 18 | 2015-18 | 2015-04-19 | 2015 | 17 | 2015-17 | 5
2015-04-28 | 2015-04-20 | 2015-04-26 | 2015 | 18 | 2015-18 | 2015-04-19 | 2015 | 17 | 2015-17 | 8
2015-04-28 | 2015-04-20 | 2015-04-26 | 2015 | 18 | 2015-18 | 2015-04-19 | 2015 | 17 | 2015-17 | 8
2015-04-30 | 2015-04-20 | 2015-04-26 | 2015 | 18 | 2015-18 | 2015-04-19 | 2015 | 17 | 2015-17 | 10
2015-05-01 | 2015-04-23 | 2015-04-26 | 2015 | 18 | 2015-18 | 2015-04-19 | 2015 | 17 | 2015-17 | 8
2015-05-04 | 2015-04-27 | 2015-05-03 | 2015 | 19 | 2015-19 | 2015-04-26 | 2015 | 18 | 2015-18 | 7
2015-05-04 | 2015-04-28 | 2015-05-03 | 2015 | 19 | 2015-19 | 2015-04-26 | 2015 | 18 | 2015-18 | 6
2015-05-05 | 2015-04-23 | 2015-05-03 | 2015 | 19 | 2015-19 | 2015-04-19 | 2015 | 17 | 2015-17 | 12
2015-05-06 | 2015-04-28 | 2015-05-03 | 2015 | 19 | 2015-19 | 2015-04-26 | 2015 | 18 | 2015-18 | 8
2015-05-06 | 2015-04-27 | 2015-05-03 | 2015 | 19 | 2015-19 | 2015-04-26 | 2015 | 18 | 2015-18 | 9
2015-05-06 | 2015-04-28 | 2015-05-03 | 2015 | 19 | 2015-19 | 2015-04-26 | 2015 | 18 | 2015-18 | 8
2015-05-08 | 2015-04-30 | 2015-05-03 | 2015 | 19 | 2015-19 | 2015-04-26 | 2015 | 18 | 2015-18 | 8
2015-05-08 | 2015-04-29 | 2015-05-03 | 2015 | 19 | 2015-19 | 2015-04-26 | 2015 | 18 | 2015-18 | 9
2015-05-11 | 2015-05-04 | 2015-05-10 | 2015 | 20 | 2015-20 | 2015-05-03 | 2015 | 19 | 2015-19 | 7
2015-05-11 | 2015-04-27 | 2015-05-10 | 2015 | 20 | 2015-20 | 2015-04-26 | 2015 | 18 | 2015-18 | 14
2015-05-11 | 2015-04-29 | 2015-05-10 | 2015 | 20 | 2015-20 | 2015-04-26 | 2015 | 18 | 2015-18 | 12
2015-05-12 | 2015-05-01 | 2015-05-10 | 2015 | 20 | 2015-20 | 2015-04-26 | 2015 | 18 | 2015-18 | 11
2015-05-12 | 2015-05-06 | 2015-05-10 | 2015 | 20 | 2015-20 | 2015-05-03 | 2015 | 19 | 2015-19 | 6
2015-05-12 | 2015-05-04 | 2015-05-10 | 2015 | 20 | 2015-20 | 2015-05-03 | 2015 | 19 | 2015-19 | 8
2015-05-13 | 2015-05-04 | 2015-05-10 | 2015 | 20 | 2015-20 | 2015-05-03 | 2015 | 19 | 2015-19 | 9
2015-05-13 | 2015-05-04 | 2015-05-10 | 2015 | 20 | 2015-20 | 2015-05-03 | 2015 | 19 | 2015-19 | 9
2015-05-13 | 2015-05-06 | 2015-05-10 | 2015 | 20 | 2015-20 | 2015-05-03 | 2015 | 19 | 2015-19 | 7
| 2015-05-06 |  |  |  |  | 2015-05-03 | 2015 | 19 | 2015-19 | #N/A
| 2015-05-08 |  |  |  |  | 2015-05-03 | 2015 | 19 | 2015-19 | #N/A
| 2015-05-12 |  |  |  |  | 2015-05-10 | 2015 | 20 | 2015-20 | #N/A
| 2015-05-11 |  |  |  |  | 2015-05-10 | 2015 | 20 | 2015-20 | #N/A
| 2015-05-12 |  |  |  |  | 2015-05-10 | 2015 | 20 | 2015-20 | #N/A
| 2015-05-12 |  |  |  |  | 2015-05-10 | 2015 | 20 | 2015-20 | #N/A
| 2015-05-06 |  |  |  |  | 2015-05-03 | 2015 | 19 | 2015-19 | #N/A
| 2015-05-07 |  |  |  |  | 2015-05-03 | 2015 | 19 | 2015-19 | #N/A
| 2015-05-12 |  |  |  |  | 2015-05-10 | 2015 | 20 | 2015-20 | #N/A
| 2015-05-13 |  |  |  |  | 2015-05-10 | 2015 | 20 | 2015-20 | #N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
Formulas:
Indirect Completed Dates = IF(INDEX(CompletedDateValues,ROW([Indirect Completed Dates]))>0,INT(INDEX(CompletedDateValues,ROW([Indirect Completed Dates]))),"")
Indirect Start Dates = IF(INDEX(StartDateValues,ROW([Indirect Completed Dates]))>0,INT(INDEX(StartDateValues,ROW([Indirect Completed Dates]))),"")
Prior Complete Sunday = IF([Indirect Completed Dates]="","",[Indirect Completed Dates] - (WEEKDAY([Indirect Completed Dates])-1))
WeekNumber Complete = IF([Prior Complete Sunday]="","",WEEKNUM([Prior Complete Sunday]))
Prior Start Sunday = IF([Indirect Start Dates]="","",[Indirect Start Dates] - (WEEKDAY([Indirect Start Dates])-1))
WeekNumber Start = IF([Prior Start Sunday]="","",WEEKNUM([Prior Start Sunday]))
Column A and B grab data from the "Your Data" sheet by indirect reference. This allows you to cut and copy and move rows in your data without corrupting the formula cell references.
This is the prior sunday for the completed date. This date is used as the start of week.
This is a neatly formatted week group name. It makes the week number two digits so that groupds sort chronologically.
This is the number of days between start and end. If the dates are flipped, it returns 0 days. If work finishes on the same day, it uses the value on the Settings tab. Typically this is 0.5 or 1 day.