## Instructions
Team Dashboard
The basis of this dashboard comes from work completed by Larry Maccherone.
The important point: Measure at least one metric TREND in four different areas.
Why: Because these four areas of metrics work in natural tension, so balance is an imperative.
Benefits-
1. Intentionally choosing to move one metric might jhave unintended consequences in the others.
2. See the actual impat of procss improvements over time. Loo at the trend, not the numbers
3. Understand what is important in your teams context.
- Is is fast response to product issues (Responsiveness?)
- Is is delivery pace with good quality?
What is this: This spreadsheet takes work item/story/defect data and creates team dashboard
How to: Get a list of completed dates (ata minimum) for each item in your electronic tracking tool. Enter this data in Column A in the "Your Data" worksheet. ptionally add the start date, and any other field values that help you manage this data.
Ideas, errors, requests? Email: troy.magennis@focusedobjective.com
Work licensed under a Creative Commons Attribution-NonCommercial-ShareAlike 4.0 International License.
Details here: http://creativecommons.org/licenses/by-nc-sa/4.0/ and
http://creativecommons.org/licenses/by-nc-sa/4.0/legalcode
Get more tools like this from: http://bit.ly/SimResources
About us: Focused Objective LLC offers tools, training and expert advice on metrics, risk and forecasting. We have more advanced tools to model Agile teams and projects that help analyze staffing options and risk, and a proven track record of positive results. We are always happy to discuss next steps and training opportunities should this tool prove useful. See our website: http://www.focusedobjective.com or email me at troy.magennis@focusedobjective.com.
Please don't by this book on Amazon; its out of date (we leave it there for people who insist on a hard-copy). Go to Bit.ly/agilesim as it says on the card and download for free.
Also - please hire us! we can help with metrics, forecasting and risk management of Agile projects. We are able to make these tools free because we are called upon for our expertise often. Either way, talk to us first before looking elsewhere!

## Your Data
Completed Date | Start Date (optional) | Type (optional) | Id (optional) | Description (optional)
2015-01-21 | 2015-01-14
2015-01-26 | 2015-01-14 | Story
2015-01-26 | 2015-01-14 | Defect
2015-01-26 | 2015-01-21 | Story
2015-01-26 | 2015-01-22 | Story
2015-01-29 | 2015-01-23 | Story
2015-02-02 | 2015-01-23 | Story
2015-02-02 | 2015-01-20 | Defect
2015-02-02 | 2015-01-20 | Defect
2015-02-04 | 2015-01-20
2015-02-04 | 2015-01-26
2015-02-04 | 2015-01-23
2015-02-04 | 2015-01-22
2015-02-04 | 2015-01-28
2015-02-05 | 2015-01-29
2015-02-05 | 2015-01-22
2015-02-06 | 2015-01-28 | Defect
2015-02-09 | 2015-01-28
2015-02-09 | 2015-02-02
2015-02-09 | 2015-01-29 | Defect
2015-02-10 | 2015-01-29 | Defect
2015-02-11 | 2015-02-04
2015-02-11 | 2015-02-02
2015-02-12 | 2015-01-29
2015-02-16 | 2015-02-05
2015-02-17 | 2015-02-09
2015-02-17 | 2015-02-04
2015-02-17 | 2015-02-04
2015-02-17 | 2015-02-05 | Defect
2015-02-17 | 2015-02-11
2015-02-18 | 2015-02-11
2015-02-23 | 2015-02-11
2015-02-23 | 2015-02-12 | Defect
2015-02-23 | 2015-02-10
2015-02-24 | 2015-02-11 | Defect
2015-02-24 | 2015-02-11
2015-02-24 | 2015-02-10
2015-02-25 | 2015-02-13
2015-02-25 | 2015-02-10 | Defect
2015-02-25 | 2015-02-20
2015-02-25 | 2015-02-20
2015-02-26 | 2015-02-18 | Defect
2015-02-27 | 2015-02-23 | Defect
2015-02-27 | 2015-02-20
2015-02-27 | 2015-02-20
2015-02-27 | 2015-02-25
2015-02-27 | 2015-02-20
2015-03-02 | 2015-02-25
2015-03-03 | 2015-02-25 | Defect
2015-03-04 | 2015-02-12 | Defect
2015-03-04 | 2015-02-27 | Defect
2015-03-05 | 2015-02-27
2015-03-05 | 2015-02-23
2015-03-05 | 2015-02-25
2015-03-06 | 2015-02-27
2015-03-06 | 2015-03-01
2015-03-09 | 2015-03-02
2015-03-10 | 2015-03-03
2015-03-10 | 2015-03-03
2015-03-10 | 2015-03-05
2015-03-10 | 2015-03-03
2015-03-10 | 2015-03-03
2015-03-10 | 2015-03-06 | Defect
2015-03-10 | 2015-03-05
2015-03-11 | 2015-03-09
2015-03-12 | 2015-03-09
2015-03-12 | 2015-03-09
2015-03-17 | 2015-03-04 | Defect
2015-03-17 | 2015-02-26
2015-03-17 | 2015-02-26
2015-03-17 | 2015-02-26
2015-03-19 | 2015-02-26
2015-03-19 | 2015-03-11
2015-03-20 | 2015-03-12 | Defect
2015-03-20 | 2015-03-12 | Defect
2015-03-20 | 2015-03-17
2015-03-20 | 2015-03-12
2015-03-23 | 2015-03-17
2015-03-24 | 2015-03-16 | Defect
2015-03-24 | 2015-03-18
2015-03-26 | 2015-03-18
2015-03-26 | 2015-03-18
2015-03-26 | 2015-03-18 | Defect
2015-03-31 | 2015-03-18
2015-04-02 | 2015-03-19
2015-04-02 | 2015-03-23 | Defect
2015-04-02 | 2015-03-24
2015-04-02 | 2015-03-24
2015-04-02 | 2015-03-25
2015-04-03 | 2015-03-19
2015-04-06 | 2015-03-19
2015-04-06 | 2015-03-30
2015-04-07 | 2015-03-31
2015-04-08 | 2015-04-01
2015-04-08 | 2015-03-20 | Defect
2015-04-08 | 2015-03-25
2015-04-09 | 2015-03-31
2015-04-09 | 2015-04-02
2015-04-09 | 2015-04-03
2015-04-10 | 2015-04-02
2015-04-10 | 2015-03-26
2015-04-10 | 2015-04-07
2015-04-14 | 2015-04-08
2015-04-14 | 2015-04-08 | Defect
2015-04-16 | 2015-04-06
2015-04-16 | 2015-04-08
2015-04-16 | 2015-04-08
2015-04-17 | 2015-04-02
2015-04-20 | 2015-04-08
2015-04-22 | 2015-04-08
2015-04-22 | 2015-04-14
2015-04-23 | 2015-04-10
2015-04-23 | 2015-04-09
2015-04-23 | 2015-04-13 | Defect
2015-04-23 | 2015-04-16
2015-04-24 | 2015-04-14
2015-04-27 | 2015-04-16
2015-04-27 | 2015-04-20
2015-04-27 | 2015-04-17
2015-04-27 | 2015-04-22
2015-04-28 | 2015-04-20
2015-04-28 | 2015-04-20
2015-04-30 | 2015-04-20
2015-05-01 | 2015-04-23
2015-05-04 | 2015-04-27
2015-05-04 | 2015-04-28
2015-05-05 | 2015-04-23
2015-05-06 | 2015-04-28
2015-05-06 | 2015-04-27 | Defect
2015-05-06 | 2015-04-28 | Defect
2015-05-08 | 2015-04-30
2015-05-08 | 2015-04-29
2015-05-11 | 2015-05-04
2015-05-11 | 2015-04-27
2015-05-11 | 2015-04-29
2015-05-12 | 2015-05-01 | Defect
2015-05-12 | 2015-05-06
2015-05-12 | 2015-05-04
2015-05-13 | 2015-05-04
2015-05-13 | 2015-05-04 | Defect
2015-05-13 | 2015-05-06
2015-05-06
2015-05-08
2015-05-12
2015-05-11
2015-05-12
2015-05-12
| 2015-05-06 | Defect
| 2015-05-07 | Defect
| 2015-05-12 | Defect
| 2015-05-13 | Defect
Put your data on this sheet.
For throughput: Only the completed date is needed.
For cycle-time and WIP, the completed date and start date is needed.
The Type, Id and Description fields are just for your convenience.
More than 5,000 rows? You will need to update the Calculations worksheet. See instructions there.
Set the Type column to show what work is planned and un-planned. Use the Settings worksheet to specify what value is for planned work and unplanned work. Any row with a blank Type is defaulted to Planned work.

## Team Dashboard
Awesome Team Dashboard | (change your team name in the Settings tab)
Quality - How Well |  | Responsiveness - How Fast
How much defect debt do we carry that impedes consistent delivery? |  | How fast do we deliver from starting something to finishing it? Goal: Look for ways to reduce time and variability for similar work.
Productivity - How Much |  | Predictability - How Repeatable
What pace do we deliver work? Goal: Look for ways to increase. Watch quality if you overdrive. |  | How consistent is our completion pace? Goal: Keep around zero. Complete something in preference to starting.

## Throughput (hidden)
Week Starting | Week Ending | week groups | Throughput | Normalized | Stories Throughput | Defects Throughput | Defects Rate | CSV | Percentiles
2015-01-18 | 2015-01-24 | 2015-04 | 1 | 0 | 1 | 0 | 0% | 1 | min | 5% | 25% | 50% | 75% | 95% | max
2015-01-25 | 2015-01-31 | 2015-05 | 5 | 0.26667 | 4 | 1 | 20% | 1,5 | 1 | 4.2 | 7 | 8 | 10 | 12.8 | 16
2015-02-01 | 2015-02-07 | 2015-06 | 11 | 0.66667 | 8 | 3 | 27.27% | 1,5,11
2015-02-08 | 2015-02-14 | 2015-07 | 7 | 0.4 | 5 | 2 | 28.57% | 1,5,11,7 | Bin | Frequency
2015-02-15 | 2015-02-21 | 2015-08 | 7 | 0.4 | 6 | 1 | 14.29% | 1,5,11,7,7 | 1 | 1 |  |  | Unplanned rate average |  |  | 19.19%
2015-02-22 | 2015-02-28 | 2015-09 | 16 | 1 | 11 | 5 | 31.25% | 1,5,11,7,7,16 | 2 | 0 |  |  | Unplanned rate chart header |  |  | Defects Percentage Rate (avg: 19.19%)
2015-03-01 | 2015-03-07 | 2015-10 | 9 | 0.53333 | 6 | 3 | 33.33% | 1,5,11,7,7,16,9 | 3 | 0
2015-03-08 | 2015-03-14 | 2015-11 | 11 | 0.66667 | 10 | 1 | 9.091% | 1,5,11,7,7,16,9,11 | 4 | 0
2015-03-15 | 2015-03-21 | 2015-12 | 10 | 0.6 | 7 | 3 | 30% | 1,5,11,7,7,16,9,11,10 | 5 | 1
2015-03-22 | 2015-03-28 | 2015-13 | 6 | 0.33333 | 4 | 2 | 33.33% | 1,5,11,7,7,16,9,11,10,6 | 6 | 2
2015-03-29 | 2015-04-04 | 2015-14 | 7 | 0.4 | 6 | 1 | 14.29% | 1,5,11,7,7,16,9,11,10,6,7 | 7 | 3
2015-04-05 | 2015-04-11 | 2015-15 | 12 | 0.73333 | 11 | 1 | 8.333% | 1,5,11,7,7,16,9,11,10,6,7,12 | 8 | 3
2015-04-12 | 2015-04-18 | 2015-16 | 6 | 0.33333 | 5 | 1 | 16.67% | 1,5,11,7,7,16,9,11,10,6,7,12,6 | 9 | 2
2015-04-19 | 2015-04-25 | 2015-17 | 8 | 0.46667 | 7 | 1 | 12.5% | 1,5,11,7,7,16,9,11,10,6,7,12,6,8 | 10 | 1
2015-04-26 | 2015-05-02 | 2015-18 | 8 | 0.46667 | 8 | 0 | 0% | 1,5,11,7,7,16,9,11,10,6,7,12,6,8,8 | 11 | 2
2015-05-03 | 2015-05-09 | 2015-19 | 8 | 0.46667 | 6 | 2 | 25% | 1,5,11,7,7,16,9,11,10,6,7,12,6,8,8,8 | 12 | 1
2015-05-10 | 2015-05-16 | 2015-20 | 9 | 0.53333 | 7 | 2 | 22.22% | 1,5,11,7,7,16,9,11,10,6,7,12,6,8,8,8,9 | 13 | 0
[9 empty] | 14 | 0
[9 empty] | 15 | 0
[9 empty] | 16 | 1
[9 empty] | 17 | 0
[9 empty] | 18 | 0
[9 empty] | 19 | 0
[9 empty] | 20 | 0
[9 empty] | 21 | 0

## Cycle Time (hidden)
Completed Date | Week Group | Cycle Time (days) | Stories Time in Process | Stories 95% = 15 days | Defects Time in Process | Defects 95% = 17.4 days | Stories In-Progress Age | Defects In-Progress Age | CSV | Week Starting | Week Ending | week groups | Min Cycle Time | Avg Cycle Time | Max Cycle Time | 25th Percentile | 30th | Median | 70th | 75th Percentile | 85th | Percentiles
2015-01-21 | 2015-04 | 7 | 7 | 15 | #N/A | 17.4 | #N/A | #N/A | 7 | 2015-01-18 | 2015-01-24 | 2015-04 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Min | 0.05 | 0.25 | 0.5 | 0.75 | 0.95 | Max
2015-01-26 | 2015-05 | 12 | 12 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12 | 2015-01-25 | 2015-01-31 | 2015-05 | 4 | 7.8 | 12 | 5 | 5.2 | 6 | 10.8 | 12 | 12 | 2 | 4 | 7 | 8 | 12 | 15 | 21
2015-01-26 | 2015-05 | 12 | #N/A | 15 | 12 | 17.4 | #N/A | #N/A | 7,12,12 | 2015-02-01 | 2015-02-07 | 2015-06 | 7 | 11.0909 | 15 | 9 | 9 | 12 | 13 | 13 | 13.5
2015-01-26 | 2015-05 | 5 | 5 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5 | 2015-02-08 | 2015-02-14 | 2015-07 | 7 | 10.2857 | 14 | 8 | 8.6 | 11 | 12 | 12 | 12.2 | Bin | Frequency | Stories | Defects
2015-01-26 | 2015-05 | 4 | 4 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4 | 2015-02-15 | 2015-02-21 | 2015-08 | 6 | 10 | 13 | 7.5 | 7.8 | 11 | 12.2 | 12.5 | 13 | 2 | 2 | 2 | 0
2015-01-29 | 2015-05 | 6 | 6 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6 | 2015-02-22 | 2015-02-28 | 2015-09 | 2 | 9.25 | 15 | 6.5 | 7 | 9.5 | 12.5 | 13 | 13 | 3 | 4 | 4 | 0
2015-02-02 | 2015-06 | 10 | 10 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10 | 2015-03-01 | 2015-03-07 | 2015-10 | 5 | 8 | 20 | 5 | 5.4 | 6 | 7.6 | 8 | 9.6 | 4 | 3 | 1 | 2
2015-02-02 | 2015-06 | 13 | #N/A | 15 | 13 | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13 | 2015-03-08 | 2015-03-14 | 2015-11 | 2 | 5.1818 | 7 | 3.5 | 4 | 5 | 7 | 7 | 7 | 5 | 9 | 8 | 1
2015-02-02 | 2015-06 | 13 | #N/A | 15 | 13 | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13 | 2015-03-15 | 2015-03-21 | 2015-12 | 3 | 12.6 | 21 | 8 | 8 | 10.5 | 19 | 19 | 19 | 6 | 11 | 9 | 2
2015-02-04 | 2015-06 | 15 | 15 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15 | 2015-03-22 | 2015-03-28 | 2015-13 | 6 | 7.3333 | 8 | 6.5 | 7 | 8 | 8 | 8 | 8 | 7 | 24 | 24 | 0
2015-02-04 | 2015-06 | 9 | 9 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9 | 2015-03-29 | 2015-04-04 | 2015-14 | 8 | 11.1429 | 15 | 9 | 9 | 10 | 13.2 | 13.5 | 14.1 | 8 | 23 | 17 | 6
2015-02-04 | 2015-06 | 12 | 12 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12 | 2015-04-05 | 2015-04-11 | 2015-15 | 3 | 10 | 19 | 7 | 7 | 7.5 | 12.5 | 14.25 | 16.05 | 9 | 10 | 7 | 3
2015-02-04 | 2015-06 | 13 | 13 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13 | 2015-04-12 | 2015-04-18 | 2015-16 | 6 | 8.8333 | 15 | 6.5 | 7 | 8 | 9 | 9.5 | 11.25 | 10 | 8 | 6 | 2
2015-02-04 | 2015-06 | 7 | 7 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7 | 2015-04-19 | 2015-04-25 | 2015-17 | 7 | 11 | 14 | 9.5 | 10 | 11 | 12.9 | 13.25 | 13.95 | 11 | 5 | 2 | 3
2015-02-05 | 2015-06 | 7 | 7 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7 | 2015-04-26 | 2015-05-02 | 2015-18 | 5 | 8.375 | 11 | 7.75 | 8 | 8 | 9.8 | 10 | 10 | 12 | 11 | 8 | 3
2015-02-05 | 2015-06 | 14 | 14 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14 | 2015-05-03 | 2015-05-09 | 2015-19 | 6 | 8.375 | 12 | 7.75 | 8 | 8 | 8.9 | 9 | 9 | 13 | 11 | 7 | 4
2015-02-06 | 2015-06 | 9 | #N/A | 15 | 9 | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9 | 2015-05-10 | 2015-05-16 | 2015-20 | 6 | 9.2222 | 14 | 7 | 7.4 | 9 | 10.2 | 11 | 11.8 | 14 | 8 | 8 | 0
2015-02-09 | 2015-07 | 12 | 12 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12 | [12 empty] | 15 | 5 | 4 | 1
2015-02-09 | 2015-07 | 7 | 7 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7 | [12 empty] | 16 | 0 | 0 | 0
2015-02-09 | 2015-07 | 11 | #N/A | 15 | 11 | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11 | [12 empty] | 17 | 0 | 0 | 0
2015-02-10 | 2015-07 | 12 | #N/A | 15 | 12 | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12 | [12 empty] | 18 | 1 | 1 | 0
2015-02-11 | 2015-07 | 7 | 7 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7 | [12 empty] | 19 | 4 | 3 | 1
2015-02-11 | 2015-07 | 9 | 9 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9 | [12 empty] | 20 | 1 | 0 | 1
2015-02-12 | 2015-07 | 14 | 14 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14 | [12 empty] | 21 | 1 | 1 | 0
2015-02-16 | 2015-08 | 11 | 11 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11
2015-02-17 | 2015-08 | 8 | 8 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8 | [12 empty] | Chart labels
2015-02-17 | 2015-08 | 13 | 13 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13 | [12 empty] | Calendar days to complete items (Time in Process) by week
2015-02-17 | 2015-08 | 13 | 13 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13 | [12 empty] | Time in Process Histogram
2015-02-17 | 2015-08 | 12 | #N/A | 15 | 12 | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12 | [12 empty] | Item Time in Process (in calendar days)
2015-02-17 | 2015-08 | 6 | 6 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6 | [12 empty] | Time in Process range for items completed within each week (year-week number)
2015-02-18 | 2015-08 | 7 | 7 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7 | [12 empty] | Time in Process value (calendar days from start to complete)
2015-02-23 | 2015-09 | 12 | 12 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12 | [12 empty] | Stories & Defects Time in Process Histogram
2015-02-23 | 2015-09 | 11 | #N/A | 15 | 11 | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11 | [12 empty] | COMPLETED ITEM Time in Process (IN CALENDAR DAYS)
2015-02-23 | 2015-09 | 13 | 13 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13
2015-02-24 | 2015-09 | 13 | #N/A | 15 | 13 | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13
2015-02-24 | 2015-09 | 13 | 13 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13
2015-02-24 | 2015-09 | 14 | 14 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14
2015-02-25 | 2015-09 | 12 | 12 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12
2015-02-25 | 2015-09 | 15 | #N/A | 15 | 15 | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15
2015-02-25 | 2015-09 | 5 | 5 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5
2015-02-25 | 2015-09 | 5 | 5 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5
2015-02-26 | 2015-09 | 8 | #N/A | 15 | 8 | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8
2015-02-27 | 2015-09 | 4 | #N/A | 15 | 4 | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4
2015-02-27 | 2015-09 | 7 | 7 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7
2015-02-27 | 2015-09 | 7 | 7 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7
2015-02-27 | 2015-09 | 2 | 2 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2
2015-02-27 | 2015-09 | 7 | 7 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7
2015-03-02 | 2015-10 | 5 | 5 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5
2015-03-03 | 2015-10 | 6 | #N/A | 15 | 6 | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6
2015-03-04 | 2015-10 | 20 | #N/A | 15 | 20 | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20
2015-03-04 | 2015-10 | 5 | #N/A | 15 | 5 | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5
2015-03-05 | 2015-10 | 6 | 6 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6
2015-03-05 | 2015-10 | 10 | 10 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10
2015-03-05 | 2015-10 | 8 | 8 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8
2015-03-06 | 2015-10 | 7 | 7 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7
2015-03-06 | 2015-10 | 5 | 5 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5
2015-03-09 | 2015-11 | 7 | 7 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7
2015-03-10 | 2015-11 | 7 | 7 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7
2015-03-10 | 2015-11 | 7 | 7 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7
2015-03-10 | 2015-11 | 5 | 5 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5
2015-03-10 | 2015-11 | 7 | 7 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7
2015-03-10 | 2015-11 | 7 | 7 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7
2015-03-10 | 2015-11 | 4 | #N/A | 15 | 4 | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4
2015-03-10 | 2015-11 | 5 | 5 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5
2015-03-11 | 2015-11 | 2 | 2 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2
2015-03-12 | 2015-11 | 3 | 3 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3
2015-03-12 | 2015-11 | 3 | 3 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3
2015-03-17 | 2015-12 | 13 | #N/A | 15 | 13 | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13
2015-03-17 | 2015-12 | 19 | 19 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19
2015-03-17 | 2015-12 | 19 | 19 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19
2015-03-17 | 2015-12 | 19 | 19 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19
2015-03-19 | 2015-12 | 21 | 21 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21
2015-03-19 | 2015-12 | 8 | 8 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8
2015-03-20 | 2015-12 | 8 | #N/A | 15 | 8 | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8
2015-03-20 | 2015-12 | 8 | #N/A | 15 | 8 | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8
2015-03-20 | 2015-12 | 3 | 3 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3
2015-03-20 | 2015-12 | 8 | 8 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8
2015-03-23 | 2015-13 | 6 | 6 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6
2015-03-24 | 2015-13 | 8 | #N/A | 15 | 8 | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8
2015-03-24 | 2015-13 | 6 | 6 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6
2015-03-26 | 2015-13 | 8 | 8 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8
2015-03-26 | 2015-13 | 8 | 8 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8
2015-03-26 | 2015-13 | 8 | #N/A | 15 | 8 | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8
2015-03-31 | 2015-14 | 13 | 13 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13
2015-04-02 | 2015-14 | 14 | 14 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14
2015-04-02 | 2015-14 | 10 | #N/A | 15 | 10 | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10
2015-04-02 | 2015-14 | 9 | 9 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9
2015-04-02 | 2015-14 | 9 | 9 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9
2015-04-02 | 2015-14 | 8 | 8 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8
2015-04-03 | 2015-14 | 15 | 15 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15
2015-04-06 | 2015-15 | 18 | 18 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18
2015-04-06 | 2015-15 | 7 | 7 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7
2015-04-07 | 2015-15 | 7 | 7 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7
2015-04-08 | 2015-15 | 7 | 7 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7
2015-04-08 | 2015-15 | 19 | #N/A | 15 | 19 | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19
2015-04-08 | 2015-15 | 14 | 14 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14
2015-04-09 | 2015-15 | 9 | 9 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9
2015-04-09 | 2015-15 | 7 | 7 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7
2015-04-09 | 2015-15 | 6 | 6 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6
2015-04-10 | 2015-15 | 8 | 8 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8
2015-04-10 | 2015-15 | 15 | 15 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15
2015-04-10 | 2015-15 | 3 | 3 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3
2015-04-14 | 2015-16 | 6 | 6 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6
2015-04-14 | 2015-16 | 6 | #N/A | 15 | 6 | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6
2015-04-16 | 2015-16 | 10 | 10 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10
2015-04-16 | 2015-16 | 8 | 8 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8
2015-04-16 | 2015-16 | 8 | 8 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8
2015-04-17 | 2015-16 | 15 | 15 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15
2015-04-20 | 2015-17 | 12 | 12 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12
2015-04-22 | 2015-17 | 14 | 14 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14
2015-04-22 | 2015-17 | 8 | 8 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8
2015-04-23 | 2015-17 | 13 | 13 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13
2015-04-23 | 2015-17 | 14 | 14 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14
2015-04-23 | 2015-17 | 10 | #N/A | 15 | 10 | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10
2015-04-23 | 2015-17 | 7 | 7 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7
2015-04-24 | 2015-17 | 10 | 10 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10
2015-04-27 | 2015-18 | 11 | 11 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11
2015-04-27 | 2015-18 | 7 | 7 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7
2015-04-27 | 2015-18 | 10 | 10 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10
2015-04-27 | 2015-18 | 5 | 5 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5
2015-04-28 | 2015-18 | 8 | 8 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8
2015-04-28 | 2015-18 | 8 | 8 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8
2015-04-30 | 2015-18 | 10 | 10 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10
2015-05-01 | 2015-18 | 8 | 8 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8
2015-05-04 | 2015-19 | 7 | 7 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7
2015-05-04 | 2015-19 | 6 | 6 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6
2015-05-05 | 2015-19 | 12 | 12 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12
2015-05-06 | 2015-19 | 8 | 8 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8
2015-05-06 | 2015-19 | 9 | #N/A | 15 | 9 | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9
2015-05-06 | 2015-19 | 8 | #N/A | 15 | 8 | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8
2015-05-08 | 2015-19 | 8 | 8 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8
2015-05-08 | 2015-19 | 9 | 9 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9
2015-05-11 | 2015-20 | 7 | 7 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9,7
2015-05-11 | 2015-20 | 14 | 14 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9,7,14
2015-05-11 | 2015-20 | 12 | 12 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9,7,14,12
2015-05-12 | 2015-20 | 11 | #N/A | 15 | 11 | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9,7,14,12,11
2015-05-12 | 2015-20 | 6 | 6 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9,7,14,12,11,6
2015-05-12 | 2015-20 | 8 | 8 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9,7,14,12,11,6,8
2015-05-13 | 2015-20 | 9 | 9 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9,7,14,12,11,6,8,9
2015-05-13 | 2015-20 | 9 | #N/A | 15 | 9 | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9,7,14,12,11,6,8,9,9
2015-05-13 | 2015-20 | 7 | 7 | 15 | #N/A | 17.4 | #N/A | #N/A | 7,12,12,5,4,6,10,13,13,15,9,12,13,7,7,14,9,12,7,11,12,7,9,14,11,8,13,13,12,6,7,12,11,13,13,13,14,12,15,5,5,8,4,7,7,2,7,5,6,20,5,6,10,8,7,5,7,7,7,5,7,7,4,5,2,3,3,13,19,19,19,21,8,8,8,3,8,6,8,6,8,8,8,13,14,10,9,9,8,15,18,7,7,7,19,14,9,7,6,8,15,3,6,6,10,8,8,15,12,14,8,13,14,10,7,10,11,7,10,5,8,8,10,8,7,6,12,8,9,8,8,9,7,14,12,11,6,8,9,9,7
[5 empty] | #N/A |  | 564 | #N/A
[5 empty] | #N/A |  | 562 | #N/A
[5 empty] | #N/A |  | 558 | #N/A
[5 empty] | #N/A |  | 559 | #N/A
[5 empty] | #N/A |  | 558 | #N/A
[5 empty] | #N/A |  | 558 | #N/A
|  |  | #N/A |  |  |  | #N/A | 564
|  |  | #N/A |  |  |  | #N/A | 563
|  |  | #N/A |  |  |  | #N/A | 558
|  |  | #N/A |  |  |  | #N/A | 557
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
[5 empty] | #N/A |  | #N/A | #N/A
The word Cycle Time means different things to different people. For this spreadsheet, it is the calendar days between two dates. YOU have to define what those dates mean. Does Completed mean delivered to a customer? Does it mean handed off for deployment? The same issue with the start date.Is start when an item is comitted? or when i is created? Please be sure to document what this cycle time means and is captured consistently.
More discussion on the glossary of definitions for cycle time can be found here in a post by Andy Carmichael: http://xprocess.blogspot.co.uk/2015/05/glossary-proposal.html
if you feel strongly this should be renamed TiP (Time in process) then please email me: troy.magennis@focusedobjective.com
Warning: These are array formulas notice the { and } surrounding the formulas.. If you edit them, ctrl+shift+enter to keep them array formulas and working. You can edit one row and then drag the others to match your edits.

## Work in Progress (hidden)
Date | Year-WeekNum | Work in Progress | Count Started | Count Completed | Cum Started | Cumulative Completed | Week Starting Sunday | Year-WeekNum | Min WIP | Avg WIP | Max WIP | Started this Week | Complete this Week | Delta | Start Cumulative | Complete Cumulative
2015-01-14 | 2015-03 | 3 | 3 | 0 | 3 | 0 | 2015-01-11 | 2015-03 | 3 | 3 | 3 | 3 | 0 | -3 | 3 | 0
2015-01-15 | 2015-03 | 3 | 0 | 0 | 3 | 0 | 2015-01-18 | 2015-04 | 3 | 7.2857 | 12 | 10 | 1 | -9 | 13 | 1
2015-01-16 | 2015-03 | 3 | 0 | 0 | 3 | 0 | 2015-01-25 | 2015-05 | 9 | 12.4286 | 15 | 8 | 5 | -3 | 21 | 6
2015-01-17 | 2015-03 | 3 | 0 | 0 | 3 | 0 | 2015-02-01 | 2015-06 | 11 | 12.7143 | 15 | 7 | 11 | 4 | 28 | 17
2015-01-18 | 2015-04 | 3 | 0 | 0 | 3 | 0 | 2015-02-08 | 2015-07 | 9 | 13.1429 | 16 | 12 | 7 | -5 | 40 | 24
2015-01-19 | 2015-04 | 3 | 0 | 0 | 3 | 0 | 2015-02-15 | 2015-08 | 10 | 13 | 16 | 6 | 7 | 1 | 46 | 31
2015-01-20 | 2015-04 | 6 | 3 | 0 | 6 | 0 | 2015-02-22 | 2015-09 | 11 | 12.7143 | 15 | 13 | 16 | 3 | 59 | 47
2015-01-21 | 2015-04 | 6 | 1 | 1 | 7 | 1 | 2015-03-01 | 2015-10 | 13 | 13.8571 | 16 | 10 | 9 | -1 | 69 | 56
2015-01-22 | 2015-04 | 9 | 3 | 0 | 10 | 1 | 2015-03-08 | 2015-11 | 8 | 10.1429 | 15 | 7 | 11 | 4 | 76 | 67
2015-01-23 | 2015-04 | 12 | 3 | 0 | 13 | 1 | 2015-03-15 | 2015-12 | 8 | 10.8571 | 14 | 12 | 10 | -2 | 88 | 77
2015-01-24 | 2015-04 | 12 | 0 | 0 | 13 | 1 | 2015-03-22 | 2015-13 | 11 | 11.2857 | 13 | 6 | 6 | 0 | 94 | 83
2015-01-25 | 2015-05 | 12 | 0 | 0 | 13 | 1 | 2015-03-29 | 2015-14 | 11 | 12.2857 | 14 | 8 | 7 | -1 | 102 | 90
2015-01-26 | 2015-05 | 9 | 1 | 4 | 14 | 5 | 2015-04-05 | 2015-15 | 10 | 11.4286 | 14 | 10 | 12 | 2 | 112 | 102
2015-01-27 | 2015-05 | 9 | 0 | 0 | 14 | 5 | 2015-04-12 | 2015-16 | 10 | 10.4286 | 11 | 6 | 6 | 0 | 118 | 108
2015-01-28 | 2015-05 | 12 | 3 | 0 | 17 | 5 | 2015-04-19 | 2015-17 | 9 | 10.8571 | 13 | 7 | 8 | 1 | 125 | 116
2015-01-29 | 2015-05 | 15 | 4 | 1 | 21 | 6 | 2015-04-26 | 2015-18 | 8 | 10 | 11 | 10 | 8 | -2 | 135 | 124
2015-01-30 | 2015-05 | 15 | 0 | 0 | 21 | 6 | 2015-05-03 | 2015-19 | 11 | 12.7143 | 14 | 10 | 8 | -2 | 145 | 132
2015-01-31 | 2015-05 | 15 | 0 | 0 | 21 | 6 | 2015-05-10 | 2015-20 | 10 | 11.5 | 13 | 6 | 9 | 3 | 151 | 141
2015-02-01 | 2015-06 | 15 | 0 | 0 | 21 | 6
2015-02-02 | 2015-06 | 14 | 2 | 3 | 23 | 9
2015-02-03 | 2015-06 | 14 | 0 | 0 | 23 | 9
2015-02-04 | 2015-06 | 12 | 3 | 5 | 26 | 14
2015-02-05 | 2015-06 | 12 | 2 | 2 | 28 | 16
2015-02-06 | 2015-06 | 11 | 0 | 1 | 28 | 17
2015-02-07 | 2015-06 | 11 | 0 | 0 | 28 | 17
2015-02-08 | 2015-07 | 11 | 0 | 0 | 28 | 17
2015-02-09 | 2015-07 | 9 | 1 | 3 | 29 | 20
2015-02-10 | 2015-07 | 11 | 3 | 1 | 32 | 21
2015-02-11 | 2015-07 | 14 | 5 | 2 | 37 | 23
2015-02-12 | 2015-07 | 15 | 2 | 1 | 39 | 24
2015-02-13 | 2015-07 | 16 | 1 | 0 | 40 | 24
2015-02-14 | 2015-07 | 16 | 0 | 0 | 40 | 24
2015-02-15 | 2015-08 | 16 | 0 | 0 | 40 | 24
2015-02-16 | 2015-08 | 15 | 0 | 1 | 40 | 25
2015-02-17 | 2015-08 | 10 | 0 | 5 | 40 | 30
2015-02-18 | 2015-08 | 10 | 1 | 1 | 41 | 31
2015-02-19 | 2015-08 | 10 | 0 | 0 | 41 | 31
2015-02-20 | 2015-08 | 15 | 5 | 0 | 46 | 31
2015-02-21 | 2015-08 | 15 | 0 | 0 | 46 | 31
2015-02-22 | 2015-09 | 15 | 0 | 0 | 46 | 31
2015-02-23 | 2015-09 | 14 | 2 | 3 | 48 | 34
2015-02-24 | 2015-09 | 11 | 0 | 3 | 48 | 37
2015-02-25 | 2015-09 | 11 | 4 | 4 | 52 | 41
2015-02-26 | 2015-09 | 14 | 4 | 1 | 56 | 42
2015-02-27 | 2015-09 | 12 | 3 | 5 | 59 | 47
2015-02-28 | 2015-09 | 12 | 0 | 0 | 59 | 47
2015-03-01 | 2015-10 | 13 | 1 | 0 | 60 | 47
2015-03-02 | 2015-10 | 13 | 1 | 1 | 61 | 48
2015-03-03 | 2015-10 | 16 | 4 | 1 | 65 | 49
2015-03-04 | 2015-10 | 15 | 1 | 2 | 66 | 51
2015-03-05 | 2015-10 | 14 | 2 | 3 | 68 | 54
2015-03-06 | 2015-10 | 13 | 1 | 2 | 69 | 56
2015-03-07 | 2015-10 | 13 | 0 | 0 | 69 | 56
2015-03-08 | 2015-11 | 13 | 0 | 0 | 69 | 56
2015-03-09 | 2015-11 | 15 | 3 | 1 | 72 | 57
2015-03-10 | 2015-11 | 8 | 0 | 7 | 72 | 64
2015-03-11 | 2015-11 | 8 | 1 | 1 | 73 | 65
2015-03-12 | 2015-11 | 9 | 3 | 2 | 76 | 67
2015-03-13 | 2015-11 | 9 | 0 | 0 | 76 | 67
2015-03-14 | 2015-11 | 9 | 0 | 0 | 76 | 67
2015-03-15 | 2015-12 | 9 | 0 | 0 | 76 | 67
2015-03-16 | 2015-12 | 10 | 1 | 0 | 77 | 67
2015-03-17 | 2015-12 | 8 | 2 | 4 | 79 | 71
2015-03-18 | 2015-12 | 13 | 5 | 0 | 84 | 71
2015-03-19 | 2015-12 | 14 | 3 | 2 | 87 | 73
2015-03-20 | 2015-12 | 11 | 1 | 4 | 88 | 77
2015-03-21 | 2015-12 | 11 | 0 | 0 | 88 | 77
2015-03-22 | 2015-13 | 11 | 0 | 0 | 88 | 77
2015-03-23 | 2015-13 | 11 | 1 | 1 | 89 | 78
2015-03-24 | 2015-13 | 11 | 2 | 2 | 91 | 80
2015-03-25 | 2015-13 | 13 | 2 | 0 | 93 | 80
2015-03-26 | 2015-13 | 11 | 1 | 3 | 94 | 83
2015-03-27 | 2015-13 | 11 | 0 | 0 | 94 | 83
2015-03-28 | 2015-13 | 11 | 0 | 0 | 94 | 83
2015-03-29 | 2015-14 | 11 | 0 | 0 | 94 | 83
2015-03-30 | 2015-14 | 12 | 1 | 0 | 95 | 83
2015-03-31 | 2015-14 | 13 | 2 | 1 | 97 | 84
2015-04-01 | 2015-14 | 14 | 1 | 0 | 98 | 84
2015-04-02 | 2015-14 | 12 | 3 | 5 | 101 | 89
2015-04-03 | 2015-14 | 12 | 1 | 1 | 102 | 90
2015-04-04 | 2015-14 | 12 | 0 | 0 | 102 | 90
2015-04-05 | 2015-15 | 12 | 0 | 0 | 102 | 90
2015-04-06 | 2015-15 | 11 | 1 | 2 | 103 | 92
2015-04-07 | 2015-15 | 11 | 1 | 1 | 104 | 93
2015-04-08 | 2015-15 | 14 | 6 | 3 | 110 | 96
2015-04-09 | 2015-15 | 12 | 1 | 3 | 111 | 99
2015-04-10 | 2015-15 | 10 | 1 | 3 | 112 | 102
2015-04-11 | 2015-15 | 10 | 0 | 0 | 112 | 102
2015-04-12 | 2015-16 | 10 | 0 | 0 | 112 | 102
2015-04-13 | 2015-16 | 11 | 1 | 0 | 113 | 102
2015-04-14 | 2015-16 | 11 | 2 | 2 | 115 | 104
2015-04-15 | 2015-16 | 11 | 0 | 0 | 115 | 104
2015-04-16 | 2015-16 | 10 | 2 | 3 | 117 | 107
2015-04-17 | 2015-16 | 10 | 1 | 1 | 118 | 108
2015-04-18 | 2015-16 | 10 | 0 | 0 | 118 | 108
2015-04-19 | 2015-17 | 10 | 0 | 0 | 118 | 108
2015-04-20 | 2015-17 | 13 | 4 | 1 | 122 | 109
2015-04-21 | 2015-17 | 13 | 0 | 0 | 122 | 109
2015-04-22 | 2015-17 | 12 | 1 | 2 | 123 | 111
2015-04-23 | 2015-17 | 10 | 2 | 4 | 125 | 115
2015-04-24 | 2015-17 | 9 | 0 | 1 | 125 | 116
2015-04-25 | 2015-17 | 9 | 0 | 0 | 125 | 116
2015-04-26 | 2015-18 | 9 | 0 | 0 | 125 | 116
2015-04-27 | 2015-18 | 8 | 3 | 4 | 128 | 120
2015-04-28 | 2015-18 | 9 | 3 | 2 | 131 | 122
2015-04-29 | 2015-18 | 11 | 2 | 0 | 133 | 122
2015-04-30 | 2015-18 | 11 | 1 | 1 | 134 | 123
2015-05-01 | 2015-18 | 11 | 1 | 1 | 135 | 124
2015-05-02 | 2015-18 | 11 | 0 | 0 | 135 | 124
2015-05-03 | 2015-19 | 11 | 0 | 0 | 135 | 124
2015-05-04 | 2015-19 | 13 | 4 | 2 | 139 | 126
2015-05-05 | 2015-19 | 12 | 0 | 1 | 139 | 127
2015-05-06 | 2015-19 | 13 | 4 | 3 | 143 | 130
2015-05-07 | 2015-19 | 14 | 1 | 0 | 144 | 130
2015-05-08 | 2015-19 | 13 | 1 | 2 | 145 | 132
2015-05-09 | 2015-19 | 13 | 0 | 0 | 145 | 132
2015-05-10 | 2015-20 | 13 | 0 | 0 | 145 | 132
2015-05-11 | 2015-20 | 11 | 1 | 3 | 146 | 135
2015-05-12 | 2015-20 | 12 | 4 | 3 | 150 | 138
2015-05-13 | 2015-20 | 10 | 1 | 3 | 151 | 141
Formulas:
Date = IF(ISNUMBER([Date, row above]),IF([Date, row above]+1<=MAX(IndirectStartDates,IndirectCompletedDates),[Date, row above]+1,""),"")
Year-WeekNum = IF(ISNUMBER([Date]),YEAR([Date])&"-"&TEXT(WEEKNUM([Date]),"00"),"")
Year-WeekNum = IF(ISNUMBER([Week Starting Sunday]),YEAR([Week Starting Sunday])&"-"&TEXT(WEEKNUM([Week Starting Sunday]),"00"),"")
Week Starting Sunday = IF(ISNUMBER([Week Starting Sunday, row above]),IF([Week Starting Sunday, row above]+7<=MAX(IndirectStartDates,IndirectCompletedDates),[Week Starting Sunday, row above]+7,""),"")

## Calculations (hidden)
Indirect Completed Dates | Indirect Start Dates | Indirect Work Type | Prior Complete Sunday | Year Complete | WeekNumber Complete | Year-Week Complete | Prior Start Sunday | Year Start | WeekNumber Start | Year-Week Start | Cycle Time (days) | In-Progress Cycle Time
2015-01-21 | 2015-01-14 |  | 2015-01-18 | 2015 | 4 | 2015-04 | 2015-01-11 | 2015 | 3 | 2015-03 | 7 | #N/A
2015-01-26 | 2015-01-14 | Story | 2015-01-25 | 2015 | 5 | 2015-05 | 2015-01-11 | 2015 | 3 | 2015-03 | 12 | #N/A
2015-01-26 | 2015-01-14 | Defect | 2015-01-25 | 2015 | 5 | 2015-05 | 2015-01-11 | 2015 | 3 | 2015-03 | 12 | #N/A
2015-01-26 | 2015-01-21 | Story | 2015-01-25 | 2015 | 5 | 2015-05 | 2015-01-18 | 2015 | 4 | 2015-04 | 5 | #N/A
2015-01-26 | 2015-01-22 | Story | 2015-01-25 | 2015 | 5 | 2015-05 | 2015-01-18 | 2015 | 4 | 2015-04 | 4 | #N/A
2015-01-29 | 2015-01-23 | Story | 2015-01-25 | 2015 | 5 | 2015-05 | 2015-01-18 | 2015 | 4 | 2015-04 | 6 | #N/A
2015-02-02 | 2015-01-23 | Story | 2015-02-01 | 2015 | 6 | 2015-06 | 2015-01-18 | 2015 | 4 | 2015-04 | 10 | #N/A
2015-02-02 | 2015-01-20 | Defect | 2015-02-01 | 2015 | 6 | 2015-06 | 2015-01-18 | 2015 | 4 | 2015-04 | 13 | #N/A
2015-02-02 | 2015-01-20 | Defect | 2015-02-01 | 2015 | 6 | 2015-06 | 2015-01-18 | 2015 | 4 | 2015-04 | 13 | #N/A
2015-02-04 | 2015-01-20 |  | 2015-02-01 | 2015 | 6 | 2015-06 | 2015-01-18 | 2015 | 4 | 2015-04 | 15 | #N/A
2015-02-04 | 2015-01-26 |  | 2015-02-01 | 2015 | 6 | 2015-06 | 2015-01-25 | 2015 | 5 | 2015-05 | 9 | #N/A
2015-02-04 | 2015-01-23 |  | 2015-02-01 | 2015 | 6 | 2015-06 | 2015-01-18 | 2015 | 4 | 2015-04 | 12 | #N/A
2015-02-04 | 2015-01-22 |  | 2015-02-01 | 2015 | 6 | 2015-06 | 2015-01-18 | 2015 | 4 | 2015-04 | 13 | #N/A
2015-02-04 | 2015-01-28 |  | 2015-02-01 | 2015 | 6 | 2015-06 | 2015-01-25 | 2015 | 5 | 2015-05 | 7 | #N/A
2015-02-05 | 2015-01-29 |  | 2015-02-01 | 2015 | 6 | 2015-06 | 2015-01-25 | 2015 | 5 | 2015-05 | 7 | #N/A
2015-02-05 | 2015-01-22 |  | 2015-02-01 | 2015 | 6 | 2015-06 | 2015-01-18 | 2015 | 4 | 2015-04 | 14 | #N/A
2015-02-06 | 2015-01-28 | Defect | 2015-02-01 | 2015 | 6 | 2015-06 | 2015-01-25 | 2015 | 5 | 2015-05 | 9 | #N/A
2015-02-09 | 2015-01-28 |  | 2015-02-08 | 2015 | 7 | 2015-07 | 2015-01-25 | 2015 | 5 | 2015-05 | 12 | #N/A
2015-02-09 | 2015-02-02 |  | 2015-02-08 | 2015 | 7 | 2015-07 | 2015-02-01 | 2015 | 6 | 2015-06 | 7 | #N/A
2015-02-09 | 2015-01-29 | Defect | 2015-02-08 | 2015 | 7 | 2015-07 | 2015-01-25 | 2015 | 5 | 2015-05 | 11 | #N/A
2015-02-10 | 2015-01-29 | Defect | 2015-02-08 | 2015 | 7 | 2015-07 | 2015-01-25 | 2015 | 5 | 2015-05 | 12 | #N/A
2015-02-11 | 2015-02-04 |  | 2015-02-08 | 2015 | 7 | 2015-07 | 2015-02-01 | 2015 | 6 | 2015-06 | 7 | #N/A
2015-02-11 | 2015-02-02 |  | 2015-02-08 | 2015 | 7 | 2015-07 | 2015-02-01 | 2015 | 6 | 2015-06 | 9 | #N/A
2015-02-12 | 2015-01-29 |  | 2015-02-08 | 2015 | 7 | 2015-07 | 2015-01-25 | 2015 | 5 | 2015-05 | 14 | #N/A
2015-02-16 | 2015-02-05 |  | 2015-02-15 | 2015 | 8 | 2015-08 | 2015-02-01 | 2015 | 6 | 2015-06 | 11 | #N/A
2015-02-17 | 2015-02-09 |  | 2015-02-15 | 2015 | 8 | 2015-08 | 2015-02-08 | 2015 | 7 | 2015-07 | 8 | #N/A
2015-02-17 | 2015-02-04 |  | 2015-02-15 | 2015 | 8 | 2015-08 | 2015-02-01 | 2015 | 6 | 2015-06 | 13 | #N/A
2015-02-17 | 2015-02-04 |  | 2015-02-15 | 2015 | 8 | 2015-08 | 2015-02-01 | 2015 | 6 | 2015-06 | 13 | #N/A
2015-02-17 | 2015-02-05 | Defect | 2015-02-15 | 2015 | 8 | 2015-08 | 2015-02-01 | 2015 | 6 | 2015-06 | 12 | #N/A
2015-02-17 | 2015-02-11 |  | 2015-02-15 | 2015 | 8 | 2015-08 | 2015-02-08 | 2015 | 7 | 2015-07 | 6 | #N/A
2015-02-18 | 2015-02-11 |  | 2015-02-15 | 2015 | 8 | 2015-08 | 2015-02-08 | 2015 | 7 | 2015-07 | 7 | #N/A
2015-02-23 | 2015-02-11 |  | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-08 | 2015 | 7 | 2015-07 | 12 | #N/A
2015-02-23 | 2015-02-12 | Defect | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-08 | 2015 | 7 | 2015-07 | 11 | #N/A
2015-02-23 | 2015-02-10 |  | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-08 | 2015 | 7 | 2015-07 | 13 | #N/A
2015-02-24 | 2015-02-11 | Defect | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-08 | 2015 | 7 | 2015-07 | 13 | #N/A
2015-02-24 | 2015-02-11 |  | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-08 | 2015 | 7 | 2015-07 | 13 | #N/A
2015-02-24 | 2015-02-10 |  | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-08 | 2015 | 7 | 2015-07 | 14 | #N/A
2015-02-25 | 2015-02-13 |  | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-08 | 2015 | 7 | 2015-07 | 12 | #N/A
2015-02-25 | 2015-02-10 | Defect | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-08 | 2015 | 7 | 2015-07 | 15 | #N/A
2015-02-25 | 2015-02-20 |  | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-15 | 2015 | 8 | 2015-08 | 5 | #N/A
2015-02-25 | 2015-02-20 |  | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-15 | 2015 | 8 | 2015-08 | 5 | #N/A
2015-02-26 | 2015-02-18 | Defect | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-15 | 2015 | 8 | 2015-08 | 8 | #N/A
2015-02-27 | 2015-02-23 | Defect | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-22 | 2015 | 9 | 2015-09 | 4 | #N/A
2015-02-27 | 2015-02-20 |  | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-15 | 2015 | 8 | 2015-08 | 7 | #N/A
2015-02-27 | 2015-02-20 |  | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-15 | 2015 | 8 | 2015-08 | 7 | #N/A
2015-02-27 | 2015-02-25 |  | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-22 | 2015 | 9 | 2015-09 | 2 | #N/A
2015-02-27 | 2015-02-20 |  | 2015-02-22 | 2015 | 9 | 2015-09 | 2015-02-15 | 2015 | 8 | 2015-08 | 7 | #N/A
2015-03-02 | 2015-02-25 |  | 2015-03-01 | 2015 | 10 | 2015-10 | 2015-02-22 | 2015 | 9 | 2015-09 | 5 | #N/A
2015-03-03 | 2015-02-25 | Defect | 2015-03-01 | 2015 | 10 | 2015-10 | 2015-02-22 | 2015 | 9 | 2015-09 | 6 | #N/A
2015-03-04 | 2015-02-12 | Defect | 2015-03-01 | 2015 | 10 | 2015-10 | 2015-02-08 | 2015 | 7 | 2015-07 | 20 | #N/A
2015-03-04 | 2015-02-27 | Defect | 2015-03-01 | 2015 | 10 | 2015-10 | 2015-02-22 | 2015 | 9 | 2015-09 | 5 | #N/A
2015-03-05 | 2015-02-27 |  | 2015-03-01 | 2015 | 10 | 2015-10 | 2015-02-22 | 2015 | 9 | 2015-09 | 6 | #N/A
2015-03-05 | 2015-02-23 |  | 2015-03-01 | 2015 | 10 | 2015-10 | 2015-02-22 | 2015 | 9 | 2015-09 | 10 | #N/A
2015-03-05 | 2015-02-25 |  | 2015-03-01 | 2015 | 10 | 2015-10 | 2015-02-22 | 2015 | 9 | 2015-09 | 8 | #N/A
2015-03-06 | 2015-02-27 |  | 2015-03-01 | 2015 | 10 | 2015-10 | 2015-02-22 | 2015 | 9 | 2015-09 | 7 | #N/A
2015-03-06 | 2015-03-01 |  | 2015-03-01 | 2015 | 10 | 2015-10 | 2015-03-01 | 2015 | 10 | 2015-10 | 5 | #N/A
2015-03-09 | 2015-03-02 |  | 2015-03-08 | 2015 | 11 | 2015-11 | 2015-03-01 | 2015 | 10 | 2015-10 | 7 | #N/A
2015-03-10 | 2015-03-03 |  | 2015-03-08 | 2015 | 11 | 2015-11 | 2015-03-01 | 2015 | 10 | 2015-10 | 7 | #N/A
2015-03-10 | 2015-03-03 |  | 2015-03-08 | 2015 | 11 | 2015-11 | 2015-03-01 | 2015 | 10 | 2015-10 | 7 | #N/A
2015-03-10 | 2015-03-05 |  | 2015-03-08 | 2015 | 11 | 2015-11 | 2015-03-01 | 2015 | 10 | 2015-10 | 5 | #N/A
2015-03-10 | 2015-03-03 |  | 2015-03-08 | 2015 | 11 | 2015-11 | 2015-03-01 | 2015 | 10 | 2015-10 | 7 | #N/A
2015-03-10 | 2015-03-03 |  | 2015-03-08 | 2015 | 11 | 2015-11 | 2015-03-01 | 2015 | 10 | 2015-10 | 7 | #N/A
2015-03-10 | 2015-03-06 | Defect | 2015-03-08 | 2015 | 11 | 2015-11 | 2015-03-01 | 2015 | 10 | 2015-10 | 4 | #N/A
2015-03-10 | 2015-03-05 |  | 2015-03-08 | 2015 | 11 | 2015-11 | 2015-03-01 | 2015 | 10 | 2015-10 | 5 | #N/A
2015-03-11 | 2015-03-09 |  | 2015-03-08 | 2015 | 11 | 2015-11 | 2015-03-08 | 2015 | 11 | 2015-11 | 2 | #N/A
2015-03-12 | 2015-03-09 |  | 2015-03-08 | 2015 | 11 | 2015-11 | 2015-03-08 | 2015 | 11 | 2015-11 | 3 | #N/A
2015-03-12 | 2015-03-09 |  | 2015-03-08 | 2015 | 11 | 2015-11 | 2015-03-08 | 2015 | 11 | 2015-11 | 3 | #N/A
2015-03-17 | 2015-03-04 | Defect | 2015-03-15 | 2015 | 12 | 2015-12 | 2015-03-01 | 2015 | 10 | 2015-10 | 13 | #N/A
2015-03-17 | 2015-02-26 |  | 2015-03-15 | 2015 | 12 | 2015-12 | 2015-02-22 | 2015 | 9 | 2015-09 | 19 | #N/A
2015-03-17 | 2015-02-26 |  | 2015-03-15 | 2015 | 12 | 2015-12 | 2015-02-22 | 2015 | 9 | 2015-09 | 19 | #N/A
2015-03-17 | 2015-02-26 |  | 2015-03-15 | 2015 | 12 | 2015-12 | 2015-02-22 | 2015 | 9 | 2015-09 | 19 | #N/A
2015-03-19 | 2015-02-26 |  | 2015-03-15 | 2015 | 12 | 2015-12 | 2015-02-22 | 2015 | 9 | 2015-09 | 21 | #N/A
2015-03-19 | 2015-03-11 |  | 2015-03-15 | 2015 | 12 | 2015-12 | 2015-03-08 | 2015 | 11 | 2015-11 | 8 | #N/A
2015-03-20 | 2015-03-12 | Defect | 2015-03-15 | 2015 | 12 | 2015-12 | 2015-03-08 | 2015 | 11 | 2015-11 | 8 | #N/A
2015-03-20 | 2015-03-12 | Defect | 2015-03-15 | 2015 | 12 | 2015-12 | 2015-03-08 | 2015 | 11 | 2015-11 | 8 | #N/A
2015-03-20 | 2015-03-17 |  | 2015-03-15 | 2015 | 12 | 2015-12 | 2015-03-15 | 2015 | 12 | 2015-12 | 3 | #N/A
2015-03-20 | 2015-03-12 |  | 2015-03-15 | 2015 | 12 | 2015-12 | 2015-03-08 | 2015 | 11 | 2015-11 | 8 | #N/A
2015-03-23 | 2015-03-17 |  | 2015-03-22 | 2015 | 13 | 2015-13 | 2015-03-15 | 2015 | 12 | 2015-12 | 6 | #N/A
2015-03-24 | 2015-03-16 | Defect | 2015-03-22 | 2015 | 13 | 2015-13 | 2015-03-15 | 2015 | 12 | 2015-12 | 8 | #N/A
2015-03-24 | 2015-03-18 |  | 2015-03-22 | 2015 | 13 | 2015-13 | 2015-03-15 | 2015 | 12 | 2015-12 | 6 | #N/A
2015-03-26 | 2015-03-18 |  | 2015-03-22 | 2015 | 13 | 2015-13 | 2015-03-15 | 2015 | 12 | 2015-12 | 8 | #N/A
2015-03-26 | 2015-03-18 |  | 2015-03-22 | 2015 | 13 | 2015-13 | 2015-03-15 | 2015 | 12 | 2015-12 | 8 | #N/A
2015-03-26 | 2015-03-18 | Defect | 2015-03-22 | 2015 | 13 | 2015-13 | 2015-03-15 | 2015 | 12 | 2015-12 | 8 | #N/A
2015-03-31 | 2015-03-18 |  | 2015-03-29 | 2015 | 14 | 2015-14 | 2015-03-15 | 2015 | 12 | 2015-12 | 13 | #N/A
2015-04-02 | 2015-03-19 |  | 2015-03-29 | 2015 | 14 | 2015-14 | 2015-03-15 | 2015 | 12 | 2015-12 | 14 | #N/A
2015-04-02 | 2015-03-23 | Defect | 2015-03-29 | 2015 | 14 | 2015-14 | 2015-03-22 | 2015 | 13 | 2015-13 | 10 | #N/A
2015-04-02 | 2015-03-24 |  | 2015-03-29 | 2015 | 14 | 2015-14 | 2015-03-22 | 2015 | 13 | 2015-13 | 9 | #N/A
2015-04-02 | 2015-03-24 |  | 2015-03-29 | 2015 | 14 | 2015-14 | 2015-03-22 | 2015 | 13 | 2015-13 | 9 | #N/A
2015-04-02 | 2015-03-25 |  | 2015-03-29 | 2015 | 14 | 2015-14 | 2015-03-22 | 2015 | 13 | 2015-13 | 8 | #N/A
2015-04-03 | 2015-03-19 |  | 2015-03-29 | 2015 | 14 | 2015-14 | 2015-03-15 | 2015 | 12 | 2015-12 | 15 | #N/A
2015-04-06 | 2015-03-19 |  | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-03-15 | 2015 | 12 | 2015-12 | 18 | #N/A
2015-04-06 | 2015-03-30 |  | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-03-29 | 2015 | 14 | 2015-14 | 7 | #N/A
2015-04-07 | 2015-03-31 |  | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-03-29 | 2015 | 14 | 2015-14 | 7 | #N/A
2015-04-08 | 2015-04-01 |  | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-03-29 | 2015 | 14 | 2015-14 | 7 | #N/A
2015-04-08 | 2015-03-20 | Defect | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-03-15 | 2015 | 12 | 2015-12 | 19 | #N/A
2015-04-08 | 2015-03-25 |  | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-03-22 | 2015 | 13 | 2015-13 | 14 | #N/A
2015-04-09 | 2015-03-31 |  | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-03-29 | 2015 | 14 | 2015-14 | 9 | #N/A
2015-04-09 | 2015-04-02 |  | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-03-29 | 2015 | 14 | 2015-14 | 7 | #N/A
2015-04-09 | 2015-04-03 |  | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-03-29 | 2015 | 14 | 2015-14 | 6 | #N/A
2015-04-10 | 2015-04-02 |  | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-03-29 | 2015 | 14 | 2015-14 | 8 | #N/A
2015-04-10 | 2015-03-26 |  | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-03-22 | 2015 | 13 | 2015-13 | 15 | #N/A
2015-04-10 | 2015-04-07 |  | 2015-04-05 | 2015 | 15 | 2015-15 | 2015-04-05 | 2015 | 15 | 2015-15 | 3 | #N/A
2015-04-14 | 2015-04-08 |  | 2015-04-12 | 2015 | 16 | 2015-16 | 2015-04-05 | 2015 | 15 | 2015-15 | 6 | #N/A
2015-04-14 | 2015-04-08 | Defect | 2015-04-12 | 2015 | 16 | 2015-16 | 2015-04-05 | 2015 | 15 | 2015-15 | 6 | #N/A
2015-04-16 | 2015-04-06 |  | 2015-04-12 | 2015 | 16 | 2015-16 | 2015-04-05 | 2015 | 15 | 2015-15 | 10 | #N/A
2015-04-16 | 2015-04-08 |  | 2015-04-12 | 2015 | 16 | 2015-16 | 2015-04-05 | 2015 | 15 | 2015-15 | 8 | #N/A
2015-04-16 | 2015-04-08 |  | 2015-04-12 | 2015 | 16 | 2015-16 | 2015-04-05 | 2015 | 15 | 2015-15 | 8 | #N/A
2015-04-17 | 2015-04-02 |  | 2015-04-12 | 2015 | 16 | 2015-16 | 2015-03-29 | 2015 | 14 | 2015-14 | 15 | #N/A
2015-04-20 | 2015-04-08 |  | 2015-04-19 | 2015 | 17 | 2015-17 | 2015-04-05 | 2015 | 15 | 2015-15 | 12 | #N/A
2015-04-22 | 2015-04-08 |  | 2015-04-19 | 2015 | 17 | 2015-17 | 2015-04-05 | 2015 | 15 | 2015-15 | 14 | #N/A
2015-04-22 | 2015-04-14 |  | 2015-04-19 | 2015 | 17 | 2015-17 | 2015-04-12 | 2015 | 16 | 2015-16 | 8 | #N/A
2015-04-23 | 2015-04-10 |  | 2015-04-19 | 2015 | 17 | 2015-17 | 2015-04-05 | 2015 | 15 | 2015-15 | 13 | #N/A
2015-04-23 | 2015-04-09 |  | 2015-04-19 | 2015 | 17 | 2015-17 | 2015-04-05 | 2015 | 15 | 2015-15 | 14 | #N/A
2015-04-23 | 2015-04-13 | Defect | 2015-04-19 | 2015 | 17 | 2015-17 | 2015-04-12 | 2015 | 16 | 2015-16 | 10 | #N/A
2015-04-23 | 2015-04-16 |  | 2015-04-19 | 2015 | 17 | 2015-17 | 2015-04-12 | 2015 | 16 | 2015-16 | 7 | #N/A
2015-04-24 | 2015-04-14 |  | 2015-04-19 | 2015 | 17 | 2015-17 | 2015-04-12 | 2015 | 16 | 2015-16 | 10 | #N/A
2015-04-27 | 2015-04-16 |  | 2015-04-26 | 2015 | 18 | 2015-18 | 2015-04-12 | 2015 | 16 | 2015-16 | 11 | #N/A
2015-04-27 | 2015-04-20 |  | 2015-04-26 | 2015 | 18 | 2015-18 | 2015-04-19 | 2015 | 17 | 2015-17 | 7 | #N/A
2015-04-27 | 2015-04-17 |  | 2015-04-26 | 2015 | 18 | 2015-18 | 2015-04-12 | 2015 | 16 | 2015-16 | 10 | #N/A
2015-04-27 | 2015-04-22 |  | 2015-04-26 | 2015 | 18 | 2015-18 | 2015-04-19 | 2015 | 17 | 2015-17 | 5 | #N/A
2015-04-28 | 2015-04-20 |  | 2015-04-26 | 2015 | 18 | 2015-18 | 2015-04-19 | 2015 | 17 | 2015-17 | 8 | #N/A
2015-04-28 | 2015-04-20 |  | 2015-04-26 | 2015 | 18 | 2015-18 | 2015-04-19 | 2015 | 17 | 2015-17 | 8 | #N/A
2015-04-30 | 2015-04-20 |  | 2015-04-26 | 2015 | 18 | 2015-18 | 2015-04-19 | 2015 | 17 | 2015-17 | 10 | #N/A
2015-05-01 | 2015-04-23 |  | 2015-04-26 | 2015 | 18 | 2015-18 | 2015-04-19 | 2015 | 17 | 2015-17 | 8 | #N/A
2015-05-04 | 2015-04-27 |  | 2015-05-03 | 2015 | 19 | 2015-19 | 2015-04-26 | 2015 | 18 | 2015-18 | 7 | #N/A
2015-05-04 | 2015-04-28 |  | 2015-05-03 | 2015 | 19 | 2015-19 | 2015-04-26 | 2015 | 18 | 2015-18 | 6 | #N/A
2015-05-05 | 2015-04-23 |  | 2015-05-03 | 2015 | 19 | 2015-19 | 2015-04-19 | 2015 | 17 | 2015-17 | 12 | #N/A
2015-05-06 | 2015-04-28 |  | 2015-05-03 | 2015 | 19 | 2015-19 | 2015-04-26 | 2015 | 18 | 2015-18 | 8 | #N/A
2015-05-06 | 2015-04-27 | Defect | 2015-05-03 | 2015 | 19 | 2015-19 | 2015-04-26 | 2015 | 18 | 2015-18 | 9 | #N/A
2015-05-06 | 2015-04-28 | Defect | 2015-05-03 | 2015 | 19 | 2015-19 | 2015-04-26 | 2015 | 18 | 2015-18 | 8 | #N/A
2015-05-08 | 2015-04-30 |  | 2015-05-03 | 2015 | 19 | 2015-19 | 2015-04-26 | 2015 | 18 | 2015-18 | 8 | #N/A
2015-05-08 | 2015-04-29 |  | 2015-05-03 | 2015 | 19 | 2015-19 | 2015-04-26 | 2015 | 18 | 2015-18 | 9 | #N/A
2015-05-11 | 2015-05-04 |  | 2015-05-10 | 2015 | 20 | 2015-20 | 2015-05-03 | 2015 | 19 | 2015-19 | 7 | #N/A
2015-05-11 | 2015-04-27 |  | 2015-05-10 | 2015 | 20 | 2015-20 | 2015-04-26 | 2015 | 18 | 2015-18 | 14 | #N/A
2015-05-11 | 2015-04-29 |  | 2015-05-10 | 2015 | 20 | 2015-20 | 2015-04-26 | 2015 | 18 | 2015-18 | 12 | #N/A
2015-05-12 | 2015-05-01 | Defect | 2015-05-10 | 2015 | 20 | 2015-20 | 2015-04-26 | 2015 | 18 | 2015-18 | 11 | #N/A
2015-05-12 | 2015-05-06 |  | 2015-05-10 | 2015 | 20 | 2015-20 | 2015-05-03 | 2015 | 19 | 2015-19 | 6 | #N/A
2015-05-12 | 2015-05-04 |  | 2015-05-10 | 2015 | 20 | 2015-20 | 2015-05-03 | 2015 | 19 | 2015-19 | 8 | #N/A
2015-05-13 | 2015-05-04 |  | 2015-05-10 | 2015 | 20 | 2015-20 | 2015-05-03 | 2015 | 19 | 2015-19 | 9 | #N/A
2015-05-13 | 2015-05-04 | Defect | 2015-05-10 | 2015 | 20 | 2015-20 | 2015-05-03 | 2015 | 19 | 2015-19 | 9 | #N/A
2015-05-13 | 2015-05-06 |  | 2015-05-10 | 2015 | 20 | 2015-20 | 2015-05-03 | 2015 | 19 | 2015-19 | 7 | #N/A
| 2015-05-06 | [5 empty] | 2015-05-03 | 2015 | 19 | 2015-19 | #N/A | 564
| 2015-05-08 | [5 empty] | 2015-05-03 | 2015 | 19 | 2015-19 | #N/A | 562
| 2015-05-12 | [5 empty] | 2015-05-10 | 2015 | 20 | 2015-20 | #N/A | 558
| 2015-05-11 | [5 empty] | 2015-05-10 | 2015 | 20 | 2015-20 | #N/A | 559
| 2015-05-12 | [5 empty] | 2015-05-10 | 2015 | 20 | 2015-20 | #N/A | 558
| 2015-05-12 | [5 empty] | 2015-05-10 | 2015 | 20 | 2015-20 | #N/A | 558
| 2015-05-06 | Defect |  |  |  |  | 2015-05-03 | 2015 | 19 | 2015-19 | #N/A | 564
| 2015-05-07 | Defect |  |  |  |  | 2015-05-03 | 2015 | 19 | 2015-19 | #N/A | 563
| 2015-05-12 | Defect |  |  |  |  | 2015-05-10 | 2015 | 20 | 2015-20 | #N/A | 558
| 2015-05-13 | Defect |  |  |  |  | 2015-05-10 | 2015 | 20 | 2015-20 | #N/A | 557
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
Formulas:
Indirect Completed Dates = IF(AND(TRIM(INDEX(CompletedDateValues,ROW([Indirect Completed Dates])))<>"",INDEX(CompletedDateValues,ROW([Indirect Completed Dates]))>0),INT(INDEX(CompletedDateValues,ROW([Indirect Completed Dates]))),"")
Indirect Start Dates = IF(AND(TRIM(INDEX(StartDateValues,ROW([Indirect Completed Dates])))<>"",INDEX(StartDateValues,ROW([Indirect Completed Dates]))>0),INT(INDEX(StartDateValues,ROW([Indirect Completed Dates]))),"")
Prior Complete Sunday = IF([Indirect Completed Dates]="","",[Indirect Completed Dates] - (WEEKDAY([Indirect Completed Dates])-1))
WeekNumber Complete = IF([Prior Complete Sunday]="","",WEEKNUM([Prior Complete Sunday]))
Prior Start Sunday = IF([Indirect Start Dates]="","",[Indirect Start Dates] - (WEEKDAY([Indirect Start Dates])-1))
WeekNumber Start = IF([Prior Start Sunday]="","",WEEKNUM([Prior Start Sunday]))
In-Progress Cycle Time = IF(OR([Indirect Completed Dates]<>"",[Indirect Start Dates]=""),NA(),MAX(0,IF(DAYS(NOW(),[Indirect Start Dates])=0,SameDayCycleTimeSettingValue,DAYS(NOW(),[Indirect Start Dates]))))
Column A and B grab data from the "Your Data" sheet by indirect reference. This allows you to cut and copy and move rows in your data without corrupting the formula cell references.
This is the prior sunday for the completed date. This date is used as the start of week.
This is a neatly formatted week group name. It makes the week number two digits so that groupds sort chronologically.
This is the number of days between start and end. If the dates are flipped, it returns 0 days. If work finishes on the same day, it uses the value on the Settings tab. Typically this is 0.5 or 1 day.
Need more than 5,000 samples?
We have designed this spreadsheet to grow automatically, except this sheet. You will need to copy-down row 5,001 to as large a row-set as you need. The other sheets and charts are designed to not need touching to increase size.

## Ageing (hidden)
Incomplete Start Date Range
2015-05-06
2015-05-07
2015-05-08
2015-05-09
2015-05-10
2015-05-11
2015-05-12
2015-05-13
FALSE
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!

## More Charts
Percentile
Marker
95%
This chart has "issues" but i want ideas -
1. the series are all different units
2. the date is wrong for the WIP series (off by 1 week)
3. its meant to infer trend and correlation, but because of the values in each unit, it looks like magnitude is important.
4. it doesnt resize to the amount of data.
Thinking: Normalizing each measure 0 (lowest) and 1 (highest) so we are comparing the same ranges as a proportion. And fixing the dates.
If Planned and Unplanned are all 0's, remember to populate the Your Data - Type column, and make sure it matches the settings for Planned and Unplanned Work Types - Settings!C5, C6.

## Settings
Team name
Awesome
Time in Process value to use when items are completed on the same day as being started.
0.5
Planned Work type | Story | Legend label | Stories | Planned work is also the default if NO work type is entered in the Your Data sheet.
Unplanned Work type | Defect | Legend label | Defects
Word for cycle time or time in process on chart labels |  | Names
| Time in Process | Cycle time
Time in Process
TiP
In process time
The word Cycle Time means different things to different people. For this spreadsheet, it is the calendar days between two dates. YOU have to define what those dates mean. Does Completed mean delivered to a customer? Does it mean handed off for deployment? The same issue with the start date.Is start when an item is comitted? or when i is created? Please be sure to document what this cycle time means and is captured consistently.
More discussion on the glossary of definitions for cycle time can be found here in a post by Andy Carmichael: http://xprocess.blogspot.co.uk/2015/05/glossary-proposal.html
if you feel strongly this should be renamed TiP (Time in process) then please email me: troy.magennis@focusedobjective.com