## simulation
Attributes
Attribute | Required | Type | Default | Model Types | Description
name | no | string |  | All | A user defined name for this simulation model. This is for reference only.
locale | no | string | Running O/S Locale | All | ISO locale cuture string. If omitted, the culture of the operating system running the simulatio engine will be used. Setting the locale string allows models to be executed in other cultures without errors due to number formatting. See http://msdn.microsoft.com/en-us/library/ms533052%28v=vs.85%29.aspx for a full list.
Sub Sections
Element | Required |  |  | Model Types | Description
setup | yes |  |  | All | The model section of the simulation.
execute | yes |  |  | All | The execution instruction for simulation.
example | no |  |  | All | The text between these tags will be displayed at the tooltip in the examples ribbon. This is mainly used to add detail about models shipped as examples with the application for learning and reference.
Parent Sections
Element
none

## setup
Attributes
Attribute | Required | Type | Default | Model Types | Description
none.
Sub Sections
Element | Required |  |  | Model Types | Description
backlog | yes |  |  | all | Contains the initial work to be simulated.
columns | yes if Kanban model type |  |  | kanban | Contains the column definitions
defects |  |  |  | all | Contains the defect definitions
addedScopes |  |  |  | all | Contains the addedScope definitions
blockingEvents |  |  |  | all | Contains the blockingEvent definitions
classOfServices |  |  |  | kanban | todo.
phases |  |  |  | all | todo.
iterations |  |  |  | scrum | todo.
forecastDate |  |  |  | all | todo.
Parent Sections
Element
simulation

## columns
Attributes
Attribute | Required | Type | Default | Model Types | Description
none.
Sub Sections
Element | Required |  |  | Model Types | Description
column | at least one. |  |  | kanban | Column definition.
Parent Sections
Element
setup

## defects
Attributes
Attribute | Required | Type | Default | Model Types | Description
none.
Sub Sections
Element | Required |  |  | Model Types | Description
defect | at least one. |  |  | all | A definition of a defect type.
Parent Sections
Element
setup

## defect
Attributes
Attribute | Required | Type | Default | Model Types | Description
Element Text Value | Yes | string |  | all | The defect title for visual display and reporting.
columnId | yes for Kanban | integer |  | kanban | The column id for counting items that pass into this column. Items entering this column are counted to determine if this defect will be generated due to this item.
startsInColumnId | yes for Kanban | integer | 0 | kanban | The column id where the defect (if created) will start. Specify the column by its id value defined in the columns section, or use 0 or -1 to indicate the defect starts from the backlog (the default behavior).
occurrenceType | yes | count, cards, stories, size, points, percentage | count for kanban, points for scrum | all | The measurement unit for occurrence rates as specified in low and high bound or by the distribution. Values: count, cards, stories, size, points, percentage are valid.
occurrenceDistribution | yes if no occurrenceLowBound specified. | a valid distribution name. |  | all | Distribution for the occurrence rate values for this event. Used instead of the low and high bound values when specified. The desitribtuon specified by name must exist in the distributions section.
occurrenceLowBound | yes if no distribution specified. | >0 | 0 | all | The low value of the occurrence rate in units of measure specified in the occurrenceType attribute.
occurrenceHighBound | yes if no distribution is specified. | >0 | 0 | all | The high value of the occurrence rate in units of measure specified in the occurrenceType attribute.
estimateDistribution | yes if no low or high bound specified. | a valid distribution by name |  | scrum | (Scrum only) Distribution for the estimate values of this defect. Used instead of high and low bound estimate values when specified. The distribution specified by name must exist in the distributions section.
estimateLowBound | yes if no distribution specified. | double | 0 | scrum | (scrum only) The low bound for estimate values of this defect.
estimateHighBound | yes if no distribution specified. | double | 0 | scrum | (scrum only) The high bound for estimate values of this defect.
count | no | integer | 1 | all | The number of defects generated each time this defect is triggered. Defaults to 1.
cardMove | no | boolean | FALSE | kanban | If false, the trigger card continues to flow on the board when a defect is triggered; a defect is created in the column specified in the startesInColumnId attribute. If true, the triggering card is immediately placed in the completed list when the defect is created.
phases | no | string |  | all | What phases this event is actively counting potential trigger items. Multiple phases separated by pipe (¦) symbol. All phases are assumed active if left blank.
classOfService | no | string |  | kanban | The classOfService by name the defect will be assigned. By default, defects wil be assigned the same class of service as the triggering card. This attribute allows you to specify another class of service instead.
targetCustomBacklog | no | string |  | all | If assigned, only items that are part of this custom backlog name will be coutned as possible trigger items. This allows defects to target specific types of work at different occurrence rates and estimates. If no targetDeliverable is assigned, all deliverables will be searched for a customBacklog of this text name with the first found being used.
targetDeliverable | no | string |  | all | If assigned, only items that are part of this deliverable name will be coutned as possible trigger items. This allows defects to target specific deliverables at different occurrence rates and estimates.
Sub Sections
Element | Required |  |  | Model Types | Description
columns
Parent Sections
Element
defects

## defect-column
Attributes
Attribute | Required | Type | Default | Model Types | Description
id | yes | a valid column id |  | kanban | The unique column identifier specified in the columns section.
estimateDistribution | yes if no low or high bound specified. | a valid distribution by name |  | kanban | A distribution defined in the distributions section that returns cycle time samples for defects of this type to use when work is in this column.
estimateLowBound | yes if no distribution specified. | double | 0 | kanban | The lower bound for cycle time samples for defects of this type to use when work is in this column.
estimateHighBound | yes if no distribution specified. | double | 0 | kanban | The upper bound for cycle time samples for defects of this type to use when work is in this column.
Sub Sections
Element | Required |  |  | Model Types | Description
none
Parent Sections
Element
defect

## addedScopes
Attributes
Attribute | Required | Type | Default | Model Types | Description
none.
Sub Sections
Element | Required |  |  | Model Types | Description
addedScope | at least one. |  |  | all | A definition of a addedScope type.
Parent Sections
Element
setup

## addedScope
Attributes
Attribute | Required | Type | Default | Model Types | Description
Element Text Value | Yes | string |  | all | The added scope title for visual display and reporting.
occurrenceType | yes | count, cards, stories, size, points, percentage | count for kanban, points for scrum | all | The measurement unit for occurrence rates as specified in low and high bound or by the distribution. Values: count, cards, stories, size, points, percentage are valid.
occurrenceDistribution | yes if no occurrenceLowBound specified. | a valid distribution name. |  | all | Distribution for the occurrence rate values for this event. Used instead of the low and high bound values when specified. The desitribtuon specified by name must exist in the distributions section.
occurrenceLowBound | yes if no distribution specified. | >0 | 0 | all | The low value of the occurrence rate in units of measure specified in the occurrenceType attribute.
occurrenceHighBound | yes if no distribution is specified. | >0 | 0 | all | The high value of the occurrence rate in units of measure specified in the occurrenceType attribute.
estimateDistribution | yes if no low or high bound specified. | a valid distribution by name |  | scrum | (Scrum only) Distribution for the estimate values of this added scope item Used instead of high and low bound estimate values when specified. The distribution specified by name must exist in the distributions section.
estimateLowBound | yes if no distribution specified. | double | 0 | scrum | (scrum only) The low bound for estimates of this added scope items. New items will use this as the lowest possible value when randomly choosing an estimate value.
estimateHighBound | yes if no distribution specified. | double | 0 | scrum | (scrum only) The high bound for estimates of this added scope items. New items will use this as the highest possible value when randomly choosing an estimate value.
count | no | integer | 1 | all | The number of added scope items generated each time this added scope is triggered. Defaults to 1.
phases | no | string |  | all | What phases this event is actively counting potential trigger items. Multiple phases separated by pipe (¦) symbol. All phases are assumed active if left blank.
classOfService | no | A valid class of service by name |  | kanban | The classOfService by name new items will be assigned. By default, new items will be assigned the same class of service as the triggering card. This attribute allows you to specify another class of service instead.
customBacklog | no | A valid customBacklog by name |  | all | The customBacklog by name the added scope items will be assigned. By default, new items wil be assigned the same customBacklog as the triggering card. This attribute allows you to specify another customBacklog instead. If deliverable is not specified, all deliverables will be searched with the first customBacklog found by name used.
deliverable | no | A valid deliverable by name. |  | all | The deliverable by name the added scope items will be assigned. By default, new items wil be assigned the same deliverable as the triggering card. This attribute allows you to specify another deiliverable instead.
targetCustomBacklog | no | string |  | all | If assigned, only items that are part of this custom backlog name will be coutned as possible trigger items. This allows added scopes to target specific types of work at different occurrence rates and estimates. If no targetDeliverable is assigned, all deliverables will be searched for a customBacklog of this text name with the first found being used.
targetDeliverable | no | string |  | all | If assigned, only items that are part of this deliverable name will be coutned as possible trigger items. This allows added scopes to target specific deliverables at different occurrence rates and estimates.
Sub Sections
Element | Required |  |  | Model Types | Description
none.
Parent Sections
Element
addedScopes

## blockingEvents
Attributes
Attribute | Required | Type | Default | Model Types | Description
none.
Sub Sections
Element | Required |  |  | Model Types | Description
blockingEvent | at least one. |  |  | all | A definition of a blockingEvent type.
Parent Sections
Element
setup

## blockingEvent
Attributes
Attribute | Required | Type | Default | Model Types | Description
Element Text Value | Yes | string |  | all | The blocking event title reporting.
columnId | yes for Kanban | integer |  | kanban | The column id for counting and blocking items that pass into this column. Items entering this column are counted to determine if this blocking event will be trigger due to this card in this column.
occurrenceType | yes | count, cards, stories, size, points, percentage | count for kanban, points for scrum | all | The measurement unit for occurrence rates as specified in low and high bound or by the distribution. Values: count, cards, stories, size, points, percentage are valid.
occurrenceDistribution | yes if no occurrenceLowBound specified. | a valid distribution name. |  | all | Distribution for the occurrence rate values for this event. Used instead of the low and high bound values when specified. The desitribtuon specified by name must exist in the distributions section.
occurrenceLowBound | yes if no distribution specified. | >0 | 0 | all | The low value of the occurrence rate in units of measure specified in the occurrenceType attribute.
occurrenceHighBound | yes if no distribution is specified. | >0 | 0 | all | The high value of the occurrence rate in units of measure specified in the occurrenceType attribute.
estimateDistribution | yes if no low or high bound specified. | a valid distribution by name |  | all | Distribution for the estimate blocking time values of this blocking event. Used instead of high and low bound estimate values when specified. The distribution specified by name must exist in the distributions section.
estimateLowBound | yes if no distribution specified. | double | 0 | all | The low bound for blocking time estimates of this blocking event. Triggered cards will use this as the lowest possible value when randomly choosing an estimate value.
estimateHighBound | yes if no distribution specified. | double | 0 | all | The high bound for blocking time estimates of this blocking event. Triggered cards will use this as the highest possible value when randomly choosing an estimate value.
phases | no | string |  | all | What phases this event is actively counting potential trigger items. Multiple phases separated by pipe (¦) symbol. All phases are assumed active if left blank.
targetCustomBacklog | no | string |  | all | If assigned, only items that are part of this custom backlog name will be coutned as possible trigger items. This allows blocking events to target specific types of work at different occurrence rates and estimates. If no targetDeliverable is assigned, all deliverables will be searched for a customBacklog of this text name with the first found being used.
targetDeliverable | no | string |  | all | If assigned, only items that are part of this deliverable name will be coutned as possible trigger items. This allows blocking events to target specific deliverables at different occurrence rates and estimates.
blockDefects | no | yes,true,no,false | yes | all | If set to true or yes, defects are counted as part of the occurrence rate calculations, otherwise defects are ignored.
blockWork | no | yes,true,no,false | yes | all | If set to true or yes, work items are counted as part of the occurrence rate calculations, otherwise work items are ignored.
blockAddedScope | no | yes,true,no,false | yes | all | If set to true or yes, added scope items are counted as part of the occurrence rate calculations, otherwise added scope items are ignored.
Sub Sections
Element | Required |  |  | Model Types | Description
none.
Parent Sections
Element
blockingEvents

## column
Attributes
Attribute | Required | Type | Default | Model Types | Description
id | yes | integer |  | kanban | The unique column identifier. Columns are referenced in other attributes by this id, and columns are ordered when simulating and display from lowest id to highest. A useful tip is to allocate these as 10, 20, 30, etc. to have plenty of space to add new columns in between entries.
estimateDistribution | yes if no low or high bound specified. | a valid distribution by name |  | kanban | A distribution defined in the distributions section that returns cycle time samples for work is in this column unless overriden by a custom backlog or defect or class of service.
estimateLowBound | yes if no distribution specified. | double | 0 | kanban | The lower bound for cycle time samples for work in this column unless overriden by a custom backlog or defect or class of service.
estimateHighBound | yes if no distribution specified. | double | 0 | kanban | The upper bound for cycle time samples for for work in this column unless overriden by a custom backlog or defect or class of service.
skipPercentage | no | 0 to 100 | 0 | kanban | The percentage of time items skip this column. Often used to model columns that have work skipping them for various reasons, but these work types are explicitely defined as a custom backlog of work type. For example, some work may require updating documentation, by observing a real system you see that only 10% of items perform this step. You would specify a skipPercentage of 90.
displayWidth | no | 1 | 1 | kanban | The width of the column in cards wide to show in the visual simulation screen.
wipLimit | yes | integer |  | kanban | The number of items allowed in this column at the same time. This limit will not be exceeded for any work type, whether its completed or blocked. Visually, the wipLimit is displayed as gray dotted outlined squares on the kanban surface. During simulation, empty positions are filled when possible. Set this value to -1 to have no limit specified.
buffer | no | true or false |  | kanban | Determines if this column is a buffer or queue column. If set to true, work entering this column is IMMEDIATELY flagged as complete. If set to false, work entering this column will begin comleting based on the relavent cycle time estimate values.
replenishInterval | no | integer |  | kanban | The number of intervals required to complete between new work will move into this this column. For example, if empty positions in a column are replenished every 5 days, set this value to 5. This value is in intervals, and is NOT days specifically. Set the number of intervalsPerDay in the forecastDate section to control the day to interval ratio.
completeInterval | no | integer |  | kanban | The number of intervals required to complete between work moving out of this column. For example, if completed work in a column is purged every 5 days, set this value to 5. This value is intervals, and is NOT days specifically. Set the number of intervalsPerDay in the forecastDate section to control the day to interval ratio.
Sub Sections
Element | Required |  |  | Model Types | Description
none
Parent Sections
Element
columns

## backlog
Attributes
Attribute | Required | Type | Default | Model Types | Description
type | yes | custom or simple |  | all | Two types of backlog definition styles, Custom or Simple. Simple allows an initial count of items to be placed in the backlog by specifying the attribute simpleCount otherwie an error will be reported. Complex backlog allows multiple deliverables and custom entries to be defined. Complex is the the most common type of backlog to define.
simpleCount | if type = simple | integer | 100 | all | If the type attribute = "simple" then this attribute speciies the initial backlog size. This is the simplest backlog to specify and is rarely enough to be useful, but ideal for initial testing of models and examples.
shuffle | no | true or false | TRUE | all | Determines if the backlog is initially randomized (shuffled). If true, the backlog will be sorted in a random order for all entries with the SAME order attribute value.
nameFormat | no | string | Story {0} | all | This string controls how the name appears on the cards in the visual simulation display. Text is displayed as shown and special placeholders are replaced during simulation with special values. {0} = running card index, {1} = the card name, {2} = the order of the custom backlog entry, {3} = the deliverable name, {4} = the deliverable order.
Sub Sections
Element | Required |  |  | Model Types | Description
deliverable | if no custom entry |  |  | all
custom | if no deliverable entry |  |  | all
Parent Sections
Element
setup

## deliverable
Attributes
Attribute | Required | Type | Default | Model Types | Description
name | yes | string |  | all | A name for this deliverable. This name is used when specifying this deliverable as a reference in other attributes, and can be displayed in the name of each story by specifying the {3} special tag in the nameFormat attribute of the backlog section.
dueDate | no | date |  | kanban | A date formatted in the way specified in the dateFormat attribute of the execute section. This date is ues as an ordering value for all deliverables with the SAME priority order value.
earliestStartDate | no | date |  | kanban | A date formatted in the way specified in the dateFormat attribute of the execute section. This date will inhibit items in this deliverable being started anytime BEFORE this date. This is used to specify date dependent constraints and risks. Items of lower priority will be allowed to start unless a pre-requisite inhibits them.
skipPercentage | no | 0 to 100 | 0 | all | The percentage of times this deliverable is omitted from the initial backlog. This allows some work to only be included some of the time and is ostent used to simulate risk factors that may or may nor come true given some probability.
order | no | integer | maximum | all | The sort order deliverables will be prioritized from lowest to highest. The default value of deliverables that omit this attribute will be the highest allowed and last.
preRequisiteDeliverables | no | string |  |  | A deliverable or set of deliverables separated by a pipe symbol (¦) that will inibit this deliverable from being able to start until they are totally completed (the last card or defect on the completed list). This can be used to model work that has strict dependency order.
Sub Sections
Element | Required |  |  | Model Types | Description
custom
Parent Sections
Element
backlog

## custom
Attributes
Attribute | Required | Type | Default | Model Types | Description
name | no | string |  | all | A name for this custom backlog entry This name is used when specifying this as a customBacklog reference in other attributes.
count | no | integer | 1 | all | The number of items added to the backlog with this custom type.
estimateDistribution | note a | valid distribution by name |  | scrum | A distribution defined in the distributions section that returns story point samples for this backlog to use when simulating iterative scrum models. This attribute is ignored when modeling cycle-time.
estimateLowBound | note a | double |  | scrum | The lower bound used when generating story point samples for this backlog to use when simulating iterative scrum models. This attribute is ignored when modeling cycle-time.
estimateHighBound | note a | double |  | scrum | The upper bound used when generating story point samples for this backlog to use when simulating iterative scrum models. This attribute is ignored when modeling cycle-time.
percentageLowBound | note a | double |  | kanban
percentageHighBound | note a | double |  | kanban
order | no | integer |  | all
classOfService | no | valid class of service by name |  | kanban
dueDate | no | date |  | all
valueLowBound | 0 | double |  | all
valueHighBound | 0 | double |  | all
completed | no | true or false | false | all | If set to true, this custom entry is considered completed at the start of simulation. Often used to pre-populate progress when modelling partially completed projects.
initialColumn |  | valid column id
note a: | It is mandatory to specify a distribution, an estimate or a percentage. One estimation type is necessary. This is only for Scrum models. Estimates are at a column level for Kanban models, except for percentage.
Sub Sections
Element | Required |  |  | Model Types | Description
column
Parent Sections
Element
deliverable
backlog

## custom-column
Attributes
Attribute | Required | Type | Default | Model Types | Description
id | yes | a valid column id |  | kanban | The unique column identifier specified in the columns section.
estimateDistribution | yes if no low or high bound specified. | a valid distribution by name |  | kanban | A distribution defined in the distributions section that returns cycle time samples for this backlog to use when work is in this column.
estimateLowBound | yes if no distribution specified. | double | 0 | kanban | The lower bound for cycle time samples for this backlog to use when work is in this column.
estimateHighBound | yes if no distribution specified. | double | 0 | kanban | The upper bound for cycle time samples for this backlog to use when work is in this column.
skipPercentage | no | 0 to 100 | 0 | kanban | The percentage of time items of the backlog type skip this column. This is most often used to skip columns by setting it to 100 (100%, skip always). For example, some work has no development work but requires testing.
Sub Sections
Element | Required |  |  | Model Types | Description
none
Parent Sections
Element
custom

## execute
Attributes
Attribute | Required | Type | Default | Model Types | Description
type | yes | kanban or scrum | kanban | all | Determines the type of model to simulate. Kanban models simulate cycle-time based systems, scrum simulates iterative based point systems.
limitIntervalsTo | no | integer | 9000 | all | Stops simulating after this number of time intervals are processed. This is to avoid models that will never finish (more work added than processed).
intervalUnit | no | string | days | all | The unit of time each simulation interval represents. This doesn't impact simulation in any way and is used when presenting a time interval in visual modelling.
decimalRounding | no | integer | 2 | all | The number of decimal places numeric results are reported to.
currencyFormat | no |  | C2 | all | The windows numeric formatting pattern for currency values. The string follows the standard defined http://msdn.microsoft.com/en-us/library/dwhawy9k%28v=vs.110%29.aspx. C2 is the default value for currency which is the executing machines currency symbol and separators including 2 decimal places.
percentageFormat | no |  | P | all | The windows numeric formatting pattern for percentage values. The string follows the standard defined http://msdn.microsoft.com/en-us/library/dwhawy9k%28v=vs.110%29.aspx.
aggregationValue | no | average, median, fifth, thentyFith, seventyFifth, ninetyFifth | average | all | Monte Carlo simulation execute the model multiple times and aggregates the results. This attribute allows you to specify which value is reported as the monte carlo results. For example, the default is average. This means that the results for monte carlo simulation will be the average values for each individual run. This is an advanced feature and It is rare that you will need to alter this from its default.
deliverables | no |  |  | all | A deliverable by name or set of deliverables by name separated by a pipe (¦) symbol to include when simulating. This is most often used to model a subset of modelled deliverables for planning.
returnResults | no |  |  | all | This is an advanced setting used for performance improvement. It restricts the results that are returned by eliminating any result value types not necessary. It is recommended this is NOT altered.
dateFormat | no |  | yyyyMMdd | all | The windows date format string controlling how dates will be parsed and reported. This setting allows model to be used internationally where the machine running the simulation may not be known at modeling time. By entering dates in this format in the model they will be safely parsed on machines using different date format settings. See http://msdn.microsoft.com/en-us/library/az4se3k1(v=vs.110).aspx for full details. The default is YYYYMMdd or 20141201 for 1st December 2014.
pullOrder | no | afterOrdering, true, false, fifo, fifoStrict | afterOrdering | kanban | This is an advanced setting used to manage the policy around what order work items are pulled onto the board and through columns.
defaultDistribution | no | uniform or weibull | uniform | kanban | When cycle time estimates are defined as estimateLowBound and estimateHighBound, this setting determines if a uniform distribution sample is chosen between the ranges or a weibull sample between the range is chosen. Uniform is the default and safest (from avoiding an underestimate perspective), but if estimate ranges are wide it can be too pessimistic. Setting this attribute to weibull infers that a left weighted long tail distribution that is commonly found in knowledge work is more likely and give a more reliable result.
activePositionsCompletePercentage |  | 0 to 100 | 0 | all | Traditionally every piece of work must be in the completed column before simulation is deemed complete. For some models, a few pieces of work can elongate and inhibit completion for extended time. In the real world, these items are rare. This attribute in combination with the completePercentage helps flag simulation is complete ealier. This attribute allows complete to be defined whilst some work is still in on-the board. It is the percentage of WIP positions containing work items. 0% means there are NO active positions on the board, 10% means complete when completePErcentage is reached and the simulation has LESS than 10% of posiitons active.
completePercentage | no | 0 to 100 | 100 | all | Traditionally every piece of work must be in the completed column before simulation is deemed complete. For some models, a few pieces of work can elongate and inhibit completion for extended time. In the real world, these items are rare. This attribute in combination with the activePositionsCompletePercentage helps flag simulation is complete ealier. This attribute allows complete to be defined whilst some work is still in progress or even in the backlog. 100% means all work complete. 95% means 95% of work originally in the backlog at the start of simulation is complete.
basePath | no |  |  | all | When a file path is specified in an attribute, this value allows the relative base path to be assigned. If this is left blank, the simulation engine path is used as the default base path.
shufflePositions | no | afterOrdering, true, false, fifo, fifoStrict | afterOrdering | kanban | This is an advanced setting used to manage the policy around what order work items are analyzed when pulling work through the columns.
Sub Sections
Element | Required |  |  | Model Types | Description
visual |  |  |  |  | todo.
monteCarlo |  |  |  |  | todo.
addStaff |  |  |  |  | todo.
sensitivity |  |  |  |  | todo.
ballot |  |  |  |  | todo.
Parent Sections
Element
simulation |  |  |  |  | The parent tage for all simML files.