## Readme
Staff and Team Capability Matrix
Version
| 1 | Initial Version
| 1.1 | Made all settings definable in the Setting tab.
| 1.2 | Added planning and stabilizing team advice.
| 2 | Made input vertical to match survey sheet and put results on the same page
What is this: This spreadsheet helps to probabilistically forecast how long it will take to complete features and stories based on range estimates.
How does it work? Given your estimates, this spreadsheet hypothetically completes all work 500 times. It calculates likelihood result as the number of simulated trials that finished on or before a given date.
Why is this better than burndowns and traditional Agile forecasting? Most forecasting techniques give a single date result and hide the likelihood of that date. Most often the date given as the result is 50% because work is divided by an average (or median). Thats the odds of a toin-coss. This method allows the reader to choose the amount of schedule risk they wish to sign-up for. 85% is a common middle ground used in the industry.
Is it reliable? It has no mathematical errors (that we know of!), and all we guarentee is its better than intuition alone and better than simple regression models. But, help us improve it by letting us know when it misses the actual results you are seeing.
How to: Fill in the orange boxes in the Forecast worksheet and read off the dates in the results table adjacent to the likelihood/certainty you think is appropriate. 85% is a common industry level of certainty used.
What is throughput? Where do I get that data? Throughput is the number of DONE stories completed by a team per week or per sprint (you choose in this spreadsheet, default is per week). We will be providing a viz that gathers this data for your team. Stay tuned.
What is this: This spreadsheet aims to quantify the staff risks due to specialist skills. It is a simple assessment of current capabilities, highlighting when you have only one expert!
Instructions:
Step 1: Enter the people/team names and the skillsets in the Settings worksheet.
Step 2: Either print out the Survey Sheet and distribute, or get the parties in a room and choose the current capability level for the matrix of teams/people vs capability/skill in the Current Assessment worksheet.
Step 3: The spreadsheet calculates the number of people you have who can create, maintain or are positioned to learn and develop each skill. Make decisions based on the analysis at the bottom og the Current Assessment worksheet.
General advice says that if the capability need is present, then 2 people minimum should be able to create and maintain. If new work isn't expected in an area, 2 maintainers might be all that is necessary. If you only have a single team/person who can do a capability, you need to train more in order to avoid the risk of that resource not being available (illness, sickness, hit by bus, etc).
Giving Feedback
Created by Troy Magennis and Adam Yuret. It is based on the concepts discussed by Chris Matts around staff liquidity: http://theitriskmanager.wordpress.com/2013/11/24/introducing-staff-liquidity-1-of-n/
Work licensed under a Creative Commons Attribution-NonCommercial-ShareAlike 4.0 International License.
Details here: http://creativecommons.org/licenses/by-nc-sa/4.0/ and
http://creativecommons.org/licenses/by-nc-sa/4.0/legalcode
Get more tools like this from: http://bit.ly/SimResources
About us: Focused Objective LLC offers tools, training and expert advice on metrics, risk and forecasting. We have more advanced tools to model Agile teams and projects that help analyze staffing options and risk, and a proven track record of positive results. We are always happy to discuss next steps and training opportunities should this tool prove useful. See our website: http://www.focusedobjective.com or email me at troy.magennis@focusedobjective.com.
Please don't by this book on Amazon; its out of date (we leave it there for people who insist on a hard-copy). Go to Bit.ly/agilesim as it says on the card and download for free.
Also - please hire us! we can help with metrics, forecasting and risk management of Agile projects. We are able to make these tools free because we are called upon for our expertise often. Either way, talk to us first before looking elsewhere!

## Settings
People / Teams | Skills and Expertise | Current Knowledge Levels | Willingness to Learn Levels
Person 1 | CSS | Know nothing | I'd quit rather than do this…
Person 2 | Javascript | Can run and use the tools needed | Actively Avoid, unless coerced…
Team 1 | DB Backup/Restore | Can tweak it or do easy bug fixes | Willing to learn
|  | Can start from nothing and create | Strongly Interested
|  | Can teach others | Please, Please, Please…
Some people use a 1 to 5 rating for this.
You are trying t find who can teach others, NOT raw talent.
Advice: Pick skills that you need to deliver as a team. Think of skills that
new hires might need to learn. You are planning skill development no
impressing everyone with all things people CAN do.
List the levels of current knowledge here. Order from top (lowest skill level) to bottom (highest skill level)
List the levels of willingness here. Order from top (highest desire) to bottom (lowest desire). 5 max.
List the team members if assessing a team, or the team names if assessing organizations count as resources with ability to perform a skill or task. 12 max (unless you expand the spreadsheet). Consider making the survey anonymous for more honest data.
List skillsets, expertise, or tasks to assess capability of people/teams. 17 max (unless you expand the spreadsheet.

## Survey Sheet
Capability Survey For Printing (enter skills in the Settings worksheet)
Team Name: |  |  | Your Name (optional)
For each capability choose from the list of CURRENT skill level values. If in doubt, err low (left)!
| Know nothing | Can run and use the tools needed | Can tweak it or do easy bug fixes | Can start from nothing and create | Can teach others
CSS
Javascript
DB Backup/Restore
For each skill, choose from the list of DESIREABLE values. If in doubt, err high (right)!
| I'd quit rather than do this… | Actively Avoid, unless coerced… | Willing to learn | Strongly Interested | Please, Please, Please…
CSS
Javascript
DB Backup/Restore

## Input and results
Analysis | [5 empty] | Inputs
Skill | Counts |  |  | Capability |  | Enter survey results in this table. Pick the value from the drop-down in each cell.
Name | Teach & Create | Do & Maintain | Novice & Learner | Risk Score |  | Skill | Person 1 | Person 2 | Team 1
CSS | 0 | 1 | 0 | 2 |  | CSS | Know nothing | Know nothing | Can tweak it or do easy bug fixes
Javascript | 2 | 0 | 0 | 7 |  | Javascript | Can teach others | Can start from nothing and create | Know nothing
DB Backup/Restore | 1 | 1 | 1 | 6 |  | DB Backup/Restore | Can run and use the tools needed | Can tweak it or do easy bug fixes | Can start from nothing and create
Risk Legend
|  |  |  | 1 | Most significant gap in skills
2
3
4
|  |  |  | 5 | Least significant gap in skills
For planning ideas and advice on building stable teams, see this sheet.
General guidelines: 0 = bad, 1 = single point of failure, >2 cool!
Teach & Create: These are the people/teams who can create new work and teach others. You need at least one (right?). Are you able to cope if that person is off sick or vacation? If not, then train up a maintainer or bench employee?
Do & Maintain: These are the people/teams who can maintain current work, but struggle to create new work. If new work isn't expected, it may be ok to have no captains but a crew of maintainers. Still, one seems too risky? Grow from the bench.
Novice & Learner (bench): These are the people/teams who although haven't got this skill yet, have the tools required to perform this task if mentored or paired with a Player. If you have too few Captains and Players, you need to develop these urgently.

## Planning and Stabilizing Teams
Stage 1 - Getting to an Effective and Resiliant Team (Stabilizing Now and Managing Risks)
Urgency (Redder = more urgent)
If skill is growing in demand, prepare the bench strength -
| Teachers |  |  |  | Teachers
Doers | 0 | 1 | 2+ | Novices | 0 | 1 | 2+
0 | 9 | 7 | 3 | 0 | 9 | 7 | 3
1 | 8 | 5 | 2 | 1 | 8 | 5 | 2
2+ | 6 | 4 | 1 | 2+ | 6 | 4 | 1
Goals -
Have 2+ people who are Doer's for each skill on the team. If creating new innovations, have at least 1 teacher for each skill.
If a skill is in demand, have at least 1 (preferably 2) teachers on the team (or available), and know who is willing (or able) to be a novice in training to doer.
Know what skills might be needed elsewhere in the company, as your team members might be pulled off at short notice.
Know what skills might be needed to fix incoming defects or production issues when rolling to customer usage.
Know how long (and plan to reduce) the onboarding time from novice to doer levels, prioritized by the skills most anticipated in need for the future.
Its *not* a goal to have everyone at Teacher level for every skill; Your goal is to have a resiliant team given un-planned disruptions and the next feature demands.
Questions -
How do I protect the skilsets where the team is at bare minimum (urgency > 5)
Will this skill be needed more in the future?
How many people are needed to maintain the rate of production support?
Is support for this skill needed 24/7 or just during normal hours?
Is there a Teacher level person in each location, or at least within the same timezone if a Doer has questions?
Will this skill be needed by other important projects if they get into difficulty?
How long does it take a teacher to train a novice into Doer level?
How long as a Doer does it take to be a Teacher? Can this be accelerated?
How much effort does it take a teacher to create a doer from a novice, Do I lose the Teacher completely?
Do we need teacher level on-staff, or can we obtain the training from external consultant?
Is this skill growing in numbers on the hiring community, or decreasing?
What skills might be needed in higher numbers for stabilization or initial production support? (where will the bug load come from)
How can onboarding be accelerated for this skill.
Stage 2 - Gowing a Team to Split, Splitting and the Restabilizing
Urgency (Redder = more urgent)
How many novices do we have ready to fill needed skills?
Doer
Novice | 0 | 1 | 2+
0 | 9 | 7 | 3
1 | 8 | 5 | 2
2+ | 6 | 4 | 1
Goals -
Build the bench of Novices who can become doers, and promote senior Doers to Teachers.
Grow a team to have 1 Teacher level for each skill, and 1 Doer level ready to become a Teacher.
Grow each skill to have at least 3 Doer's in all needed skill areas, even if you don't need that many. You need to be plump on skills to split!
Split the teams and revisit Stage 1 - Getting to a Stable and Resiliant Team as soon as possible.
Questions -
Who is willing to learn an in-demand skill (become novices)?
Which Doer's are candidates to become Teacher level for a skill?
Can I loan a Teacher from another team to upskill my Doer's or mentor a new Teacher after splitting the team?
Is one location better than another to split?
Todo: Planning new teams.

## Calculations
Teach & Create | Do & Maintain | Novice & Learner |  | Person 1 | Person 2 | Team 1 | [9 empty] | Totals
0 | 1 | 0 | CSS | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
2 | 0 | 0 | Javascript | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
1 | 1 | 1 | DB Backup/Restore | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0